T.C.K Sdn Bhd x MAIA

Project Scope and Meeting Links

Prepared for implementation handover | 1 July 2026

# 1. Package Contents

| File | Purpose |
| --- | --- |
| 01_Signed Proposal - T.C.K Sdn Bhd x MAIA Proposal.pdf | Signed proposal and commercial agreement. |
| 02_Project Scope and Meeting Links - T.C.K Sdn Bhd x MAIA.docx | Implementation scope summary, project boundaries, and meeting recording links. |

# 2. Project Overview

Client: T.C.K Sdn Bhd

Product: MAIA

Signed proposal date: 26 June 2026

Project intent: Implement MAIA as an internal B2B order processing and control layer that sits on top of AutoCount. AutoCount remains the source of truth, while MAIA helps users process WhatsApp-driven orders more cleanly, prepare draft sales orders, apply agreed pricing and approval rules, support document handling, and improve operational visibility.

# 3. Business Context

Orders are currently received mainly through WhatsApp groups.

Orders are manually forwarded internally and keyed into AutoCount before documents are generated.

Warehouse picking is coordinated separately, commonly through manually compiled Excel or Word-style lists.

Approximate volume discussed: around 50 orders per day and roughly 1,000 orders per month.

The operational risk is mainly manual checking, repeated key-in, inconsistent pricing handling, and fragmented visibility across WhatsApp, AutoCount, and internal follow-ups.

# 4. Phase 1 Scope

| Area | Included Scope |
| --- | --- |
| Order intake | Internal order intake forwarding from customer WhatsApp messages to MAIA. |
| Draft sales order preparation | MAIA prepares draft sales orders for human review and confirmation before submission. |
| AutoCount-linked submission | Confirmed order outputs are submitted into AutoCount within the agreed integration scope. |
| Document handling | Sales order, invoice, delivery order support, and pick list support are included. |
| Backend visibility | Order status, document trail, activity trail, and agreed operational tracking are available in the backend workspace. |
| Warehouse handoff | Basic pick-list support and basic fulfillment status visibility through MAIA-assisted workflow. |

# 5. Confirmed Customizations and Setup Items

| Type | Item | Description | Commercial Treatment |
| --- | --- | --- | --- |
| Customization | Customer grouping with markup | Allows customers to be grouped into pricing groups and applies agreed markup by group during order creation. | RM8,000 total customization value, waived / FOC. Payable amount: RM0. |
| Customization | Weekly base price upload / update | Allows users to update weekly item base prices using a MAIA-provided upload template. MAIA uses the latest uploaded base prices during order preparation. | RM8,000 total customization value, waived / FOC. Payable amount: RM0. |
| Setup | Min/max selling price guardrails | Configures minimum and maximum selling price limits so MAIA can check pricing against agreed limits. | Included as setup. |
| Setup | High-value order approval flow | Configures an order value threshold so orders above the threshold are routed for approval before final submission into AutoCount. | Included as setup. |

# 6. Commercial Summary

| Item | Commercial |
| --- | --- |
| One-time Phase 1 implementation fee | RM20,000 |
| Customization value | RM8,000, waived / FOC |
| Total one-time payable | RM20,000 |
| Monthly subscription | RM2,500/month |
| Monthly order volume tier | Up to 2,500 orders/month |
| Payment terms | 50% upfront upon project commencement; 50% upon completion of UAT. |

# 7. Third-Party Costs Not Included in Monthly Subscription

Cloud hosting and cloud infrastructure charges

ChatGPT / OpenAI API key or usage fees

WhatsApp Business API charges

WhatsApp number registration or subscription fees

WhatsApp vendor / BSP charges

AutoCount vendor charges

Other third-party platform fees unless explicitly stated in writing

# 8. Standard Implementation Timeline

| Stage | Timeline | Scope |
| --- | --- | --- |
| Kickoff and workflow confirmation | Week 1 | Confirm order flow, user roles, AutoCount access, pricing rules, approval rules, document formats, and implementation PICs. |
| Configuration and integration setup | Week 2 to Week 3 | Set up MAIA workflows, AutoCount integration, customer/item references, document handling, backend workspace, pricing setup, and approval rules. |
| Customization setup | Week 3 to Week 4 | Configure customer grouping with markup and weekly base price upload/update template. |
| User acceptance testing | Week 5 | Test agreed workflows, document outputs, AutoCount submission, pricing logic, approval flow, and backend visibility. |
| Training and go-live support | Week 6 | Train agreed users, support go-live, monitor initial usage, and resolve issues within agreed scope. |

Timeline note: The 6-week target depends on AutoCount access, vendor coordination, turnaround time for data/rule clarification, and timely UAT feedback.

# 9. Client Inputs Required

Relevant system access or vendor coordination

Customer, item, and pricing references

Customer grouping rules and markup rules by customer group

Weekly base price structure or existing price format

Min/max selling price references

Order value approval threshold and approver names or roles

Sample documents and existing flow references

Internal PICs for review, testing, and sign-off

# 10. Scope Boundaries and Exclusions

Full ERP replacement is not included. AutoCount remains the source of truth.

Full warehouse management system is not included.

Deeper warehouse execution logic beyond basic pick-list support is not included unless separately scoped.

Customer-facing ordering chatbot and full customer-facing B2B self-service ordering rollout are not included unless separately scoped.

Complex multi-level approval matrices beyond the agreed high-value order approval flow are not included unless separately scoped.

Custom dashboards or reports beyond agreed backend visibility are not included unless separately scoped.

Additional customizations not listed in the signed proposal are separately scoped and quoted.

# 11. Meeting Recording Links

| Meeting | Fireflies Link | Purpose / Notes |
| --- | --- | --- |
| Intro Meeting | Open Fireflies recording | Initial discovery and business context. |
| Proposal Walkthrough | Open Fireflies recording | Proposal walkthrough and scope discussion. |
| Proposal Finalization 1 | Open Fireflies recording | First proposal finalization discussion. |
| Proposal Finalization 2 | Open Fireflies recording | Second proposal finalization discussion. |
| Proposal Finalization 3 | Open Fireflies recording | Third proposal finalization discussion. |
| Proposal Finalization 4 | Open Fireflies recording | Final finalization discussion before signing. |

# 12. Handover Note

Important: The signed proposal remains the source of truth for commercial terms, scope boundaries, assumptions, and exclusions. This scope document is a practical implementation handover summary and should be read together with the signed proposal included in this ZIP package.