03Aug26_MacroFrozen_Operational_UAT_Conductor_Pack

# Macro Frozen — Operational UAT Conductor Pack

Evidence cut-off: 29 July 2026
Controlling sources: Macro Frozen — Scope Lock v3 and Macrofood (Macro Frozen) × MAIA — Voice of Customer Extraction v3. Both are marked draft; Scope Lock v3 supersedes v2. No later verified regression evidence was supplied.

# PART 1 — UAT COMMANDER DASHBOARD

## 1. Session Mission

| Item | Operational position |
| --- | --- |
| Client | Macro Frozen Sdn Bhd, frozen-food wholesaler/distributor. |
| Objective | Prove the WhatsApp-to-SQL Accounting flow: correct order, controls, warehouse actuals, finance documents and auditable handoffs. |
| Round | Third UAT. |
| Date / location | Window: 11–14 August 2026. Exact date, time and location: Unknown — Must Be Clarified. |
| Recommended duration | 5 hours 15 minutes, including break and sign-off review. |
| Readiness | NO-GO on available evidence. Critical rules and dependencies remain unresolved or unproven. |
| Final signatory | Unknown — Must Be Clarified. The second UAT recorded no formal verdict or named signer. |
| Internal lead / escalation | Unknown — Must Be Clarified. Ivan is named only for the credit decision with David. |

Scope Lock v3 places the project post-second-UAT/pre-third-UAT and identifies credit enforcement and notification ownership as blockers. fileciteturn10file0

## 2. Client Priorities

| Client Priority | Why It Matters | How the Client May Test It | Sign-Off Impact |
| --- | --- | --- | --- |
| Final quantity and ERP correctness | Picked weight often differs from ordered weight. | Amend actuals; inspect DN, Invoice, stock and SQL. | Blocker if wrong. |
| Picking proof and usable documents | Paper/Excel currently proves what was picked and checked. | Print the pick list; inspect breakdown, text and headers. | Blocker if unusable; workaround acceptance may be needed. |
| Price control | Prices are market-driven and customer-specific. | Test normal, intermediate and below-minimum prices. | Blocker if price or approver is wrong. |
| Credit and visible escalation | Silent blocks previously damaged confidence. | Trigger amount/term failures and observe assignment/override. | Blocker. |
| Real devices and handoffs | David, Lai and Grace rely on mobile, notifications and print. | Use named phones; verify Lai/Grace events. | Blocker for mandatory actions. |

The priorities reflect confirmed discovery and second-UAT reactions. fileciteturn10file1 fileciteturn12file8

## 3. Non-Negotiable Acceptance Criteria

An authorised salesperson can create, correct and submit an SO through the agreed live channel using correct SQL-derived data.

All three price tiers route correctly; unauthorised pricing cannot complete.

Credit amount/term rules are written, applied consistently, notified and auditable.

Sales and warehouse visibility restrictions work.

Mandatory approval, SO, warehouse and finance notifications reach only intended recipients.

Final quantity/UOM, DN, Invoice, stock and SQL records are correct, sequenced and non-duplicated.

Intended users can complete mandatory work on the actual channel, devices and printed outputs.

## 4. Critical Pre-UAT Gates

Confirm date, location, attendees, duration and final signer.

Identify the tested build/environment; attach current P0/P1 regression evidence.

Verify and smoke-test the WhatsApp number.

Prove ERP Integration access and SQL test-company results.

Sign off credit mode, overdue tolerance and override authority.

Assign notification ownership and prove every mandatory event.

Prepare actual accounts and retest David’s Z Fold and Krystle’s iPhone.

Select deterministic pricing, credit, quantity, Chinese-text and document data.

# PART 2 — CLIENT AND WORKFLOW BRIEF

## 1. Client Snapshot

Macro Frozen distributes frozen food to wholesale and retail customers.

Orders mainly arrive through WhatsApp and may use informal product wording that staff translate into the correct item.

Warehouse staff cut, pick and weigh goods. Actual weight can differ from requested weight, so final commercial documents must reflect the confirmed quantity.

The current operation relies on WhatsApp groups, route-grouped paper pick lists, handwritten actuals, Excel and SQL Accounting.

Pricing is market-driven and customer-specific; David is the central price controller and final authority for the lowest-price tier.

SQL Accounting remains the customer/item and accounting master. MAIA must not create invalid document sequences, quantities, stock effects or duplicate records.

Silence is interpreted as failure: blocked orders and operational handoffs must visibly reach the responsible person. fileciteturn10file1

## 2. What Makes This Client Different

Requested quantity is not necessarily invoice quantity. The warehouse’s confirmed weight is commercially decisive.

Units are mixed. Orders may be expressed in kg or cartons; pieces and per-box breakdown remain conditional.

Customer language is informal. Correct customer/item mapping must survive shorthand and spelling variation.

Pricing is controlled outside the ERP today. UAT must prove the latest price source, floor and approval ladder.

Human control must remain visible. David does not want silent automation changing prices, credit or documents.

Physical operations matter. A browser-only pass is insufficient if mobile approvals or printed pick lists fail.

## 3. Current Workflow

Plaintext CUSTOMER Sends order through WhatsApp, often in informal wording ↓ SALES Interprets customer, item, quantity and delivery requirement ↓ DAVID / OFFICE Coordinates orders and prepares the operational order information ↓ WAREHOUSE Receives route-grouped paper pick list Cuts, picks and weighs the goods [MANUAL — actual quantity and checks recorded on paper] ↓ GRACE / FINANCE Uses confirmed information to create DN and Invoice in SQL Accounting ↓ DELIVERY Goods delivered; proof and cash information may remain in WhatsApp or Excel ↓ FINANCE Matches payments and updates SQL Accounting

Current pain points include interpretation errors, differences between requested and picked quantity, weak picker/checker traceability, pricing outside the system, manual payment records and dependence on David. fileciteturn10file1

## 4. Intended MAIA Workflow

Plaintext CUSTOMER Sends WhatsApp order ↓ SALESPERSON Forwards order to the single MAIA WhatsApp number Reviews/corrects MAIA draft SO ↓ CUSTOMER + ITEM + ROLE CHECK Correct SQL-derived records and authorised visibility? ├── No → stop and correct mapping/permission └── Yes ↓ PRICE CHECK Normal/approved price ─────────────────────────────→ Continue Below default, at/above minimum ──────────────────→ CJ approval Below minimum ────────────────────────────────────→ David approval ↓ CREDIT + PAYMENT-TERM CHECK Pass ─────────────────────────────────────────────→ Continue Fail ─→ assign/notify approver ─→ David decision ─→ record override ↓ SALESPERSON Submits SO ↓ MAIA Sends submitted SO/PDF to Lai ↓ WAREHOUSE Picks and confirms actual quantity [MANUAL PAPER/EXCEL MAY REMAIN — mechanism must be agreed before UAT] ↓ MAIA Updates the confirmed order and sends the finance handoff ↓ GRACE / FINANCE Explicitly requests DN and Invoice ↓ ERP INTEGRATION — SQL ACCOUNTING Creates valid records in the allowed sequence Stock moves only at the confirmed Invoice/SCN point ↓ FINAL OUTPUT Correct documents, traceable approvals and auditable handoffs

The core order-to-cash path is locked, but the detailed fresh-weight upload and picked-quantity-breakdown mechanism remains agreed in principle rather than fully locked. fileciteturn11file2 fileciteturn9file4

## 5. Role and Decision Map

| Person / Role | What They Must Do During UAT | Decision Authority | Mandatory? |
| --- | --- | --- | --- |
| David — Owner/MD | Perform below-minimum price and final credit-override actions; validate business control. | Final below-minimum price and credit approver. | Yes |
| CJ — Sales Manager | Perform intermediate price approval and validate sales workflow. | Approves below-default but at/above-minimum price. Credit-setting authority requires clarification. | Yes |
| Queenie or Ben — Salesperson | Enter and submit real orders; prove customer isolation and usability. | No final exception authority. | Yes — at least one actual sales user |
| Lai — Warehouse/Logistics | Receive submitted SO, use/inspect pick output and confirm the actual-quantity process. | Operational acceptance of warehouse handoff; backup is undefined. | Yes if warehouse flow is in scope |
| Grace — Finance Manager | Validate DN/Invoice generation, documents and SQL Accounting results. | Finance-process acceptance; not recorded as final UAT signer. | Yes |
| Apple — Finance | Validate payment terms and finance customer settings if included. | Conflicting Sources: credit-limit authority overlaps with CJ in the current evidence. | As required; conflict must be resolved first |
| Krystle — Ops/Admin | Retest the known iPhone rotation/layout failure. | No recorded final acceptance authority. | Required for named-device retest |
| Named client signatory | Review results and record Pass, Conditional Pass or Fail. | Final UAT acceptance. | Yes — currently unknown |

The role evidence identifies David, CJ, Queenie, Grace, Lai, Apple and Krystle, while also showing that warehouse voice is thin and credit-setting authority is not fully consistent across sources. fileciteturn10file1 fileciteturn11file4

# PART 3 — UAT EXECUTION PLAN

## 1. Session Sequence

Plaintext OPENING Confirm participants, signer, scope and known gaps ↓ 1. ENVIRONMENT GATE Build → WhatsApp → Login → Permissions → Notifications → ERP ↓ 2. BASE ORDER Salesperson → real customer/item → draft → review → submit ↓ 3. PRICE CONTROLS Normal → CJ tier → David tier ↓ 4. CREDIT CONTROLS Within limit → amount/term failure → override ↓ 5. HANDOFFS SO to Lai → approval/block events → finance event ↓ 6. WAREHOUSE ACTUALS kg/carton → picked actual → confirmed order ↓ 7. DOCUMENTS AND ERP DN → Invoice → SQL records → stock ↓ 8. DEVICE AND OUTPUT Z Fold → iPhone rotation → PDF → physical print ↓ 9. OPTIONAL ITEMS Only after mandatory blocks pass ↓ 10. REVIEW AND SIGN-OFF Pass / Conditional Pass / Fail

## 2. Ordered Test Blocks

| Order | Test Block | Outcome | Primary User | Others | Preconditions / Data | Duration | Expected Result | If It Fails |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| 1 | Environment/channel/access | Correct build, users, WhatsApp, permissions, notifications and ERP are available. | Each named user | Conductor, tech, Grace | Build ID; accounts; WhatsApp; SQL company | 20 min | All mandatory access and role paths work. | Stop dependent tests. |
| 2 | Standard order/mapping | A salesperson creates and submits the correct SO. | Queenie or Ben | CJ; Lai available | Assigned customer; normal-price kg item; realistic wording | 30 min | Correct customer, item, UOM, term and price; no data exposure. | Stop that order and later dependent blocks. |
| 3 | Pricing ladder | Price exceptions cannot bypass authority. | Salesperson; CJ/David approve | Conductor | Normal, intermediate and below-minimum records | 35 min | Normal continues; CJ and David receive their correct tiers; decisions are logged. | Stop affected exception path; normal order may continue. |
| 4 | Credit/terms | Written credit and term rules block and escalate correctly. | Salesperson; David decides | CJ/Apple after role resolution; Grace | Within-limit, over-limit and overdue customers | 35 min | Correct rule, approver, notification and override record. | Stop credit-dependent orders. |
| 5 | Notifications/handoffs | No mandatory step becomes silent. | Salesperson, Lai, Grace | David/CJ | Configured recipients; approved SO and exception | 25 min | Correct event, PDF/context and audit trail; no wrong recipient. | Stop dependent handoff; independent tests may continue. |
| 6 | Warehouse/actual quantity | Final operational quantity remains correct and traceable. | Lai | Salesperson, Grace | kg/carton items; variable actuals; agreed capture method | 45 min | Ordered context and actual quantity/UOM are preserved for finance. | Stop DN/Invoice for that order. |
| 7 | DN/Invoice/ERP | SQL Accounting receives valid records from the confirmed order. | Grace | Lai, tech | Confirmed order; SQL access; known stock/numbering result | 40 min | Correct DN/Invoice; no duplicate/invalid record; correct stock timing. | Stop all ERP, stock and finance acceptance. |
| 8 | Mobile/PDF/print | Mandatory work is usable on real devices and paper. | David, Krystle, Lai | Grace | Z Fold; iPhone; printer; Chinese item | 30 min | Mobile approval works; Chinese text and full header print. | Stop affected device/warehouse acceptance. |
| 9 | Optional finance/secondary | Only a formally included secondary workflow is assessed. | Grace/Apple | Tech | Written inclusion and prepared data | 25 min | Tested item is clearly Passed, Failed or Deferred. | Do not delay core verdict unless formally mandatory. |
| 10 | Review/sign-off | A clear decision and conditions are recorded. | Named signer | All owners | Completed results and issue list | 30 min | Explicit Pass, Conditional Pass or Fail. | No signer means no acceptance. |

## 3. Dependency and Stop Logic

Plaintext Block 1 fails → stop all dependent functional tests. Block 2 fails → stop Blocks 3–7 for that order. Block 3 fails → stop exception-price paths; normal order may continue. Block 4 fails → stop credit-dependent orders; do not invent a rule. Block 5 fails → stop its approval or handoff path. Block 6 fails → stop DN/Invoice for that order. Block 7 fails → stop ERP, stock and finance acceptance. Time runs short → drop Block 9 first; protect Blocks 3, 4, 6, 7 and sign-off.

## 4. Session Timing

Recommended total: 5 hours 15 minutes.

Plaintext Opening and Blocks 1–3 100 min Block 4 35 min Break 15 min Blocks 5–8 140 min Optional Block 9 25 min Review and sign-off 30 min

For a half-day session, remove Block 9 and defer non-mandatory demonstrations. Do not compress pricing, credit, quantity, ERP or sign-off.

## 5. Conductor Instructions

Before: confirm signer, users and escalation owners; record build/environment/channel/SQL company; verify test data; disclose approved limitations; confirm result-recording method.

During each block: state the business outcome; let the real client user operate; confirm the expected result first; observe rather than coach; record Pass, Fail or Blocked before moving on.

On failure: capture evidence first; check approved scope; retry once only where safe; timebox investigation to 10–15 minutes; use only approved workarounds; stop dependent blocks and escalate.

Before closing: reconcile all mandatory blocks; separate defects, data/configuration issues, unresolved requirements and new requests; record workaround conditions and owners; obtain an explicit decision.

# PART 4 — ACCEPTANCE, RISK AND ESCALATION

## 1. Acceptance Boundaries

| Category | Included Items |
| --- | --- |
| Must Pass for Sign-Off | Core salesperson order entry; correct customer/item/role visibility; price tiers; written credit/term control; required notifications; correct final quantity and UOM; DN/Invoice and SQL Accounting integrity; mandatory mobile and physical-document usability. |
| May Enter Hypercare | Only explicitly accepted, non-blocking cosmetic or convenience issues that do not affect data, approvals, permissions, documents, mobile completion or warehouse work. No item is pre-approved for hypercare in the supplied evidence. |
| Requires Explicit Workaround Acceptance | The warehouse actual-quantity capture mechanism where paper/Excel remains; picked-quantity breakdown/pcs support under AS-11; any retained Excel packing-list process. Retaining Excel must not be recorded as a product Pass. |
| Deferred / Future Phase | Catalogue, quotation, customer PO mechanism, cost/buying-price workflow, driver/POD, accelerated AR workspace, broader dashboards/reminders, SKU replacement until its approval route is defined, and SCN/CCN connector acceptance for this round. |
| Out of Scope | AP reconciliation, merchant/QR settlement, automated WhatsApp blasting, full route/trip planning, WMS/barcode/QR, packing-list Excel OCR, supplier purchase-invoice stock entry, customer announcement blasting, Facebook leads and fleet telemetry. |

The Scope Lock distinguishes locked core controls from agreed-in-principle items and explicitly excludes SCN/CCN from round-three acceptance while retaining several warehouse and driver mechanisms as unresolved. fileciteturn10file0 fileciteturn12file6

## 2. Consolidated Risk, Gap and Response Map

| Risk ID | Workflow Point | What May Fail / Known Gap | Client Impact | Current Status | Conductor Action | Approved Workaround / Disclosure | Continue? | Escalate To |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| R1 | Credit control | Warn-only versus hard block, overdue tolerance and override authority are unresolved; SQL payment knock-off lags. | False blocks, unsafe overrides or inconsistent orders. | Confirmed | Require written rule and configured evidence before Block 4. | None — stop the affected workflow. No approved date; do not estimate. | Unrelated tests only | Ivan ↔ David |
| R2 | Notifications | Direction is locked, but ownership and shipped evidence were not supplied. | Silent block or missed Lai/Grace handoff repeats the client’s complaint. | Verify Before UAT | Prove every mandatory event and recipient before dispatch. | Disclosure wording must be approved before UAT; no bypass Pass. | No dependent handoff | Assigned notification owner — currently unknown |
| R3 | Live channel | Second UAT ran on Telegram because WhatsApp verification was pending. | The purchased operating channel remains unproven. | Not Yet Tested | Smoke-test the actual WhatsApp number, accounts and message flow. | Telegram is not an approved substitute for acceptance. | No channel-dependent tests | Technical/operations owner — unknown |
| R4 | ERP Integration | SQL vendor access remained open. | DN, Invoice, stock and finance outcomes cannot be accepted. | Verify Before UAT | Confirm access, health check, test company and rollback/safety controls. | None — stop the affected workflow. | Non-ERP tests only | Product lead / SQL vendor owner |
| R5 | Mobile operation | David’s Z Fold, Krystle’s rotated iPhone and a mobile payment-term field failed previously. | Approvers or finance users cannot complete daily work. | Verify Before UAT | Retest the named devices on the release build before and during UAT. | None for mandatory mobile roles; desktop substitution is not a Pass. | Independent tests only | Technical owner — unknown |
| R6 | Pick-list output | Chinese text and company header failed on physical print. | Warehouse output may be unreadable or incomplete. | Verify Before UAT | Print the real template before the session and repeat with Lai. | None approved. No approved date; do not estimate. | Non-print tests only | Document/template owner — unknown |
| R7 | Actual quantity / breakdown | AS-11 feasibility and presentation are not locked; pcs is tied to the same mechanism. | Excel-removal promise may be exposed; customer/internal proof may be lost. | Confirmed | State the tested boundary and use pcs only after explicit inclusion. | Proposed: retain Excel if infeasible; explicit client acceptance required. | Yes, if accepted and correctly classified | Product lead / David / Grace |
| R8 | Authority and closure | No final signer is named; CJ/Apple credit-setting roles conflict across evidence. | The room may be unable to decide or may apply the wrong authority. | Conflicting Sources | Resolve role matrix and name the signer before UAT. | None — do not improvise authority. | No affected approval or sign-off | Account lead / David |
| R9 | Warehouse adoption | Warehouse voice is thin; Lai’s backup and MAIA access model are unresolved. | A technically correct flow may be rejected operationally. | Unknown — Must Be Clarified | Confirm Lai’s attendance, access, actual method and backup before Block 6. | Current paper/Excel may remain only as an explicitly accepted boundary. | Core sales tests may continue | David / Lai / account lead |

R1–R4 come directly from the Scope Lock’s blocking items and deployment dependencies. R5–R7 are confirmed second-UAT defects or scope gaps. R9 reflects the VoC’s explicit coverage limitation and the unresolved backup/access model. fileciteturn10file0 fileciteturn12file2 fileciteturn12file8

## 3. Stop and Escalation Rules

Wrong price or financial value: stop that order and all dependent documents. Unrelated usability tests may continue.

Wrong quantity or UOM: stop DN/Invoice for that order. Do not “correct it later” and mark the flow Passed.

Invalid stock movement or duplicate/invalid ERP document: stop every ERP and finance block; preserve evidence and escalate immediately.

Restricted-data exposure or wrong-role access: pause the whole session until exposure is contained and the impact is assessed.

Critical approval or notification failure: stop the dependent exception or handoff; normal independent flows may continue only where no control is bypassed.

Same mandatory workflow fails twice: stop live troubleshooting after the controlled retry and move only to independent blocks.

Expected behaviour contradicts approved scope: pause the affected test; classify it as an unresolved requirement rather than choosing a convenient answer.

No authorised final signer: complete result review, but do not record UAT acceptance.

## 4. Do Not Promise

A fix, go-live or readiness date that has not been approved.

That Telegram proves WhatsApp readiness.

That desktop completion proves a mandatory mobile workflow.

Removal of Excel or paper before the AS-11/warehouse mechanism is accepted.

Driver/POD, AR acceleration, SCN/CCN, catalogue or route-planning delivery as part of this UAT.

A credit rule or approver that has not been confirmed in writing.

That a bypassed control or manual workaround counts as a product Pass.

## 5. Sign-Off Decision

### PASS

All mandatory business workflows pass using the intended users, WhatsApp channel, named devices, printed outputs and ERP Integration.

### CONDITIONAL PASS

Only explicitly accepted non-blocking issues remain. Each condition has a named owner, written workaround or limitation, due/retest requirement and client acceptance.

### FAIL / NO SIGN-OFF

A mandatory workflow fails, remains blocked, is tested through a substitute path, or cannot be safely validated.

Current recommendation: NO-GO. As of the evidence cut-off, the credit-enforcement rule, notification ownership/proof, WhatsApp verification, ERP access, final signer and known device/document fixes were not shown as closed by verified regression evidence. The core design may be stable, but dispatching a conductor before these gates close would make the client session a discovery exercise rather than UAT. fileciteturn10file0 fileciteturn11file2

# PART 5 — SUPPORTING REFERENCES

| Supporting Document | When the Conductor Should Open It |
| --- | --- |
| Macro Frozen — Scope Lock v3 (29 Jul 2026) | Confirm whether a behaviour is locked, agreed in principle, unresolved, deferred or out of scope. |
| Macrofood (Macro Frozen) × MAIA — Voice of Customer Extraction v3 (29 Jul 2026) | Understand why the client reacts strongly to quantity, pricing, notifications, Excel, devices and printed documents. |
| Approved round-three detailed UAT checklist | Execute the exact scenarios and record Pass/Fail/Blocked. Not supplied with the current evidence set. |
| Round-three test-data and account sheet | Find the selected customers, items, prices, credit states, devices, logins and expected SQL results. Must be completed before UAT. |
| Latest P0/P1 regression evidence | Confirm that the NO-GO gates and previous mobile/print defects have actually cleared. Not supplied. |
| Defect and known-issue tracker | Check current status, ownership and retest evidence without debating from memory. |
| ERP Integration health evidence | Confirm SQL vendor access, test company, document sequence and stock validation before Block 7. |
| Session control, escalation and sign-off sheet | Find the exact date/location, conductor, technical contacts, final client signer and written outcome form. Must be completed before UAT. |