Dalson Phase 1 — Backward Plan to Go-Live

## owner: Gareth
status: draft
last_reviewed: 2026-07-01
client: Dalson
phase: 1
lark_url: https://eg69120xnei.sg.larksuite.com/wiki/WlrVwm24PilISckXZdDl0lyzgde

End goal: Core MAIA live + client trained by Fri 24 Jul 2026; hypercare through 1 Aug 2026
Created: 2026-06-21
Updated: 2026-07-01 — milestones rescheduled (M1–M7)
Channel: Telegram (Meta/WhatsApp on hold — business verification pending; Telegram confirmed with client)
Scope: Core MAIA only — Customer PO → SO → Invoice → DO; AutoCount 2-way sync; SKU matching; DO retrieval; Proof of delivery; New customer push; e-invoice readiness.
Model: Same pattern as [[Macrofood Phase 1 Timeline]] — internal test + live-fix session before client sees it; on-the-spot UAT during UAT session.

## Milestone Map

NOW ─── M0 Deps ─── M1 Deploy + Chatbot ─── M2 AutoCount + 2-way sync ─── M3 Internal Test ─── M4 UAT ─── M5 Go-Live + Sign-off ─── M6 Training ─── M7 Hypercare Sat Sat–Mon Jul 1–3 Jul 3–7 Jul 8–10 Jul 14–17 Jul 18–20 Jul 22–24 Jul 30–Aug 1 Jun 21 Jun 21–23

| Phase | Date | Status | Who | Goal |
| --- | --- | --- | --- | --- |
| M0 Deps + Kickoff | Sat 21 – Mon 23 Jun | Done | Gareth | Lock all remaining deps; confirm Telegram channel; chase AutoCount vendor |
| M1 AWS Deploy + Telegram | Jul 1 – 3 | In progress | Dev | MAIA instance live on AWS; Telegram chatbot connected and smoke-tested |
| M2 AutoCount Integration + 2-way Sync | Jul 3 – 7 | Scheduled | Dev + PM | Customer/item master read; SO/Invoice/DO write; new customer push; 2-way sync verified |
| M3 Internal Test + Core Features | Jul 8 – 10 | Scheduled | Gareth + Dev | Full Dalson workflow run-through live; fix on spot; all scope items green |
| M4 UAT | Jul 14 – 17 | To schedule — confirm date with client | PM + Dalson | Client runs UAT on spot; PM triages same session |
| M5 Go-Live + Sign-off | Jul 18 – 20 | To schedule | PM + Dalson | Punch list cleared; live confirmed; sign-off obtained |
| M6 Training | Jul 22 – 24 | To schedule — confirm date with client | PM + Dalson team | Full team trained on live system |
| M7 Hypercare / Live Care | Jul 30 – Aug 1 | Planned | PM + Dev | Post-go-live monitoring; fast-response fixes |

## ⚠️ Critical Path — AutoCount Integration (Azib)

AutoCount credentials already received. Vendor (Ms Tan) dependency is cleared. Hard go-live blocker is now Azib completing the integration build by Sat 28 Jun.

Azib builds AutoCount read + write + 2-way sync (Wed 25 – Sat 28 Jun) → internal test session with Gareth (Sat 28 – Mon 30 Jun) → UAT Tue 1 Jul.

If Azib's integration is not testable by Sat 28 Jun, internal test compresses and Jul 1 UAT is at risk — flag immediately.

UltraViewer access already received:

| Credential | Value |
| --- | --- |
| UltraViewer ID | 100 763 541 |
| UltraViewer password | 03935 |
| AutoCount ID | admin |
| AutoCount password | admin |
| AutoCount version | 2.2 (build 2.2.90) |

Channel note: Telegram is the go-live channel — confirmed with client. Meta/WhatsApp is not a blocker. WhatsApp can layer in post go-live once Meta business verification is resolved.

## M0 — Dependencies + Kickoff (Sat 21 – Mon 23 Jun)

Who: Gareth
Goal: Confirm every input that M1 and M2 depend on. Nothing downstream moves until these land.

### Already Done ✅

AWS onboarding setup complete (MAIA config ready)

OpenAI API key set up

AutoCount vendor identified (Ms Tan — contact details above)

UltraViewer + AutoCount admin credentials received

AutoCount integration credentials received — Azib to proceed with build

Telegram confirmed as go-live channel (comms with client)

### Pending — Not Yet Done

AWS deployment on Dalson's AWS — pending Wei Yon; gates M1

### Chase by Mon 23 Jun

| Dependency | Blocks | Status |
| --- | --- | --- |
| Dalson company user list (name, role, contact) | User seed (M2) | ⬜ |
| One sample of each document Dalson uses: SO, Invoice, DO | PDF template config (M2) | ⬜ |
| Customer master export from AutoCount (debtor list) | Data seed (M2) | ⬜ |
| Item / SKU master export from AutoCount | Data seed (M2) | ⬜ |
| Confirm Telegram bot handle / name agreed with client | Chatbot (M1) | ⬜ |
| Confirm internal PIC from Dalson for UAT (name + contact) | UAT (Jul 1) | ⬜ |

## M1 — AWS Deploy + Telegram Chatbot (Jul 1 – 3) — In Progress

Who: Wei Yon (Dev)
Goal: MAIA instance live on Dalson's AWS; Telegram chatbot connected and responding.

Wei Yon: deploy MAIA instance on Dalson's AWS — onboarding setup already done; pending deployment

Set up Telegram chatbot — primary go-live channel

Connect chatbot to MAIA instance

Smoke-test basic message flow: send message → MAIA responds

Confirm instance + chatbot stable before M2 begins

WhatsApp / Meta: not in scope for go-live. Do not block on it.

## M2 — AutoCount Integration + 2-way Sync (Jul 3 – 7) — Scheduled

Who: Azib (Dev) + PM
Goal: Full AutoCount sync working. All read + write flows verified before internal test.

Azib: AutoCount integration build complete + testable — Sat 28 Jun (hard target; gates M3)

Confirm integration method with Azib (API, SDK, or middleware via UltraViewer — credentials already received)

Build + verify AutoCount READ:

Customer (debtor) master sync

Item / SKU master sync (incl. customer-specific descriptions where available)

Pricing sync (price list per customer or item)

Build + verify AutoCount WRITE:

Sales Order push to AutoCount

Invoice push to AutoCount (e-invoice fields included)

Delivery Order push to AutoCount

New customer creation push (with required e-invoice fields: company reg, tax ID)

Verify 2-way sync — MAIA write → AutoCount reflects; AutoCount update → MAIA reads back

Test all write flows on cloned test DB first — never write to Dalson's live AutoCount until go-live

Confirm firewall / IP whitelist requirements with Ms Tan if needed (AutoCount cloud-hosted)

Seed Dalson company users into MAIA

Seed customer + item master data from AutoCount exports

Configure SO / Invoice / DO PDF templates from Dalson doc samples

## M3 — Internal Test + Core Features (Jul 8 – 10) — Scheduled

Who: Gareth + Dev
Duration: ~2–3 hours (one session)
Format: PM runs every scope item live on Dalson env; dev fixes on the spot during session. Anything not fixable in session → explicit defer decision logged. Nothing goes to client UAT with a known failure.

### Core workflow checklist — run live

| # | Item | FE | Chatbot | AutoCount | Status |
| --- | --- | --- | --- | --- | --- |
| 1 | Customer master synced from AutoCount (read) | — | — | ☐ | ⬜ |
| 2 | Item / SKU master synced from AutoCount (read) | — | — | ☐ | ⬜ |
| 3 | Pricing synced per customer from AutoCount (read) | — | — | ☐ | ⬜ |
| 4 | Forward customer PO (image/PDF) → MAIA reads and drafts SO | ☐ | ☐ | — | ⬜ |
| 5 | SKU ambiguity: MAIA surfaces closest match → coordinator confirms | ☐ | ☐ | — | ⬜ |
| 6 | Duplicate order warning triggers on repeat submission | ☐ | ☐ | — | ⬜ |
| 7 | Sales Order created in MAIA + pushed to AutoCount (write) | ☐ | ☐ | ☐ | ⬜ |
| 8 | Invoice generated from SO + pushed to AutoCount (e-invoice fields populated) | ☐ | — | ☐ | ⬜ |
| 9 | Delivery Order generated + stored against order record | ☐ | — | ☐ | ⬜ |
| 10 | DO retrieval: search by customer / date / order number → PDF generated | ☐ | ☐ | — | ⬜ |
| 11 | Proof of delivery: driver sends photo via chatbot → attached to order DO | ☐ | ☐ | — | ⬜ |
| 12 | New customer creation → push to AutoCount (with e-invoice required fields) | ☐ | ☐ | ☐ | ⬜ |
| 13 | Credit note issued from invoice ID → linked to source invoice in MAIA | ☐ | — | ☐ | ⬜ |
| 14 | 2-way sync verified: MAIA write → AutoCount reflects | — | — | ☐ | ⬜ |
| 15 | Daily digest surfaces pending orders / invoices / delivery follow-ups | ☐ | — | — | ⬜ |
| 16 | SO / Invoice / DO PDF renders correctly with Dalson formatting | ☐ | — | — | ⬜ |

End of session: green items locked; deferred items explicitly logged with decision

### Items NOT to test in M3 (out of scope, do not creep in)

Pick list / packing list — Dalson does not use this

Receipts — not required by default; add post go-live if requested

Supplier / procurement logic — explicitly out of scope

WhatsApp / Meta channel — not a go-live dependency

## M4 — UAT (Jul 14 – 17) — To Schedule (confirm date with client)

Who: PM + Dalson UAT users
Format: PM briefs scope → Dalson team runs UAT on the spot → PM triages same session.

Brief client: what's in scope vs deferred; what's new vs old

Dalson team runs core workflow live on MAIA env:

Forward a PO → SO created → Invoice → DO

SKU ambiguity scenario — MAIA suggests match, user confirms

DO retrieval — search and retrieve an old DO

Proof of delivery — driver photo attached

New customer creation flow

Daily digest view

PM on standby; log issues and triage same session

Minor issues: fix same day or before M5

Sign-off criteria agreed before session starts

Collect UAT results → conditional sign-off or punch list

## M5 — Go-Live + Sign-off (Jul 20 – 22) — To Schedule

Who: PM + Dalson
Goal: UAT punch list cleared → confirm live → sign-off.

All UAT punch list items resolved

Instance stable (no regressions from UAT fixes)

Telegram chatbot live on production — Dalson team using it

All Dalson users confirmed active in MAIA

AutoCount sync live on production (not test DB)

Sign-off obtained — 70% payment milestone triggered

Go-live confirmed — Dalson team begins live operations

## M6 — Training (Jul 22 – 27) — To Schedule (confirm date with client)

Who: PM + full Dalson team (sales coordinators + any warehouse / delivery staff using chatbot)
Format: Full structured session; cover end-to-end live workflow.

Prep training material (slides / walkthrough based on UAT scenarios)

Demo environment with clean data ready

Train: full order flow — forward PO → SO → Invoice → DO via Telegram

Train: SKU matching — what MAIA suggests, how to confirm or override

Train: DO retrieval — how to search and pull old DOs

Train: proof of delivery — driver sends photo → how it attaches

Train: new customer — how to add via MAIA + AutoCount push

Train: daily digest — what it shows, how to act on it

Cover: how to flag issues post go-live; escalation contact

WhatsApp path: inform client Meta verification is in progress; WhatsApp will layer in once resolved — no action needed from client

## M7 — Hypercare / Live Care (Jul 30 – Aug 1)

Who: PM + Dev
Goal: Close monitoring post go-live; fast turnaround on any live issues.

Daily check-in with Dalson team on live usage

Monitor AutoCount sync for errors on production

Fast-track fixes for any issues surfaced post-training

Close out hypercare with a final stability check + handover to BAU support

## Scope at Go-Live (What Dalson Gets)

| Feature | Status |
| --- | --- |
| Telegram chatbot order intake (PO, text, image) | ✅ In scope |
| SKU ambiguity matching with coordinator confirmation | ✅ In scope |
| Sales Order creation + AutoCount push | ✅ In scope |
| Invoice generation + e-invoice readiness + AutoCount push | ✅ In scope |
| Delivery Order generation, retrieval, PDF | ✅ In scope |
| Proof of delivery photo capture (chatbot → order record) | ✅ In scope |
| New customer creation → AutoCount push (with e-invoice fields) | ✅ In scope |
| Credit notes (invoice-linked) + AutoCount push | ✅ In scope |
| Daily digest + pending task visibility | ✅ In scope |
| Duplicate order warning guardrail | ✅ In scope |
| AutoCount 2-way sync (read master data; write transactions) | ✅ In scope |

## NOT in Go-Live Scope (Do Not Creep In)

WhatsApp / Meta channel — Meta verification pending; layer in post go-live

Pick list / packing list — Dalson does not use this in their workflow

Receipts — not standard; activate post go-live if customer requests

Supplier / procurement logic — explicitly out of scope per signed proposal

Advanced management dashboards / custom reports — post go-live

Historical DO migration — DOs before go-live date not auto-migrated; retrieve from AutoCount directly if needed

LHDN e-invoice direct submission — handled by AutoCount; MAIA prepares and pushes only

## Key Contacts

| Role | Name | Contact |
| --- | --- | --- |
| AutoCount vendor / system owner | Ms Tan | +60192392686 / easysoftprosolution@gmail.com |
| AutoCount version | 2.2 (cloud, build 2.2.90) | Hosted on vendor server |
| UltraViewer remote access | — | ID: 100 763 541 / PW: 03935 |
| AutoCount login | — | admin / admin |
| Dalson UAT PIC | TBC | Chase in M0 |

## Milestone Dates

| # | Milestone | Date | Status |
| --- | --- | --- | --- |
| — | Signed Date | TBC | — |
| — | Payment Date (30% upfront) | TBC | — |
| — | Kickoff Date | 2026-06-21 | Done |
| M0 | Deps + Kickoff | 2026-06-21 – 2026-06-23 | Done |
| M1 | AWS Deploy + Telegram | 2026-07-01 – 2026-07-03 | In progress |
| M2 | AutoCount Integration + 2-way Sync | 2026-07-03 – 2026-07-07 | Scheduled |
| M3 | Internal Test + Core Features | 2026-07-08 – 2026-07-10 | Scheduled |
| M4 | UAT | 2026-07-14 – 2026-07-17 | To schedule — confirm with client |
| M5 | Go-Live + Sign-off | 2026-07-18 – 2026-07-20 | To schedule |
| M6 | Training | 2026-07-22 – 2026-07-24 | To schedule — confirm with client |
| M7 | Hypercare / Live Care | 2026-07-30 – 2026-08-01 | Planned |

## See Also

[[Dalson MAIA autocount integration]]

[[Dalson Industrial Supplies Customer Narrative Document]]

[[Macrofood Phase 1 Timeline]]

[[Fixguru 2nd UAT Backward Plan]]

|（注：部分内容可能由 AI 生成）