Fixguru 2nd UAT  Plan

End goal: Client conducts 2nd UAT → sign-off

Created: 2026-06-06

Updated: 2026-06-07 (status refresh)

## Milestone Map

Plain Text NOW → M1 Brief + Dev Fix → M2 Internal Test + Live Fix → M3 Stable + Schedule → M4 On-the-spot UAT Sat Mon Tue (2hr session) Wed Mon–Tue Jun 7 Jun 9 Jun 10 Jun 11 Jun 16–17

| Phase | Who | Goal |
| --- | --- | --- |
| M1 Brief + Dev Fix | PM + Amirul + Bryan + Azib (+ team) | Walk all remaining items; dev fixes same day |
| M2 Internal Test + Live Fix | Gareth + Amirul + Bryan + Azib | 2hr session — test every item on spot; fix on spot |
| M3 Stable + Schedule | PM | Fixguru stable; UAT form ready; ask client if Jun 16–17 works |
| M4 On-the-spot UAT | PM + Fixguru testers | Brief client on gaps, run UAT on the spot → sign-off |

## Status Snapshot — Jun 7

### Ready for UAT ✅

| Item | Notes |
| --- | --- |
| Pick shipping method | — |
| Search customer by phone number | — |
| Calculator (RSC + Diecut) | Tested, complete |
| FOC items | Done |
| External SKU item code | Done |

### Retest Required 🔁

| Item | FE | Chatbot | Notes |
| --- | --- | --- | --- |
| Apply Discount | — | 🔧 Chatbot issue | Need retest after chatbot fix |
| Item historical pricing | — | 🔧 Chatbot fixing | Retest when chatbot fix done |

### Partial — FE Done, Chatbot Pending 🔧

| Item | FE | Chatbot | Notes |
| --- | --- | --- | --- |
| Customer pricing enforcement | ✅ Done | 🔧 Pending | — |

### First-Time Test Needed (Pending Dev) 🔲

| Item | Blocker | Priority |
| --- | --- | --- |
| Credit limit exposure | Ready to test — no blocker | 🔴 High — Gareth to test first |
| External doc ID | Pending BE | — |
| 2-way sync | Pending BE | — |
| Auto-populate shipping method SKU as line item | Pending BE | — |
| Volume fields in item profile | Pending FE + Chatbot | — |
| Draft Fixguru custom PDF template | Pending PDF/BE | — |
| Language preference | Pending BE | — |
| HQ + branch contact | Pending BE + Chatbot | — |

### Chatbot Fix In Progress 🔧

| Item | Issue | Notes |
| --- | --- | --- |
| 2-warehouse ↔ items | Chatbot bug |  |
| UOM conversion (multi-item) | Multi-UOM chatbot broken | Single UOM works |
| Item shelf | Chatbot: populate shelf no. in additional note (DN only) | Scoped fix |

## M0 — PM Decisions (DONE)

| Decision | Resolution | Target Date |
| --- | --- | --- |
| QTN amendment API | Blocker — API doesn't exist |  |
| Volumetric fields BE | ✅ BE done — FE + chatbot can proceed |  |
| Customer price enforcement | Field-level (read-only) — lock icon already signals it |  |
| FOC items | Done |  |
| UOM split + shelf + 2-warehouse chatbot | In scope — retest required; single UOM works |  |
| Item historical pricing | In scope — retest required |  |
| Pricing enforcement FE + chatbot | FE done , chatbot fixing |  |
| Calculator (RSC + Diecut) | Done |  |
| Volumetric fields FE + chatbot + DN PDF | In scope — dev in progress |  |
| Credit limit exposure | In scope — testing |  |
| HQ + branch contact | In scope — blocker; dev fixing |  |
| Delivery method as SKU | In scope — blocker; dev fixing , need to test |  |
| PDF — Fixguru custom draft template | In scope — dev in progress |  |
| Item shelf in chatbot | Scoped: populate shelf no. in additional note (DN only) |  |
| External SKU item code | Done |  |
| Language preference | In scope — dev in progress |  |
| 2-way sync | In scope — testing |  |

## M1 — Brief + Dev Fix Day (Mon Jun 9)

Who: PM + Amirul + Bryan + Azib (+ Fariha, Haiqal, Rahim, WeiShen as needed)

Format: Morning brief → dev fixes for the rest of the day

### Morning Brief

Walk all remaining items (use ETA table below) — PM explains expected behaviour per item

Confirm each item's owner

Flag anything unrealistic to land by Tue — cut scope now or slip UAT

### ETAs to confirm (Jun 9 brief)

| Item | Owner | Can ship Tue? |
| --- | --- | --- |
| External doc ID on PDF | Azib | WIP |
| Credit limit BE formula | Fariha | testing |
| HQ + branch contact sync | Azib | Done |
| Up to date 2 warehouse sync | Azib | wip |
| 2-way sync | Azib | Need to align |
| Add shipping method as SKU | Gareth | Retest |
| Language preference BE | Azib | Done |
| Item level discount auto-compute fix | Amirul | Fixed |
| Volumetric fields FE + PDF display | Amirul/Rahim | EOD of 08/06/2026 |
| Credit limit exposure FE | Haiqal | testing |
| Draft Fixguru custom PDF template | Rahim | Testing |
| Apply Discount chatbot fix | Bryan | Minor fix |
| Item historical pricing chatbot fix | Bryan | Testing done |
| Customer pricing enforcement chatbot | Bryan | Ready to test |
| UOM conversion (multi-item) chatbot | Bryan | Testing done |
| Item shelf — additional note (DN) | Bryan | Fixing |
| 2-warehouse chatbot fix | Bryan | Done |
| Volume fields chatbot | Bryan | Ready to test |
| Credit limit exposure chatbot | WeiShen | testing |
| HQ + branch chatbot | Bryan | done |
| Language preference chatbot | Bryan | Done |

### Dev Fix (Mon afternoon — after brief)

Dev team fixes assigned items before Tue session

PM available for questions; no formal check-in needed

## M2 — Internal Testing + Live Bug Fix Session (Tue Jun 10)

Who: Gareth + Amirul + Bryan + Azib

Duration: 2 hours

Format: PM tests every item live on Fixguru env; dev fixes on the spot if broken

Run all items in scope — doesn't matter what was "fixed" beforehand, test live

Dev fixes any failures on the spot during session

Log anything that can't be fixed in session → explicit defer decision

End of session: agree on what's green, what's deferred

Test checklist (run in session):

Already passing — smoke check only

Pick shipping method

Search customer by phone number

Calculator (RSC + Diecut) — price flows into QTN + SO

FOC items — submit works, correct lines

External SKU item code

Retest

Apply Discount — chatbot

Item historical pricing — chatbot (last invoice, avg price, QTN history)

Customer pricing enforcement — chatbot enforces locked price

UOM conversion — multi-item different UOM chatbot vs FE

Item shelf — chatbot populates shelf no. in additional note (DN only)

2-warehouse — chatbot handles correctly

First-time tests

Credit limit exposure — FE shows limit / exposure / available balance

Credit limit exposure — chatbot (WeiShen)

External doc ID — visible on PDF

Auto-populate shipping method SKU — chatbot adds as line item

Volume fields — visible in item profile FE + chatbot

Draft Fixguru custom PDF template — renders correctly

Language preference — FE + chatbot

HQ + branch contact — chatbot assigns correct branch on SO

2-way sync

Historical pricing web — discount %, auto-derive, dropdown (Tests 5–7)

Item level discount — auto-compute when unit price > std price

## M3 — Stability Check + Schedule UAT (Wed Jun 11)

Who: PM (Gareth)

Verify Fixguru FE instance stable — no regressions from Tue fixes

Verify Fixguru chatbot stable — quick smoke on key flows

UAT form finalised — all test groups clean, no draft markers

Seed/verify test data intact

Contact Fixguru — inform internal testing done; propose Jun 16–17 for UAT; confirm date

Brief client on gaps addressed from last UAT + what's new in scope

## M4 — On-the-spot UAT (Mon–Tue Jun 16–17)

Who: PM + Fixguru testers (Xiao Ling, Hayati, Zuha, Abishaah/Wendy, Marcus)Format: PM brief on fixes → testers run UAT on the spot same session

Brief: what was fixed vs last UAT, what's new in scope

Run UAT on the spot — testers test live with PM on standby

Use Jam to log any bugs found

Collect results + triage same session

Sign-off or conditional sign-off with punch list