Fixguru Action Plan — 3rd UAT Backward Plan

Based on the 24 June 2026 UAT session (Fireflies transcript + 2026-06-24 Fixguru UAT Debrief + learnings log).

Core conclusion: Client still cannot proceed confidently because the first sales-order pricing step is unsolved. The blocker is not only data correctness — it is how MAIA presents historical price, discount %, net price, and next action in a way sales users can understand in one glance. This repeats 7 Apr, 14 May, and 16 Jun. Prompt-level patching has hit its ceiling; a first-class invoice-sourced module is required.

## Open Decisions (Resolve Before Next Demo Date)

Rendering mechanism — chat single-message vs. image/label vs. dual web interface (70/30 co-work view)

Block level — order vs. DN (client leans DN; must be confirmed and locked in writing)

UAT sign-off authority — confirm Gareth is the signatory (no valid acceptance without this)

Dual interface scope — Phase-1 inclusion or costed CR

## Client Blockers Needed (Ivan to Chase)

| # | Item | From | Why blocking |
| --- | --- | --- | --- |
| C1 | Real WhatsApp order-intake message samples (format reference for parser) | Yvonne | Defines the intake string MAIA must parse |
| C2 | AutoCount screenshot of two blocks (min price + credit limit) + which roles can bypass | Azib | Credit/approval logic can't be built without this |
| C3 | Minimum price floor per item (std + floor, e.g. G1 0.33 / 0.27) | Gareth | Approval threshold rule requires floors |
| C4 | Standard price list (global, fluctuating) — share in group | Gareth | Needed to compute discount % vs. current standard |
| C5 | Updated RSC/Diecut formulas + volume metrics (carryover from prior UAT) | Fixguru | Calculator accuracy still unresolved |
| C6 | Confirm UAT sign-off authority (is Gareth the signatory?) | Ivan ↔ Fixguru | No signed acceptance = Milestone-2 RM24k unpaid |

## Product Action Plan

| Priority | Product action | Why it matters | Output for tech |
| --- | --- | --- | --- |
| P0 | Redesign pricing decision flow | Users abandon when too much text / unclear pricing. First step must be fixed before next flow. | Final UX spec for "Historical Pricing Review before QTN/SO creation" |
| P0 | Define exact historical pricing table fields | Client wants quick comparison, not long chatbot text. Min 5 rows per item (3 is explicitly too few); date matters — signals price drift vs. current standard. | Table columns: Date, Item Code, Qty, Standard Unit Price, Discount %, Net Price, Source Invoice ID |
| P0 | Clarify source of historical pricing | Client confirmed: source must be actual invoices, not draft orders. | Rule: pull last 5 invoice transactions per customer + item |
| P0 | Simplify chatbot copywriting | Users "don't like reading"; single message, yes/no, no grand-total noise (total lives in PDF). Grand total = meaningless at line level; show qty, unit price, discount, normal vs net price only. | Rewrite chatbot prompts: "Review price → choose discount → generate QTN/SO". No enrichment beyond what's asked. "Not found = not found." |
| P0 | Decide hybrid UX pattern | Chat alone cannot show rich tables for 20–100 line items. 24 June discussion raised dual interface (70/30 co-work view) — must be an explicit decision, not improvisation. | Product decision: WhatsApp for input, web view or image/table card for pricing review. Do not let this delay step-1. |
| P1 | Define delivery method recommendation UX | Client wants last 5 confirmed delivery methods (courier / Lalamove / self-pickup) to recap with customer. | Add "Historical Delivery Method" section: last 5 with delivery method and charge item |
| P1 | Delivery address history | Customer may want to reuse a previous delivery address; surfacing history removes manual lookup. | Show last 5 confirmed delivery addresses per customer from SO history; user selects or enters new |
| P1 | Default to historical price on line item add | When user adds an item, MAIA should pre-fill with last invoiced price (not standard price) to reduce back-and-forth. | On item add: fetch last invoiced price for that customer + item; pre-fill as default; user can override |
| P1 | Cash / credit term confirmation | After delivery address is set, payment term must be captured before SO is created. | Bot asks: "Cash or credit term?" after delivery address step; term applied to SO |
| P1 | Define customer search behaviour | Customers WhatsApp in with phone only, often no name/company; existing customers can look new. | Search priority: phone/mobile → landline → customer match → branch/contact → show confirmation |
| P1 | Define approval UX — block at DN level, not order level | Client explicit instruction: blocking the order too early loses the chance to collect money/invoice. Two blocks only: minimum price + credit limit. | Approval states: Draft allowed; DN submit blocked if below-floor price OR DO value exceeds credit limit. Quotation still generated pending approval — no hard-stop mid-flow. |
| P1 | Credit approval paths (two distinct flows) | AR-negative means customer is prepaid — approve on bank-in slip. Credit-limit-exceeded is a separate path — approve case-by-case on bank-in slip. | Route to Ivan for approval in both cases; approver sees AR, pending SO/DN amount, credit limit, available balance. |
| P1 | FOC rule | Production overage is free: order 1000, produce 1050 → 50 units are FOC. | Bill billable qty; deduct billable + FOC from stock. FOC line appears on DO. |
| P1 | Custom item handling | Base item (e.g. G5) spawns {Customer Name} G5 variants. | Item retrieval and matching must handle customer-named variants of base items |
| P1 | Item-retrieval fallback | On no exact item match, return the customer's historically ordered items to reduce dead-ends in the flow. | Fallback: show items previously invoiced to that customer |
| P1 | Confirm scope vs CR | Avoid another UAT mismatch. | Mark: must-fix in current scope vs future CR. Especially calculator versioning, extra calculators, raw material planning. |
| P2 | Role-aware information density | Sales users want yes/no flow to get things done; managers/approvers need full context. | Define two response modes: sales (minimal, action-only) vs manager (full AR, pricing, credit, history) |
| P2 | Lead/prospect creation when customer not found | Sales users often only have phone or WhatsApp number — no name. If not found, must not dead-end. | If no customer match by phone: offer "Create as lead/prospect" requiring phone/WhatsApp only; do not block order intake |
| P2 | Create retest script based on real Fixguru flow | Previous test was feature-by-feature, not user-flow-based. | One golden script: WhatsApp order → historical price review → discount select → QTN PDF → delivery method + address → cash/credit term → SO/DN approval check |

## Tech Action Plan

| Priority | Tech action | Lead | Acceptance criteria |
| --- | --- | --- | --- |
| P0 | Historical pricing API/data fix | Afiq / Wei Yon | For each ordered item: date, qty, std price, discount %, net price, invoice ID. Min 5 rows. Source = invoices only. |
| P0 | Discount calculation fix | Afiq | 3%, 5%, 10% discounts calculate correctly against standard unit price |
| P0 | Item-level discount support | Afiq | Same order: item A 3%, item B 10%, item C no discount |
| P0 | Chatbot response formatter | Afiq | User understands all item pricing in one glance; no scrolling through long text |
| P0 | Order creation flow guardrail | Afiq | Bot asks "Use which discount/net price?" before generating QTN/SO |
| P0 | Language bug fix | Afiq | Quick replies stay in English throughout an English conversation; no mid-flow switch to Malay |
| P0 | Hybrid table/web view feasibility | Jermaine / Amirul | Product + tech agree one implementation path; timeboxed spike, must not delay step-1 |
| P1 | Customer search by phone/mobile + landline | Wei Yon | User pastes phone number; MAIA finds correct customer and branches across both mobile and landline fields |
| P1 | Branch/contact sync check | Wei Yon | SO/DN uses selected branch contact, not HQ default |
| P1 | Delivery method as SKU/item | Wei Yon | Delivery charge appears as item line with correct item code/accounting treatment |
| P1 | Historical delivery method retrieval | Wei Yon | Bot/table shows last 5 confirmed delivery methods per customer |
| P1 | Delivery address history retrieval | Wei Yon | Fetch last 5 confirmed delivery addresses per customer from SO history; surface in bot after delivery method step |
| P1 | Line item price defaulting | Afiq | When item added to order: fetch last invoiced price for that customer+item; pre-fill as default net price; user can override |
| P1 | Payment term capture | Wei Yon | After delivery address step, bot asks cash/credit term; term applied to SO before creation |
| P1 | Credit limit / AR exposure — block at DN level | Wei Yon | DN submit blocked when DO value exceeds credit limit OR below-floor price; order creation is not blocked. Block is DO-value-triggered (not just outstanding balance flag). Shows AR, pending SO/DN, credit limit, available balance. |
| P1 | AR-negative approval path | Wei Yon | AR-negative (prepaid) customer → approve on bank-in slip receipt. Credit-limit-exceeded → separate case-by-case bank-in approval. Both route to Ivan. |
| P1 | Minimum price approval block | Wei Yon | Quotation draft allowed; DN/SO submit blocked until approval when price below floor |
| P1 | Custom item variant support | Wei Yon | Item lookup handles {Customer Name} G5-style naming; matched against base item and customer history |
| P1 | WhatsApp latency investigation | Wei Yon | Identify why WhatsApp response is slower than Telegram; remediation or escalation |
| P1 | AutoCount external ID consistency | Wei Yon | Submitted doc displays AutoCount ID, not only MAIA internal ID |
| P2 | Warehouse / shelf configuration review | Wei Yon | Picking list / DN shows shelf/warehouse info correctly |
| P2 | Performance test on real usage | Jermaine | Chatbot/web response remains usable under concurrent order scenarios (30 invoices/day) |

## Immediate Execution Plan

### Day 1 (Wed 25 Jun) — Alignment Lock

Product lead + tech lead + PM align on one critical outcome: fix the pricing decision step first. Do not spread effort across all remaining features until this is usable.

Product to deliver:

Final pricing table mockup

Final chatbot prompt wording

Exact happy-path flow

Scope classification: must-fix / defer / CR

Tech to confirm:

Where historical invoice data comes from

Whether discount %, net price, standard price are available reliably

Whether WhatsApp can display the table cleanly, or whether web/image table is needed

### Day 2–3 (Thu 26 Jun – Fri 27 Jun) — Build P0 Fixes

Tech focuses only on:

Historical pricing API (invoices, min 5 rows)

Discount calculation

Item-level discount

Short chatbot response/table formatter

Language bug fix

Stop premature QTN/SO generation before price confirmation

Product supports with live examples and expected output.

### Day 4 (Mon 30 Jun) — Internal Retest

Run one full Fixguru scenario end-to-end:

Customer sends WhatsApp order → MAIA identifies customer by phone → shows last 5 historical invoice prices per item → user chooses discount per item → MAIA generates QTN/SO → PDF → delivery method + address selected → cash/credit term confirmed → approval check if needed.

Pass criteria: user should not need to open AutoCount for the pricing decision.

### Day 5 (Tue 1 Jul) — Client Retest

Show Fixguru only the corrected pricing flow first. Do not demo all features. Goal: prove the main blocker is fixed before moving to delivery, credit, PDF, and warehouse flows.

## Lead-Review Recommendation (P0 Recovery Scope)

Historical pricing + discount decision UX (invoice-sourced, min 5 rows, one glance)

Correct item-level discount calculation

One-glance chatbot/table output + language bug

Phone/customer search (mobile + landline)

Delivery method as item/SKU

Credit/minimum price approval visibility (block at DN level, DO-value-triggered; two paths)

Everything else is secondary until Fixguru confirms the first sales pricing flow is finally usable.

|（注：部分内容可能由 AI 生成）