22 June 26 - Forensic Account Dossier

# Source Manifest — what I actually received and processed

| Source item | Type | Date range | Volume | Processed in full? | Evidence |
| --- | --- | --- | --- | --- | --- |
| 3_3_2026 Fixguru E-Invoice (SI_CN_DBN) Sync.docx | Doc | 2026-03-03 | 1 doc | Yes | fileciteturn6file12 |
| Fixguru <> Mindhive - UAT Brief - Transcript | Transcript | 2026-04-07 | 1 call | Yes | fileciteturn2file2 |
| Fixguru Meta Setup Fixing - Transcript | Transcript | 2026-05-07 | 1 call | Yes; duplicate copy also present | fileciteturn6file18 |
| Fixguru <> Mindhive - UAT Brief & Historical Pricing Testing - Transcript | Transcript | 2026-05-13 | 1 call | Yes, but ASR quality is weak | fileciteturn0file2 |
| Fixguru <> Mindhive - UAT (On-site) - Transcript | Transcript | 2026-05-14 | 1 long UAT call/session | Yes, but ASR quality is noisy | fileciteturn3file0 |
| Fixguru <> Mindhive - UAT (On-site) - stock backward visibility transcript | WhatsApp-style transcript / meeting extract | 2026-05-14 | 1 thread/extract | Yes | fileciteturn5file7 |
| Fixguru feedback sync - Transcript | Internal Mindhive transcript | 2026-05-15 | 1 call | Yes | fileciteturn0file8 |
| Fixguru Scoping Sync - Transcript | Transcript | 2026-05-19 | 1 call | Yes, but ASR quality too poor for many claims | fileciteturn0file0 |
| Fixguru UAT Gaps.docx | Gap register / meeting notes | Post-2026-05-14 | 1 doc | Yes | fileciteturn6file7 |
| Fixguru UAT prep & brief - Transcript | Internal UAT prep transcript | 2026-06-16 | 1 call | Yes, but ASR quality is noisy | fileciteturn0file3 |
| Fixguru SOW.docx | SOW | Effective 2025-07-22 | 1 doc | Processed via indexed extract, not local file | fileciteturn2file0 |
| Fixguru MAIA - Product Specification Baseline (SOW).docx | Product baseline / SOW | Undated baseline | 1 doc | Processed via indexed extract, not local file | fileciteturn6file9 |
| Fixguru Scope Gathering (17_7_2025).docx | Discovery notes | 2025-07-17 | 1 doc | Processed via indexed extract, not local file | fileciteturn4file0 |
| Fixguru 2nd UAT Plan.docx | UAT recovery plan | Created 2026-06-06; updated 2026-06-07 | 1 doc | Processed via indexed extract, not local file | fileciteturn4file1 |
| Fixguru Functional Requirements.docx | Requirements / diagram | Undated | 1 doc | Targeted extract only | fileciteturn1file14 |

Coverage gaps / named-but-not-provided sources: WhatsApp group history, Jam videos, Fireflies original recording, Claude meeting notes, Granola action notes, updated RSC/Diecut Excel files, Volume Metrics Excel, signed SOW copy, payment records, actual UAT form submissions, actual MAIA build/test logs, AutoCount API logs, and post-Jun-17 sign-off outcome were not provided as primary evidence. Any claim requiring those sources is marked INSUFFICIENT EVIDENCE.

# Fixguru — Account Dossier (v1, 2026-06-20)

## PART A — Executive Layer

### A1. Snapshot

| Phase | Contract value | Relationship health | Overall confidence | One-line status |
| --- | --- | --- | --- | --- |
| UAT recovery / second UAT preparation after a failed or blocked first UAT | RM48,000 one-off; RM24,000 deposit + RM24,000 on UAT completion; estimated monthly RM1,000 OpenAI/platform + RM200 server | RED for first-UAT trust; AMBER if Jun 16–17 fixes passed | MED-HIGH | The client’s decisive success condition is not “chatbot exists”; it is whether MAIA can replace AutoCount-facing sales execution without losing historical pricing, discounts, credit controls, stock/branch/PDF fidelity, and speed. fileciteturn6file4 fileciteturn6file8 fileciteturn6file7 fileciteturn4file1 |

### A2. Top 5 things that matter most right now — client POV

Historical pricing + customer/item discount is sign-off critical. The client said, “if it’s not done right we cannot sign off,” and later repeated that without historical discount/net price the sales team has “no point” using MAIA. fileciteturn2file2 fileciteturn6file8

MAIA must be faster or operationally better than AutoCount, not just integrated with it. The UAT gap register records “They feel doing autocount is much faster than chatbot,” and the client complained during UAT that they were “wasting time here.” fileciteturn6file7 fileciteturn3file0

Sales concurrency is a hard workflow requirement. Fixguru salespeople handle 4–10 active customer orders simultaneously, while the observed chatbot flow could create multiple SOs but could not edit mid-flow reliably. fileciteturn6file7

AutoCount fidelity matters: IDs, PDF templates, branch contacts, delivery method-as-SKU, credit exposure, stock/shelf/warehouse, and document traceability are not cosmetic. These are recorded UAT gaps and first-time/retest items in the second UAT plan. fileciteturn6file14 fileciteturn6file5

Second UAT is not a formality; it is a recovery event. The Jun 7 plan still had retests, first-time tests, pending BE/FE/PDF work, and “fixing/testing” statuses before the planned Jun 16–17 on-the-spot UAT. fileciteturn4file1 fileciteturn6file5

### A3. The Ultimax check — headline

Material divergence found. Confidence: HIGH.

The most dangerous divergence is this: Fixguru appears to believe they are buying a sales execution layer that lets their team stop relying on AutoCount during daily quoting/order work, while the build and scope evidence shows MAIA was still catching up to AutoCount fidelity at UAT: historical discount, item-level pricing, branch contacts, PDF templates, delivery method-as-SKU, stock/shelf, credit exposure, external IDs, and 2-way sync were still being fixed, retested, or first-tested. The client’s own words are direct: “If I use it, I must well owe you an account. Right? So I wouldn’t need your your this back end. I want it to be there,” and “if this thing no circle… cannot kick start ready.” fileciteturn6file8

### A4. Recommended next moves — maximum 3

Owner: Ivan / Gareth — run a “client-visible acceptance matrix” before any sign-off ask. Separate Must Pass for UAT, Accepted Deferral, and Chargeable CR across historical pricing, item-level discount, branch contact, PDF, credit exposure, stock/shelf, 2-way sync, and delivery method-as-SKU; tie every row to the SOW or CR boundary. fileciteturn6file5 fileciteturn6file14

Owner: Gareth — force explicit Fixguru sign-off authority. The evidence shows people can block UAT verbally, but not who can legally sign UAT or scope changes; unresolved signing authority is a high-risk account control gap. fileciteturn2file2 fileciteturn4file1

Owner: Ivan / Jermaine — decide the AutoCount policy: “MAIA replaces daily AutoCount operations” vs “MAIA assists and syncs.” The relationship will keep bleeding if scope is sold as replacement but engineered as partial assistant/integration. fileciteturn4file0 fileciteturn6file7

## PART B — Evidence Layer

### B1. Source manifest & coverage / blindness

Source coverage: The dossier is built from discovery docs, SOW/product baseline extracts, UAT transcripts, internal feedback sync, UAT gap register, e-invoice notes, and second-UAT plan. fileciteturn4file0 fileciteturn2file0 fileciteturn6file7 fileciteturn4file1

Structural blindness by source type:

| Source type | What it can show | What it cannot prove |
| --- | --- | --- |
| Transcripts | What was said in meetings/UAT, pain, objections, verbal commitments, observed confusion | Final agreed scope unless contractually incorporated; actual build state unless demonstrated live; full async sentiment |
| Gap docs | Mindhive’s internal synthesis of problems, action items, CR candidates | Whether client formally agreed to each deferral/CR; whether each bug was fixed later |
| SOW / baseline docs | Contracted scope, acceptance criteria, commercial terms | Whether implementation passed; whether client expectations drifted after signing |
| 2nd UAT plan | Latest visible recovery plan and dev/test status as of Jun 7 | Actual Jun 16–17 UAT result; post-UAT acceptance; production readiness |
| E-invoice note | Specific e-invoice preference and cutoff facts | Full e-invoice implementation status or LHDN integration behavior in MAIA |

### B2. Chronological timeline

| Date | Event | Who | What changed | Evidence |
| --- | --- | --- | --- | --- |
| 2025-07-17 | Scope gathering | Mindhive + Fixguru | Painpoints captured: sales/operations miscommunication, stock count, no reminders, no customer follow-up, custom products, no raw-material tracking. | fileciteturn4file0 |
| 2025-07-17 | AutoCount positioned as core system | Fixguru / discovery notes | AutoCount recorded as main database; process captured as Quotation → Sales Order/proforma → DO → Invoice; one proforma can have two or more DOs. | fileciteturn4file0 |
| 2025-07-17 | Pricing model discovered | Fixguru / discovery notes | Each customer has their own pricing and set discount; B2B customers have credit terms and management approval for credit term. | fileciteturn4file0 |
| 2025-07-17 | Target operational flow captured | Discovery notes | Bot should coordinate sales → operations → driver, update status, validate payment, create DO/invoice, and remind sales on inactive customers. | fileciteturn4file0 |
| 2025-07-22 | SOW effective date | Mindhive + IAM Worldwide / Fixguru | SOW frames project as internal WhatsApp AI chatbot integrated with MAIA and AutoCount for B2B order-to-delivery. | fileciteturn2file0 |
| 2025-07-22 | Commercial terms set | Mindhive + Fixguru | One-off development cost RM48,000; RM24,000 on confirmation and RM24,000 on UAT completion; monthly estimates RM1,000 platform/OpenAI and RM200 server. | fileciteturn6file4 |
| 2025-07-22 | Acceptance criteria set | Mindhive + Fixguru | 100% automated DO/invoice generation for qualifying orders; credit checks block invoice creation when limits exceeded; POD image within 5 minutes; sync failure ≤0.1% over 30-day UAT. | fileciteturn6file3 |
| 2026-03-03 | E-invoice sync discussion | Mindhive / Fixguru | AutoCount auto-sends e-invoice to LHDN/customer; Fixguru consolidates customers who do not need e-invoice; MAIA should always give customer choice of individual vs consolidated; Fixguru internal cutoff is 5th of month. | fileciteturn6file12 |
| 2026-04-07 | UAT brief begins | Gareth / Fixguru guest | Mindhive provided test form and account; client can log issues via form/WhatsApp/Jam. | fileciteturn6file11 |
| 2026-04-07 | UAT timeline discussed | Gareth / Fixguru guest | One-week UAT proposed; client flagged management travel and asked for possible extension; go-live could move to end of month / early next month depending on bug resolution. | fileciteturn2file2 |
| 2026-04-07 | Historical pricing escalated as blocker | Fixguru guest | Client said historical customer/item price from quotation/invoice is required and “if it’s not done right we cannot sign off.” | fileciteturn2file2 |
| 2026-05-07 | WhatsApp/Meta setup debugging | Mindhive + guest | Meta/WhatsApp setup required creating/using Maya V2, correct phone number ID/token, and later “everything is working” for interactive bot messages; payment method still needed for business-initiated messages. | fileciteturn6file15 fileciteturn5file1 |
| 2026-05-07 | AutoCount pricing mechanics clarified | Fixguru guest | AutoCount has one list price but different customers have different discount structures; historical price/discount is customer+SKU specific, usually past five/seven invoices. | fileciteturn6file18 |
| 2026-05-14 | On-site UAT exposes historical pricing failure | Fixguru guest / Mindhive | Client says discount %, historical data, net price, and standard price must show; wrong discount calculation observed where 3% of RM60 was captured like RM3. | fileciteturn6file8 |
| 2026-05-14 | On-site UAT exposes concurrency/editing mismatch | Fixguru guest / Mindhive | Client describes handling 4–10 customers and needing to edit draft SOs before final submission; chatbot flow was not stable for mid-flow edits. | fileciteturn3file0 fileciteturn6file7 |
| 2026-05-14 | On-site UAT exposes PDF/template mismatch | Fixguru guest / Mindhive | Client says generated PDF/template is different from AutoCount/Fixguru format and default PDF is unacceptable for draft documents. | fileciteturn3file0 fileciteturn6file14 |
| 2026-05-14 | On-site UAT exposes external ID/running-number mismatch | Fixguru guest / Mindhive | Client says documents must follow their AutoCount running number / ID, not MAIA internal ID. | fileciteturn5file17 |
| 2026-05-14 | On-site UAT exposes warehouse/picking fields | Fixguru guest / Mindhive | Client says weight, cubic/volume metric, and shelf number are needed for storage, picking list, and delivery planning. | fileciteturn5file17 |
| 2026-05-14 | Raw material / finished stock workflow discussed | Amirul / Fixguru | Client needs visibility of both finished box stock and raw material stock; raw-to-finished conversion can have yield variance, e.g. 2000 raw → expected 4000 finished but actual 3900. | fileciteturn5file7 |
| 2026-05-15 | Internal feedback sync | Mindhive | Internal team records Fixguru “totally cannot proceed” and starts consolidating UAT gaps such as historical pricing, calculator, branch contacts, PDFs, credit exposure, 2-way sync, language, SKU display. | fileciteturn0file8 |
| Post-2026-05-14 | UAT Gaps doc created | Mindhive | Overall feedback logged: AutoCount faster than chatbot; sequential flow fails; historical pricing/discount not captured; item-level discount unsupported. | fileciteturn6file7 |
| Post-2026-05-14 | UAT gap classification begins | Mindhive | Calculator updates, AutoCount integration gaps, contact/branch sync, PDF template, delivery method-as-SKU, UOM conversion, stock balance, volume metric, shelf/warehouse, credit limit, language, and full document traceability are logged. | fileciteturn6file14 |
| 2026-06-06 / 2026-06-07 | 2nd UAT plan created/updated | Mindhive | Plan targets Jun 16–17 on-the-spot UAT; status includes ready items, retests, first-time tests, and pending dev/fix items. | fileciteturn4file1 |
| 2026-06-09 / Jun 10 plan | Internal fix/testing cadence | Mindhive | Dev fix day and internal live bug-fix session planned; every item should be tested live, with green/deferred decisions by session end. | fileciteturn4file1 |
| 2026-06-16 | UAT prep transcript | Mindhive internal | Discount, standard selling price, historical pricing, FOC, external ID, delivery method, non-stock item, and stock-related issues were still being tested/discussed; transcript quality is weak, so precise status is LOW confidence. | fileciteturn0file3 |

Timeline gaps: There is no primary async WhatsApp evidence between the Apr 7 UAT brief and May 7 Meta setup; no actual Jun 16–17 UAT result; no client written sign-off/conditional sign-off; no post-UAT production/go-live record. These gaps matter because relationship recovery and payment milestone 2 depend on UAT completion. fileciteturn6file4 fileciteturn4file1

### B3. The client’s world

Business reality. Fixguru is a B2B order-to-delivery operation with sales, logistics/operations, drivers, accounts, and management/boss roles; the discovered workflow depends on AutoCount, WhatsApp/internal chatbot, DOs, invoices, stock visibility, payment validation, and delivery proof. fileciteturn4file0

Order volume. The SOW targets “~30 or more confirmed orders/day,” and the UAT gap register says one sales team has 30 invoices per day with high context switching. fileciteturn2file0 fileciteturn6file6

Pricing reality. Each B2B customer can have their own set pricing and discount; AutoCount shows historical customer/SKU price and discount, and Fixguru expects MAIA to surface this during quoting. fileciteturn4file0 fileciteturn6file18

Stock reality. Fixguru cares about finished goods, raw materials, raw-to-finished conversion, yield variance, warehouse/shelf, and volume/weight for picking and lorry planning. fileciteturn5file7 fileciteturn5file17

Document reality. Fixguru’s document flow is Quotation → Sales Order/proforma → DO → Invoice, and one proforma can have multiple DOs; later UAT notes explicitly require traceability where one SO can have multiple DOs and multiple invoices by DO date. fileciteturn4file0 fileciteturn6file6

Success in the client’s words. Success is MAIA making AutoCount lookup unnecessary for the sales workflow: the client said, “If I use it, I must well owe you an account. Right? So I wouldn’t need your your this back end. I want it to be there.” [Fixguru On-site UAT | 2026-05-14 | Guest] fileciteturn6file8

Failure in the client’s words. Failure is needing AutoCount or another person for pricing: “Otherwise, right, we we no point the the pricing, got to get it from other personnel.” [Fixguru On-site UAT | 2026-05-14 | Guest] fileciteturn6file8

What matters to Mindhive about this account — separate list.

Payment exposure: RM24,000 second milestone is tied to UAT completion. fileciteturn6file4

Refund exposure: SOW states refund path if core requirements remain unmet after SLA remediation, including full refund if failure to go live post-UAT. fileciteturn1file0

Product architecture signal: Fixguru exposes a broader AutoCount fidelity pattern: external IDs, draft PDFs, credit exposure, stock/shelf, branch contacts, 2-way sync, and historical data are not edge cases. fileciteturn6file14

Scope-control signal: Calculator expansion from 2 calculators to 5 and updated RSC/Diecut formulas were marked CR candidates, not automatic baseline scope. fileciteturn5file10

### B4. Actors — profiles + decision map

| Actor | Role | Side | Authority | Signing authority? | What they want | Sentiment + trajectory | Representative quote / evidence |
| --- | --- | --- | --- | --- | --- | --- | --- |
| Guest / likely Fixguru senior user or stakeholder | UAT participant / operational stakeholder | Client | Blocker / high influence | UNKNOWN | Historical pricing, AutoCount-equivalent workflow, discount %, net price, AutoCount IDs/PDFs | Neutral at Apr brief → sharply negative at May 14 UAT | “This one if it’s not done right we cannot sign off…” [UAT Brief |
| Marcus | Named in UAT gaps / likely client tester or stakeholder | Client | Influence / possible blocker | UNKNOWN | Sales-doc creation/editing accuracy; confusion adding item into active quotation/SO | Negative/friction in UAT notes | “Confusion in adding item for Sales Order into a Quotation that user just talk about (Marcus).” fileciteturn6file6 |
| Stephen | Mentioned as possible attendee | Client | UNKNOWN | UNKNOWN | UNKNOWN | INSUFFICIENT EVIDENCE | Mentioned as possibly joining in Apr 7 UAT brief. fileciteturn6file10 |
| Yvonne / “Yvong” | Mentioned in UAT brief and on-site transcript | Client | UNKNOWN | UNKNOWN | Historical pricing possibly discussed with previous Mindhive staff | UNKNOWN | Client references prior conversation about historical data and Yvonne is named in meeting context. fileciteturn2file2 |
| Xiao Ling, Hayati, Zuha, Abishaah/Wendy, Marcus | Listed 2nd UAT testers | Client | Testers / influence | UNKNOWN | Execute Jun 16–17 UAT | UNKNOWN before actual result | 2nd UAT plan lists them as Fixguru testers for on-the-spot UAT. fileciteturn4file1 |
| Gareth | PM / account operator | Mindhive | Delivery owner / coordinator | No evidence of signing authority | UAT planning, gap triage, dev coordination | Internal problem-owner | 2nd UAT plan names PM/Gareth across Jun 9–11 testing and scheduling. fileciteturn4file1 |
| Amirul | Developer / FE-calculator-related | Mindhive | Implementation owner for some items | No | Calculator, item-level discount, volumetric FE/PDF | Fixing/testing | 2nd UAT plan assigns item-level discount auto-compute and volumetric FE/PDF to Amirul/Rahim. fileciteturn6file5 |
| Bryan | Chatbot developer | Mindhive | Chatbot implementation owner | No | Historical pricing chatbot, UOM, 2-warehouse, language, HQ+branch chatbot | Fixing/testing | 2nd UAT plan assigns multiple chatbot fixes to Bryan. fileciteturn6file5 |
| Azib | Backend / integration owner | Mindhive | Implementation owner | No | External doc ID, branch contact sync, 2-way sync, 2-warehouse sync | WIP/done split | 2nd UAT plan assigns Azib to external doc ID, HQ+branch contact sync, 2-way sync, warehouse sync. fileciteturn6file5 |
| WeiShen | Credit-limit chatbot owner | Mindhive | Implementation owner | No | Credit limit exposure chatbot | Testing | 2nd UAT plan says credit limit exposure chatbot: WeiShen testing. fileciteturn6file5 |
| Johnson Goh | CEO, Mindhive | Mindhive | Vendor executive | Yes for Mindhive in SOW signature block | Commercial accountability | Present in on-site UAT attendees | SOW signature block names Johnson Goh as CEO; on-site attendees include Johnson. fileciteturn1file0 fileciteturn3file0 |
| Jermaine | CTO / senior technical stakeholder | Mindhive | Technical authority | No evidence of signing authority | Scope/product decisions | Present in on-site UAT/internal sync | On-site and feedback sync attendees include Jermaine. fileciteturn3file0 fileciteturn0file8 |

Authority ambiguity — high risk. The evidence shows UAT-blocking statements from a “Guest,” but no signed Fixguru authority map, no named UAT signatory, and no evidence identifying who can approve CRs or deferrals. The 2nd UAT plan lists testers but not signatory authority. fileciteturn2file2 fileciteturn4file1

### B5. Commercial state

| Item | State | Evidence |
| --- | --- | --- |
| Contract party | Mindhive Sdn Bhd and IAM Worldwide Sdn Bhd (“Fixguru”) | fileciteturn2file0 |
| Effective date | 2025-07-22 | fileciteturn2file0 |
| One-off cost | RM48,000 | fileciteturn6file4 |
| Payment terms | 50% RM24,000 project confirmation; 50% RM24,000 UAT completion | fileciteturn6file4 |
| Monthly estimates | OpenAI/platform ~RM1,000 depending on usage; server RM200 | fileciteturn6file4 |
| Refund exposure | Full 100% refund if failure to go live post-UAT; refund tied to unmet core requirements after SLA remediation and written notice | fileciteturn1file0 |
| Paid vs unpaid | INSUFFICIENT EVIDENCE — payment records not provided | Source gap |
| Change requests | Calculator expansion to 5 calculators, updated formulas, volume metrics, raw-to-finished customization are treated or proposed as CR/chargeable in UAT gaps | fileciteturn5file10 |
| Retainer revision | Internal feedback sync indicates retainer may need revision if wider 2-way sync/data migration is needed, but no commercial agreement provided | fileciteturn0file8 |

### B6. Commitments ledger — both directions

| Commitment | Direction | Made when / where | Due | Status | Evidence |
| --- | --- | --- | --- | --- | --- |
| Internal WhatsApp-based AI chatbot integrated with MAIA and AutoCount | Mindhive → Fixguru | SOW | Project delivery | Open / UAT not proven complete | fileciteturn2file0 |
| Nightly master/transaction sync to AutoCount | Mindhive → Fixguru | SOW | UAT / production | Open; later 2-way sync under testing | fileciteturn2file0 fileciteturn6file5 |
| Bot drafts quotation and pro-forma invoice from sales agent chats | Mindhive → Fixguru | SOW high-level flow | UAT | Partially built; UAT gaps around editing, PDF, pricing | fileciteturn2file0 fileciteturn6file7 |
| Credit-limit / credit-term checks before invoice/DO | Mindhive → Fixguru | SOW / discovery | UAT | Open/testing; credit exposure first-time tests pending | fileciteturn2file0 fileciteturn6file5 |
| Historical pricing/customer discount visibility | Mindhive → Fixguru, per client-stated prior agreement | Apr 7 UAT brief / May 7 clarification | Before sign-off | Broken at first UAT; retest/fix later | fileciteturn2file2 fileciteturn6file8 fileciteturn6file5 |
| Calculator in quotation | Mindhive → Fixguru | Apr 7 UAT brief | After Friday / UAT | Later “Calculator RSC + Diecut tested, complete”; expansion beyond 2 calculators treated as CR | fileciteturn5file12 fileciteturn6file2 fileciteturn5file10 |
| Fixguru provides WhatsApp Business number | Fixguru → Mindhive | SOW dependency | Setup | Met enough for bot messages after Meta debugging; business-initiated payment setup remained later | fileciteturn6file3 fileciteturn5file1 |
| Fixguru supplies Lalamove credentials | Fixguru → Mindhive | SOW dependency | Integration | INSUFFICIENT EVIDENCE | fileciteturn6file3 |
| Fixguru internal roles allocated/trained | Fixguru → Mindhive | SOW dependency | UAT/training | INSUFFICIENT EVIDENCE | fileciteturn6file3 |
| Internal users during business hours; languages English/Malay/Mandarin | Mindhive → Fixguru | SOW non-functional requirement | UAT | Gap: multilingual response not working; client staff cannot read English; plan later has language preference in dev | fileciteturn6file3 fileciteturn6file6 fileciteturn6file5 |
| Sign-off / conditional sign-off after Jun 16–17 UAT | Fixguru + Mindhive | 2nd UAT plan | Jun 16–17 | INSUFFICIENT EVIDENCE; plan only | fileciteturn4file1 |

### B7. Decisions log

| Decision | Made by | When / where | Locked or reversible | Downstream impact | Evidence |
| --- | --- | --- | --- | --- | --- |
| AutoCount is main database / master record for many objects | Discovery / SOW | 2025-07-17 and SOW | Locked at architecture level unless renegotiated | MAIA must preserve AutoCount IDs, stock, pricing, customer, document fidelity | fileciteturn4file0 fileciteturn2file0 |
| UAT timeline extended beyond initial one week due to Fixguru management travel | Client / Gareth | 2026-04-07 | Reversible schedule decision | Go-live shifted toward end-April/early-May depending bug resolution | fileciteturn2file2 |
| Historical pricing must be addressed before sign-off | Fixguru guest | 2026-04-07 | Functionally locked by client | Blocks UAT sign-off and milestone 2 | fileciteturn2file2 |
| Use current Fixguru WhatsApp/Meta app setup via correct phone/token | Mindhive / guest | 2026-05-07 | Operational | Enabled interactive bot messages | fileciteturn5file1 |
| Customer price enforcement as field-level read-only; lock icon signals it | Mindhive | 2nd UAT Plan | Reversible only via scope change | Narrows implementation approach for pricing enforcement | fileciteturn6file1 |
| QTN amendment API blocker: API does not exist | Mindhive | 2nd UAT Plan | Hard technical blocker unless new API/workaround | Limits ability to amend quotations through expected flow | fileciteturn6file1 |
| Calculator scope: only 2 calculators RSC + Diecut; additional Pizza/Layer Pad/5 panels are CR | Mindhive | UAT Gaps | Reversible with paid CR | Prevents scope creep from 2 to 5 calculators | fileciteturn5file10 |
| Updated RSC/Diecut formula Excels are CR | Mindhive | UAT Gaps | Reversible with CR | Formula drift needs versioning process | fileciteturn5file10 |
| Item shelf in chatbot scoped to additional note on DN only | Mindhive | 2nd UAT Plan | Reversible | Limits shelf implementation to DN note, not full model | fileciteturn6file1 |
| 2nd UAT should be on-the-spot Jun 16–17 | Mindhive plan | 2026-06-06/07 | Reversible schedule | Recovery plan depends on live testing and punch-list sign-off | fileciteturn4file1 |

### B8. Understood deliverable vs scope vs build — feature-by-feature Ultimax check

| Feature / deliverable | What client believes they get | What is actually scoped | What is actually built / status evidence | Divergence | Gap type |
| --- | --- | --- | --- | --- | --- |
| Historical customer-item pricing | MAIA shows last quoted/invoiced price, discount %, standard/net price, enough to avoid AutoCount lookup | SOW mentions order/quotation management and custom quotation; discovery records each customer has own pricing/discount, but SOW extract does not explicitly name historical price lookup | Apr 7 blocker; May 14 failing; Jun 7 retest/chatbot fix | Material divergence — client treats as sign-off condition; build was not UAT-ready initially | TRANSLATION / possible CAPTURE |
| Item-level discount | Discounts by item/customer; normal percentage rounding; discount column visible | Approval for selling below min price is scoped; detailed item-level discount mechanics not clearly scoped in SOW extract | UAT Gaps: item-level discount unsupported; 2nd UAT plan: auto-compute fix by Amirul, testing/retest | Material divergence | TRANSLATION |
| AutoCount PDF template / draft docs | Use Fixguru/AutoCount PDF style even in draft mode | SOW scopes document generation; not clear that exact AutoCount draft template is guaranteed | UAT Gaps: wrong PDF templates, default PDF for unsubmitted sales doc; 2nd UAT: custom draft PDF in progress/testing | Material divergence | TRANSLATION |
| External AutoCount IDs / running numbers | Salespeople use AutoCount SBI/SPI-style IDs; MAIA must show those | SOW scopes AutoCount sync; exact external ID display not explicit in cited extract | UAT gaps: MAIA item code instead of theirs; 2nd UAT: external SKU done, external doc ID pending/WIP | Divergence | TRANSLATION |
| Sales concurrency / multitasking | Sales can handle 4–10 active orders and edit mid-flow | SOW non-functional peak capacity says ≥60 concurrent internal chats / 30+ orders/day, but concurrency ≠ multi-order edit context | UAT Gaps: sequential flow fails; chatbot cannot edit mid-flow; concurrency needs testing | Material divergence | CAPTURE / TRANSLATION |
| Branch contacts / delivery addresses | Customer branch-specific address/contact should flow correctly | Customer sync scoped; detailed branch-contact per delivery address not explicit in SOW extract | UAT Gaps: multiple contacts/branch data not syncing; 2nd UAT: HQ+branch contact blocker/dev fixing, then done/test | Divergence | CAPTURE / TRANSLATION |
| Credit limit exposure | Users/approvers see owing, current DO/SO amount, credit limit, available balance before approval | Credit-limit/term enforcement scoped; acceptance says credit checks block invoice when exceeded | UAT Gaps: credit limit sync, inconsistent Indah Pesona figures; 2nd UAT: credit exposure first-time test/testing | Divergence | TRANSLATION |
| Stock balance / warehouse / shelf | Prevent oversell; show stock, shelf, warehouse, picking list info | Inventory and stock tracking scoped; AutoCount/WMS authoritative in baseline | UAT Gaps: stock balance cannot be identified; shelf/warehouse needed; 2nd UAT retests 2-warehouse/shelf | Divergence | TRANSLATION |
| Raw material → finished goods planning | Sales can commit based on finished stock + raw material convertible quantity and yield variance | Discovery mentions raw materials; SOW scopes inventory/stock tracking generally | UAT Gaps treats multi-level stock and raw-to-finished yield as customization/chargeable discussion | Divergence if client expects it included | CAPTURE / DEFERRAL |
| FOC quantity | Same logical line has billable qty + FOC qty; stock decrements both, revenue only billable | Not explicit in SOW extract | 2nd UAT plan says FOC done; UAT gaps explains ERPNext lacks native side-by-side FOC column | Smaller divergence, likely resolved by workaround | TRANSLATION |
| Delivery method as SKU | “3PL Lalamove” can be a line item because it affects accounting/e-invoice treatment | Lalamove API / delivery options scoped; delivery-method-as-SKU not explicit | UAT Gaps: chatbot treated 3PL Lalamove as delivery method, not item; 2nd UAT: delivery method as SKU in scope/dev fixing | Divergence | CAPTURE / TRANSLATION |
| Volume/weight/cubic metrics | Needed in DN/PDF and logistics planning | Not explicit in SOW extract except inventory/logistics broadly | UAT Gaps says volume metric m3 desired; 2nd UAT: volumetric BE done, FE/chatbot/PDF in progress | Divergence | CAPTURE / TRANSLATION |
| Calculator formulas | RSC + Diecut calculator in quotation; possibly latest formula behavior | SOW says custom box quotation module based on IAM Excel sheet | 2 calculators done; client now has 5 calculators and updated formula Excels; CR decision | No divergence for 2 calculators; divergence for 5/new versions | DEFERRAL / CR |
| E-invoice choice | Customer gets choice: individual vs consolidated; Fixguru cutoff 5th | E-invoice note captures specific behavior | Build status unknown | INSUFFICIENT EVIDENCE | Unknown |
| Language | English, Malay, Mandarin | SOW says English, Malay, Mandarin | UAT gaps: multilingual response not working; staff cannot read English; 2nd UAT: language preference in dev/done by backend/chatbot but unproven client pass | Divergence | TRANSLATION |
| Full document traceability | One SO can have multiple DOs and one invoice per DO/date | Discovery says one proforma can have 2+ DOs | UAT Gaps says make sure retrievable; build status unknown | Potential divergence | TRANSLATION |

### B9. Gaps & risks — prioritized

| Gap / risk | Evidence | Gap type | Impact if unaddressed | Severity | Owner |
| --- | --- | --- | --- | --- | --- |
| Historical pricing/discount remains the account’s sign-off killer | Client explicitly said cannot sign off if not done; UAT showed discount/history failures | TRANSLATION | No UAT sign-off; RM24k milestone blocked; refund exposure | H | Gareth + Bryan + Amirul |
| Trust erosion from failed first UAT | UAT Gaps says AutoCount faster; client said no point/wasting time/cannot proceed | N/A relationship | Client churn/refund posture; second UAT becomes adversarial | H | Ivan + Gareth |
| Scope ambiguity: MAIA replacement vs assistant | Client expects not to return to AutoCount; build still depends on AutoCount and partial sync fidelity | CAPTURE | Endless “this is expected” vs “this is scope” arguments | H | Ivan + Jermaine |
| AutoCount fidelity gaps | External IDs, PDF templates, branch contacts, delivery method-as-SKU, stock, shelf, credit exposure, 2-way sync | TRANSLATION | Client sees MAIA as slower/wrong vs current system | H | Azib + Rahim + Gareth |
| Credit exposure accuracy | SOW scopes credit checks; UAT gaps note credit limit sync and inconsistent figures | TRANSLATION | Wrong approval/rejection decisions; financial risk to client | H | Fariha/Haiqal/WeiShen |
| Concurrency/editing mismatch | 4–10 active customer orders; chatbot cannot edit mid-flow | CAPTURE / TRANSLATION | Sales users abandon chatbot because it does not match work reality | H | Bryan + Product |
| Signing authority unknown | UAT blockers are verbal; testers named but signatory not identified | Governance | Wrong person signs/blocks; scope/CR disputes | H | Gareth / Ivan |
| Calculator formula versioning | Updated RSC/Diecut formulas and 5 calculators | DEFERRAL / CR | Perpetual formula drift; unpaid scope creep | M-H | Gareth / Product |
| Language support gap | SOW has English/Malay/Mandarin; UAT gaps say staff cannot read English and multilingual response not working | TRANSLATION | Adoption failure for non-English staff | M-H | Bryan / Azib |
| Raw material planning/yield variance | Client needs raw+finished visibility; UAT gaps recommend quote/spec/charge | CAPTURE / DEFERRAL | Sales promise dates from incomplete availability | M-H | Ivan / Product |
| E-invoice choice | Specific requirement exists; implementation status unknown | Unknown | Compliance/process mismatch near monthly cutoff | M | Gareth |
| WhatsApp business-initiated message billing | Meta setup says interactive messages work, payment method later needed for business-initiated messages | Dependency | Reminder/notification failures if unpaid or not configured | M | Fixguru + Mindhive PM |

### B10. Relationship health & sentiment trajectory

| Date / phase | Sentiment | Evidence | Confidence |
| --- | --- | --- | --- |
| Discovery / SOW | Constructive: client has clear operational pain and measurable goals | Painpoints, order volume, SOW objectives/key results | HIGH |
| Apr 7 UAT brief | Cautious but cooperative; first major blocker raised | Client agrees to test but flags management travel; then historical pricing as cannot-sign-off issue | HIGH |
| May 7 Meta/pricing sync | Technical debugging plus clarification; not hostile | WhatsApp setup solved; pricing mechanics clarified | MED |
| May 14 on-site UAT | Negative / at-risk | Client repeatedly says cannot proceed, no point, wrong template/discount, wasting time | HIGH |
| May 15 internal sync | Mindhive recognizes account is blocked | Internal note: Fixguru “totally cannot proceed”; UAT gap register created | HIGH |
| Jun 7 second UAT plan | Recovery posture | Many fixes/testing items planned; second UAT scheduled with punch list | MED |
| Jun 16 prep | Still fragile | Transcript shows continued testing/debugging; ASR too noisy for confident client-facing conclusion | LOW-MED |

Load-bearing quotes:

“This one if it’s not done right we cannot sign off because this was the deal that we want to we already agreed that we need that otherwise right this thing cannot work.” [Fixguru UAT Brief | 2026-04-07 | Guest] fileciteturn2file2

“Someone will have to pick up because this was the deal that we agreed. Before we even kickstart…” [Fixguru UAT Brief | 2026-04-07 | Guest] fileciteturn6file13

“One list price. Correct. But different customers have different discount structures.” [Meta Setup Fixing | 2026-05-07 | Guest] fileciteturn5file1

“You just need pull up from the system… historical past five invoices.” [Meta Setup Fixing | 2026-05-07 | Guest] fileciteturn6file18

“I know need to go here… For me my sales team can kick start using… Otherwise… no point…” [On-site UAT | 2026-05-14 | Guest] fileciteturn6file8

“3% of 60 ringgit is not 3 ringgit. They capture, but they capture 3 ringgit instead of 3%.” [On-site UAT | 2026-05-14 | Guest/You sequence] fileciteturn6file8

“Our is SPI… Anything else, please follow our running number.” [On-site UAT | 2026-05-14 | Guest] fileciteturn5file17

“You’re wasting time here.” [On-site UAT | 2026-05-14 | Guest] fileciteturn3file0

### B11. Open questions / unresolved threads

| Unresolved thread | Last touched | Why it matters | Evidence |
| --- | --- | --- | --- |
| Who can sign UAT? | 2nd UAT plan lists testers, not signatory | Payment and closure depend on valid sign-off | fileciteturn4file1 |
| Did Jun 16–17 UAT pass, conditionally pass, or fail? | 2nd UAT plan schedules it | Current account status cannot be declared closed | fileciteturn4file1 |
| Was historical pricing accepted by client after fixes? | Jun 7 says testing/retest | It is the top blocker | fileciteturn6file5 |
| Did credit exposure figures become accurate? | Jun 7 says testing; UAT gaps say inconsistent Indah Pesona figures | Wrong credit decisions are financially dangerous | fileciteturn6file6 |
| Was exact AutoCount/Fixguru PDF template accepted? | Jun 7 says draft custom PDF template testing | Client objected strongly to wrong/default templates | fileciteturn6file14 |
| Was 2-way sync implemented or only scoped/testing? | Jun 7 says need align/testing; UAT gaps says all QTN/SO/SI from AutoCount not in MAIA yet | Without this, fallback-to-AutoCount breaks MAIA state | fileciteturn6file5 fileciteturn6file14 |
| Is raw-material planning included or quoted as CR? | UAT gaps says quote/spec/charge | Client may treat it as operationally necessary | fileciteturn5file10 |
| Are updated RSC/Diecut formulas supplied? | UAT gaps says pending from Fixguru | Calculator accuracy depends on latest formulas | fileciteturn5file10 |
| Is Volume Metrics Excel supplied? | UAT gaps says pending / need? | DN/PDF and lorry planning depend on volume metrics | fileciteturn5file10 |
| Was e-invoice behavior implemented in MAIA? | Mar 3 note defines process, no build evidence | Monthly cutoff and customer choice matter | fileciteturn6file12 |

### B12. What we do NOT know — mandatory

| Unknown | Why it matters | Source/action to resolve |
| --- | --- | --- |
| Whether Fixguru signed the SOW and who signed | Determines legal authority and enforceability | Signed SOW |
| Whether RM24,000 deposit was paid | Determines commercial exposure and project state | Payment record / invoice |
| Whether RM24,000 UAT milestone was invoiced/paid | Determines closure status | Payment record / UAT sign-off |
| Actual Jun 16–17 UAT outcome | Current relationship status hinges on this | UAT form, minutes, signed punch list |
| Actual MAIA build state after Jun 16 | The plan is not proof of delivery | Deployment logs, QA results, client retest |
| Which Fixguru person can approve CRs / deferrals | Prevents scope disputes | Client RACI / written email |
| Whether historical pricing fixed behavior matches client expectation | Top blocker | Client demo recording + acceptance checklist |
| Whether AutoCount API supports all branch/contact/PDF/sync needs | Some gaps may be technical blockers | API docs/logs |
| Whether Chinese/Malay response is contractually required as full response language or only intake | SOW says languages; internal discussion proposes partial support | Signed language acceptance criterion |
| Whether e-invoice logic is in scope for current UAT | Mar note exists but implementation evidence missing | UAT cases / SOW annex |
| Whether raw material/yield variance is baseline or CR | Client may see it as stock visibility; Mindhive notes treat as customization | CR decision doc |
| Whether performance is acceptable at 30+ orders/day / 4–10 active customer contexts | UAT gap says this is real workflow; no load test evidence | Load test + sales team shadow test |

## PART C — Synthesis

### C1. Confidence statement

RICH evidence / HIGH confidence

Historical pricing and discount visibility are sign-off critical. The client said it directly in Apr 7 UAT brief, and the same issue reappeared during May 14 UAT and Jun 7 retest planning. fileciteturn2file2 fileciteturn6file8 fileciteturn6file5

First UAT relationship health was materially at risk. The client’s language and UAT gap register show inability to proceed, AutoCount being faster, and workflow mismatch. fileciteturn6file7 fileciteturn3file0

Contract value and payment structure are clear. fileciteturn6file4

SOW scope includes internal WhatsApp chatbot, AutoCount sync, credit checks, DO/invoice generation, reminders, dashboard, languages, and 30+ order/day capacity. fileciteturn2file0 fileciteturn6file3

THIN evidence / MED-LOW confidence

Actual build state after Jun 16 is unclear; evidence shows plans/tests, not acceptance. fileciteturn4file1

Identity/authority of Fixguru speakers is weak because transcripts use “Guest” and ASR is noisy. fileciteturn3file0

E-invoice implementation status is unknown; only process notes are available. fileciteturn6file12

Paid-vs-delivered status is unknown because payment and sign-off records are absent. fileciteturn6file4

Conclusion that would break if wrong: The dossier’s core claim — “material divergence exists between client expectation and build/scope at first UAT” — would weaken only if there is later unprovided evidence showing Fixguru formally accepted all key divergences as deferred/CR and passed Jun 16–17 UAT. No such evidence was provided.

### C2. Rollup handoff note — for cross-account Q3 plan

Build-once: AutoCount fidelity layer — external IDs, branch contacts, draft PDF template, credit exposure, stock/shelf/warehouse, document traceability. Fixguru shows these are not client-specific luxuries. fileciteturn6file14

Product policy: Historical pricing/customer-item discount needs a first-class module, not prompt-level patching. fileciteturn6file18 fileciteturn6file8

Delivery governance: Every UAT needs a signed acceptance matrix with Pass / Deferral / CR / Out-of-scope before the client session, not after the blow-up. fileciteturn4file1

Commercial guardrail: Formula versioning, new calculators, raw-material planning, and historical migration must have default CR language. fileciteturn5file10

Portfolio signal: If MAIA is sold as “replace your current daily workbench,” parity with the client’s current operational system becomes scope; if it is sold as “assist and sync,” expectations must be reset before UAT. fileciteturn4file0 fileciteturn6file7