Fixguru — 3rd UAT Backward Plan

# Fixguru Action Plan — 3rd UAT Backward Plan

Based on the 24 June 2026 UAT session (Fireflies transcript + [[Meetings/2026-06-24 Fixguru UAT Debrief]] + [[context/learnings]]).

Core conclusion: Client still cannot proceed confidently because the first sales-order pricing step is unsolved. The blocker is not only data correctness — it is how MAIA presents historical price, discount %, net price, and next action in a way sales users can understand in one glance. This repeats 7 Apr, 14 May, and 16 Jun. Prompt-level patching has hit its ceiling; a first-class invoice-sourced module is required.

## Open Decisions (Resolve Before Next Demo Date)

Rendering mechanism — chat single-message vs. image/label vs. dual web interface (70/30 co-work view)

Block level — order vs. DN (client leans DN; must be confirmed and locked in writing)

UAT sign-off authority — confirm Gareth is the signatory (no valid acceptance without this)

Dual interface scope — Phase-1 inclusion or costed CR

## Client Blockers Needed (Ivan to Chase)

| # | Item | From | Why blocking |
| --- | --- | --- | --- |
| C1 | Real WhatsApp order-intake message samples (format reference for parser) | Yvonne | Defines the intake string MAIA must parse |
| C2 | AutoCount screenshot of two blocks (min price + credit limit) + which roles can bypass | Azib | Credit/approval logic can't be built without this |
| C3 | Minimum price floor per item (std + floor, e.g. G1 0.33 / 0.27) | Gareth | Approval threshold rule requires floors |
| C4 | Standard price list (global, fluctuating) — share in group | Gareth | Needed to compute discount % vs. current standard |
| C5 | Updated RSC/Diecut formulas + volume metrics (carryover from prior UAT) | Fixguru | Calculator accuracy still unresolved |
| C6 | Confirm UAT sign-off authority (is Gareth the signatory?) | Ivan ↔ Fixguru | No signed acceptance = Milestone-2 RM24k unpaid |

## Product Action Plan

| Priority | Product action | Why it matters | Output for tech |
| --- | --- | --- | --- |
| P0 | Redesign pricing decision flow | Users abandon when too much text / unclear pricing. First step must be fixed before next flow. | Final UX spec for "Historical Pricing Review before QTN/SO creation" |
| P0 | Define exact historical pricing table fields | Client wants quick comparison, not long chatbot text. Min 5 rows per item (3 is explicitly too few); date matters — signals price drift vs. current standard. | Table columns: Date, Item Code, Qty, Standard Unit Price, Discount %, Net Price, Source Invoice ID |
| P0 | Clarify source of historical pricing | Client confirmed: source must be actual invoices, not draft orders. | Rule: pull last 5 invoice transactions per customer + item |
| P0 | Simplify chatbot copywriting | Users "don't like reading"; single message, yes/no, no grand-total noise (total lives in PDF). | Rewrite chatbot prompts: "Review price → choose discount → generate QTN/SO". No enrichment beyond what's asked. "Not found = not found." |
| P0 | Decide hybrid UX pattern | Chat alone cannot show rich tables for 20–100 line items. 24 June discussion raised dual interface (70/30 co-work view) — must be an explicit decision, not improvisation. | Product decision: WhatsApp for input, web view or image/table card for pricing review. Do not let this delay step-1. |
| P1 | Define delivery method recommendation UX | Client wants last 5 confirmed delivery methods (courier / Lalamove / self-pickup) to recap with customer. | Add "Historical Delivery Method" section: last 5 with delivery method and charge item |
| P1 | Define customer search behaviour | Customers WhatsApp in with phone only, often no name/company; existing customers can look new. | Search priority: phone/mobile → landline → customer match → branch/contact → show confirmation |
| P1 | Define approval UX — block at DN level, not order level | Client explicit instruction: blocking the order too early loses the chance to collect money/invoice. Two blocks only: minimum price + credit limit. | Approval states: Draft allowed; DN submit blocked if below-floor price OR credit limit exceeded. Quotation still generated pending approval — no hard-stop mid-flow. |
| P1 | Credit approval paths (two distinct flows) | AR-negative means customer is prepaid — approve on bank-in slip. Credit-limit-exceeded is a separate path — approve case-by-case on bank-in slip. | Route to Ivan for approval in both cases; approver sees AR, pending SO/DN amount, credit limit, available balance. |
| P1 | FOC rule | Production overage is free: order 1000, produce 1050 → 50 units are FOC. | Bill billable qty; deduct billable + FOC from stock. FOC line appears on DO. |
| P1 | Custom item handling | Base item (e.g. G5) spawns {Customer Name} G5 variants. | Item retrieval and matching must handle customer-named variants of base items |
| P1 | Item-retrieval fallback | On no exact item match, return the customer's historically ordered items to reduce dead-ends in the flow. | Fallback: show items previously invoiced to that customer |
| P1 | Delivery address history | Customer may want to reuse a previous delivery address; surfacing history removes manual lookup. | Show last 5 confirmed delivery addresses per customer from SO history; user selects or enters new |
| P1 | Default to historical price on line item add | When user adds an item, MAIA should pre-fill with last invoiced price (not standard price) to reduce back-and-forth. | On item add: fetch last invoiced price for that customer + item; pre-fill as default; user can override |
| P1 | Cash / credit term confirmation | After delivery address is set, payment term must be captured before SO is created. | Bot asks: "Cash or credit term?" after delivery address step; term applied to SO |
| P1 | Confirm scope vs CR | Avoid another UAT mismatch. | Mark: must-fix in current scope vs future CR. Especially calculator versioning, extra calculators, raw material planning. |
| P2 | Role-aware information density | Sales users want yes/no flow to get things done; managers/approvers need full context. | Define two response modes: sales (minimal, action-only) vs manager (full AR, pricing, credit, history) |
| P2 | Lead/prospect creation when customer not found | Sales users often only have phone or WhatsApp number — no name. If not found, must not dead-end. | If no customer match by phone: offer "Create as lead/prospect" requiring phone/WhatsApp only; do not block order intake |
| P2 | Create retest script based on real Fixguru flow | Previous test was feature-by-feature, not user-flow-based. | One golden script: WhatsApp order → historical price review → discount select → QTN PDF → delivery method → SO/DN approval check |

## Tech Action Plan

| Priority | Tech action | Lead | Acceptance criteria |
| --- | --- | --- | --- |
| P0 | Historical pricing API/data fix | Afiq / Wei Yon | For each ordered item: date, qty, std price, discount %, net price, invoice ID. Min 5 rows. Source = invoices only. |
| P0 | Discount calculation fix | Afiq | 3%, 5%, 10% discounts calculate correctly against standard unit price |
| P0 | Item-level discount support | Afiq | Same order: item A 3%, item B 10%, item C no discount |
| P0 | Chatbot response formatter | Afiq | User understands all item pricing in one glance; no scrolling through long text |
| P0 | Order creation flow guardrail | Afiq | Bot asks "Use which discount/net price?" before generating QTN/SO |
| P0 | Language bug fix | Afiq | Quick replies stay in English throughout an English conversation; no mid-flow switch to Malay |
| P0 | Hybrid table/web view feasibility | Jermaine / Amirul | Product + tech agree one implementation path; timeboxed spike, must not delay step-1 |
| P1 | Customer search by phone/mobile + landline | Wei Yon | User pastes phone number; MAIA finds correct customer and branches across both mobile and landline fields |
| P1 | Branch/contact sync check | Wei Yon | SO/DN uses selected branch contact, not HQ default |
| P1 | Delivery method as SKU/item | Wei Yon | Delivery charge appears as item line with correct item code/accounting treatment |
| P1 | Historical delivery method retrieval | Wei Yon | Bot/table shows last 5 confirmed delivery methods per customer |
| P1 | Credit limit / AR exposure — block at DN level | Wei Yon | DN submit blocked when DO value exceeds credit limit OR below-floor price; order creation is not blocked. Block is DO-value-triggered (not just outstanding balance flag). Shows AR, pending SO/DN, credit limit, available balance. |
| P1 | AR-negative approval path | Wei Yon | AR-negative (prepaid) customer → approve on bank-in slip receipt. Credit-limit-exceeded → separate case-by-case bank-in approval. Both route to Ivan. |
| P1 | Minimum price approval block | Wei Yon | Quotation draft allowed; DN/SO submit blocked until approval when price below floor |
| P1 | Custom item variant support | Wei Yon | Item lookup handles {Customer Name} G5-style naming; matched against base item and customer history |
| P1 | WhatsApp latency investigation | Wei Yon | Identify why WhatsApp response is slower than Telegram; remediation or escalation |
| P1 | Delivery address history retrieval | Wei Yon | Fetch last 5 confirmed delivery addresses per customer from SO history; surface in bot after delivery method step |
| P1 | Line item price defaulting | Afiq | When item added to order: fetch last invoiced price for that customer+item; pre-fill as default net price; user can override |
| P1 | Payment term capture | Wei Yon | After delivery address step, bot asks cash/credit term; term applied to SO before creation |
| P1 | AutoCount external ID consistency | Wei Yon | Submitted doc displays AutoCount ID, not only MAIA internal ID |
| P2 | Warehouse / shelf configuration review | Wei Yon | Picking list / DN shows shelf/warehouse info correctly |
| P2 | Performance test on real usage | Jermaine | Chatbot/web response remains usable under concurrent order scenarios (30 invoices/day) |

## Milestone Chain (Backward from 3rd UAT)

Plain Text [DONE] Fixguru 2nd UAT Debrief (24 Jun 2026) ↓ [IN PROGRESS] UX Bug Fix Sprint ↓ [UPCOMING] Internal QA ↓ [UPCOMING] Showcase (go/no-go gate) ↓ [LOCKED OUT] 3rd UAT with Fixguru ← only scheduled after Showcase passes

### Milestone 1 — Fixguru 2nd UAT Debrief DONE

Date: 24 Jun 2026

Key conclusion: same blocker since Apr 7 — historical pricing UX is broken. Prompt patching exhausted. Four rounds of same feedback. See [[Meetings/2026-06-24 Fixguru UAT Debrief]] and [[context/learnings]].

### Milestone 2 — UX Bug Fix Sprint IN PROGRESS

Target done by: Wed 2 Jul

Scope: UX of chatbot response only. Not a full feature rebuild — fixing how WeyShen's chatbot surfaces the historical pricing output to the user.

What is being fixed:

Historical pricing formatter — structured table output (not inline text walls)

Discount calculation — price list rate as base, not item price

Item-level discount support — different % per item in same order

Order flow gate — no QTN/SO generated before user confirms price

Language bug — quick replies match session language throughout

Definition of done for this milestone:

WeyShen confirms chatbot returns table format with all 6 columns per item

Discount % computes correctly against price list rate

No Malay quick replies in an English session

Gareth has signed off on the chatbot prompt wording and happy-path flow spec

Product deliverables to support tech:

Pricing table mockup (exact column layout, sort order, row count rule)

Chatbot prompt rewrites (per-step wording, one action per turn)

Happy-path flow spec (each step = one bot message + expected user response + transition)

"Not found" rule: single line, no enrichment

### Milestone 3 — Internal QA UPCOMING

Target date: Fri 4 Jul

Who: Product (Gareth) + Tech (WeyShen / Afiq) run the scenario together.

What happens:

Gareth runs full Fixguru golden scenario end-to-end on the fixed build

Tech observes — any gap or bug logged immediately

Not a formal sign-off — a joint discovery pass before Showcase

Golden scenario:

Customer sends WhatsApp order → MAIA identifies customer by phone → shows last 5 historical invoice prices per item as clean table → user picks discount per item → MAIA generates QTN/SO → PDF preview shown.

Pass gate to proceed to Showcase:

Gareth completes pricing decision without opening AutoCount

No issue from AC-UX checklist (see below) — all five UX checks pass

Any remaining bugs logged, triaged, and either fixed or explicitly deferred

### Milestone 4 — Showcase UPCOMING

Target date: Tue 8 Jul

Who: Product demos to high-level stakeholders (internal leadership + optionally Ivan).

Purpose: Align delivery — confirm the fixed historical pricing flow meets the definition of done before scheduling 3rd UAT with client. This is the go/no-go gate.

What is demoed: Historical pricing flow only. No delivery, credit, PDF template, or warehouse. One flow, proven clean.

Definition of done — Showcase pass criteria:

High-level stakeholders confirm: "this is what we promised Fixguru"

Flow matches the Scope Lock v1 capability: historical pricing lookup, discount selection, QTN/SO generation

No open P0 items from Internal QA still outstanding

If Showcase fails: bug fix sprint continues. 3rd UAT is not scheduled until Showcase passes.

### Milestone 5 — 3rd UAT with Fixguru LOCKED — schedule after Showcase passes

Not scheduled until Milestone 4 passes.

Scope for 3rd UAT: Historical pricing flow first. If that passes, proceed to remaining ACs (AC-02 through AC-06). Do not present all features at once — sequence by dependency.

Sign-off authority: Gareth (pending C6 confirmation — see Open Decisions above).

## AC-UX — Chatbot Expected Output & Acceptance Criteria (Internal QA Gate)

Scope: Historical pricing UX only. Pass = a blue-collar sales user can make the discount decision in one glance, without opening AutoCount. Fail = anything that makes them read, hunt, or wait.

Why this matters (client's exact words, 24 Jun 2026):"People who use MAIA are very simple minded. If head of departments need 5 minutes to digest, their team will take much longer. MAIA must be super direct." — Ivan"I speak many times the same… I don't know how to tell you." — Gareth (Fixguru)"AutoCount is the benchmark — MAIA must be faster and simpler at daily quoting."

### Expected Chatbot Output — Step by Step

This is the exact interaction the chatbot must produce. Any deviation from this sequence or format is a fail.

Step 1 — User sends order

User input (WhatsApp):

Plain Text 011-XXXX XXXX — G3 100, G1 300, PM72 500

Bot response:

Plain Text Customer: [Customer Name] Is this correct? Yes / No

Phone-number-first lookup: search mobile AND landline fields

Confirmation shown before proceeding — no silent auto-match

Step 2 — Bot returns historical pricing per item (customer-specific)

The table is always scoped to this customer + this item. It shows what price Fixguru actually invoiced this specific customer for this specific item in the past — not global pricing, not other customers.

Two rendering paths depending on order size:

Path A — Small order (≤ 3 items): table inline in WhatsApp

Bot sends one message per item directly in chat:

Plain Text [Customer Name] × G3 — Past Invoices Date ¦ Std Price ¦ Disc % ¦ Net Price ¦ Qty ---------¦-----------¦--------¦-----------¦----- 06/2026 ¦ RM 0.10 ¦ 3% ¦ RM 0.097 ¦ 100 05/2026 ¦ RM 0.10 ¦ 10% ¦ RM 0.090 ¦ 1000 03/2026 ¦ RM 0.09 ¦ 5% ¦ RM 0.0855 ¦ 300 01/2026 ¦ RM 0.10 ¦ 0% ¦ RM 0.100 ¦ 200 10/2025 ¦ RM 0.05 ¦ 5% ¦ RM 0.0475 ¦ 500 Apply last discount (3%, RM 0.097)? [Yes] [Custom]

Path B — Large order (> 3 items): chatbot sends FE link

WhatsApp chat alone cannot hold 5+ item tables without becoming a wall of text. Bot sends a link to the MAIA web frontend where the full pricing table is displayed cleanly for all items side by side:

Plain Text [Customer Name] — 5 items to price. View pricing history here: [link] Confirm discounts in the app, then reply "Done" to generate QTN.

User opens the link → sees full table per item in the FE → confirms discounts → replies "Done" in WhatsApp → bot generates QTN/SO.

Why this split (from 24 Jun debrief): Ivan proposed the dual interface (70/30 co-work view) specifically because WhatsApp cannot display 20–100 line item tables legibly. The FE link path is not a workaround — it is the intended design for larger orders. Decision: chat for input and short responses, FE for rich tabular data.

Threshold to lock before Internal QA: Is the cutoff 3 items or 5 items? Must be confirmed with tech (WeiShen) before Fri 4 Jul.

How the quick reply works (Path A): Bot reads the most recent invoice row for this customer × item, extracts the discount % and net price, and offers to apply that specific deal again. User answers yes or enters a different figure. No abstract % buckets — the offer is always grounded in actual history with this customer.

Non-negotiable format rules (from 24 Jun debrief):

| Rule | Requirement | Source |
| --- | --- | --- |
| Columns | Date, Std Price, Disc %, Net Price, Qty — exactly these five | Ivan 24 Jun |
| Row count | Min 5 rows per item — "3 is too few" | Ivan 24 Jun |
| Sort | Most recent first | Implied — date signals price drift |
| Source | Confirmed invoices only — never draft SOs | Ivan 24 Jun |
| Grand total | NOT shown in chatbot — total is PDF-only | Ivan 24 Jun |
| Format | Table, not paragraphs, not bullet points | Ivan 24 Jun |
| Per-item message | Each item = its own message block — never combine two items in one wall of text | UX principle |
| Quick replies | Discount options as tappable buttons: [3%] [5%] [10%] [Custom] | One-glance requirement |

Step 3 — User picks discount per item

User taps: 3%

Bot response (single line, no enrichment):

Plain Text G3: RM 0.097 × 100 = RM 9.70 ✓

Repeat Steps 2–3 for each item. After all items confirmed:

Step 4 — Bot generates document

Plain Text Quotation created: QTN-XXXX Customer: [Name] Items: G3 × 100, G1 × 300, PM72 × 500 [View PDF]

No additional commentary. No summary of discounts. No totals in chatbot.

Step 5 — "Not Found" response (if item has no invoice history)

Plain Text No pricing history for [item]. Use standard price RM X.XX? Yes / No

One line. No explanation. No alternatives listed unprompted. "Not found = not found." — Ivan

### Acceptance Criteria Checklist (Internal QA, Fri 4 Jul)

| # | Check | Pass condition | Fail example |
| --- | --- | --- | --- |
| UX-01 | Output format | Table, not prose or bullets | Long paragraph per item |
| UX-02 | Columns present | Date, Std Price, Disc %, Net Price, Qty — all five | Missing Date or Net Price |
| UX-03 | Row count | Min 5 invoice-sourced rows | Only 2–3 rows shown |
| UX-04 | Source | Confirmed invoices only | Draft SO rows included |
| UX-05 | Grand total | Not shown in chatbot | Total embedded in message |
| UX-06 | Single message per item | All rows for one item in one message | Rows split across messages |
| UX-07 | Quick replies | Discount options as tappable buttons | User must type discount manually |
| UX-08 | One question per turn | Bot asks ONE thing after table | Bot asks discount + delivery in same message |
| UX-09 | No premature doc | QTN/SO only after user confirms price | QTN generated before discount chosen |
| UX-10 | Not found = one line | Single-line response, no enrichment | Multi-line explanation when item missing |
| UX-11 | Language | Zero Malay in English session, including quick replies | Quick reply labels switch to Malay |
| UX-12 | Speed feel | Gareth: "faster than opening AutoCount" | Feels slower or more effort than AutoCount |

Verdict options per check: Pass / Fail / Conditional (note exact message that failed)

Overall gate: All 12 must pass before proceeding to Showcase. Any Fail = fix and retest before Tue 8 Jul.

## Lead-Review Recommendation (P0 Recovery Scope)

Historical pricing + discount decision UX (invoice-sourced, min 5 rows, one glance)

Correct item-level discount calculation

One-glance chatbot/table output + language bug

Phone/customer search (mobile + landline)

Delivery method as item/SKU

Credit/minimum price approval visibility (block at DN, not order; two paths)

Everything else is secondary until Fixguru confirms the first sales pricing flow is finally usable.