GST Fine Foods Phase 1 — Backward Plan to Go-Live

End goal: Core MAIA live + client trained + SAP B1 integration verified
Created: 2026-06-22
Channel: WhatsApp (GST handles WABA/Meta setup themselves; MAIA provides setup guide) + Telegram as fallback
Scope: Core MAIA — RFQ intake + product matching, Sales Order creation, payment slip approval routing, credit limit checks, SAP B1 integration (Service Layer API), Crystal Reports-aligned document output, daily digests.
Model: Same pattern as [[Macrofood Phase 1 Timeline]] and [[Dalson Phase 1 Timeline]] — lock all deps, deploy instance, SAP integration, internal test + live fix, UAT, go-live, training.

## Milestone Map

NOW ─── M0 Deps ─── M1 Deploy + Chatbot ─── M2 SAP Integration ─── M3 Internal Test ─── M4 UAT ─── M5 Go-Live ─── M6 Training Now Now–TBC TBC TBC TBC TBC TBC TBC Jun 22

| Phase | Date | Who | Goal |
| --- | --- | --- | --- |
| M0 Deps + Kickoff | Now — TBC | Gareth + GST | Lock all remaining deps; SAP UAT license; schedule AWS + OpenAI setup meeting |
| M1 AWS Deploy + Telegram/WA | TBC | Dev | MAIA instance live on GST AWS; chatbot connected and smoke-tested |
| M2 SAP B1 Integration + Data Seed | TBC | Dev + PM | SAP Service Layer sync working; master data seeded; Crystal Reports PDF config |
| M3 Internal Test + Live Fix | TBC | Gareth + Dev | Full GST workflow run-through live; fix on spot; all scope items green |
| M4 UAT | TBC | PM + GST | Client runs UAT on spot; PM triages same session |
| M5 Go-Live | TBC | PM + GST | Punch list cleared; live confirmed; sign-off obtained |
| M6 Training | TBC | PM + GST team | Full team trained on live system |

## ⚠️ Critical Path — SAP UAT License + Integration (M0 → M2 → M3)

SAP B1 integration via Service Layer API is a hard go-live blocker. Two gates control the critical path:

SAP UAT license from GST's vendor — expected Wed 25 Jun. No UAT environment = no integration build.

AWS + OpenAI setup meeting — Gareth to schedule with GST; gates instance deploy (M1).

SAP UAT license received (Wed 25 Jun) → integration build starts → data seed → internal test → UAT → go-live.

If SAP vendor slips past Wed 25 Jun, all downstream milestones shift — escalate immediately.

WABA / WhatsApp: GST handles their own Meta + WABA account setup. MAIA provides the [[Guide] Channel & Infrastructure Setup Guide Copy] to GST. Not a MAIA-controlled blocker. Telegram is the fallback channel if WhatsApp is not ready at go-live.

## M0 — Dependencies + Kickoff (Now — TBC)

Who: Gareth + GST
Goal: Confirm every input M1 and M2 depend on. Nothing downstream moves until these land.

### Already Done ✅

SAP B1 access received

VPN network access received

Remote desktop access received

Core MAIA setup complete

WABA setup guide prepared for GST — [[Guide] Channel & Infrastructure Setup Guide Copy]

### Pending — Critical

| Dependency | Blocks | Status | Expected |
| --- | --- | --- | --- |
| SAP vendor provides UAT license access to MAIA team | SAP integration build (M2) | 🟡 Pending | Wed 25 Jun 2026 |
| Schedule meeting with GST to set up AWS account access | Instance deploy (M1) | ⬜ Gareth to schedule | TBC |
| Schedule meeting with GST to set up OpenAI API key | Chatbot (M1) | ⬜ Gareth to schedule | TBC |

### Pending — Client Deliverables

| Dependency | Blocks | Status |
| --- | --- | --- |
| GST company user list (name, role, contact, branch) | User seed (M2) | ⬜ |
| PDF samples of gold-standard Crystal Reports outputs (Quotation, SO, Invoice, DO) | PDF template config (M2) | ⬜ |
| Item master excerpt from SAP (anonymised) | SAP mapping (M2) | ⬜ |
| Customer-specific naming / cross-reference sheet | Product matching config (M2) | ⬜ |
| Confirm stock availability source — SAP live vs daily Excel extract | Core flow config (M2) | ⬜ |
| Confirm which branch goes live first (Penang or KL) | Scope lock | ⬜ |
| WhatsApp Business number + Meta Business Account (GST-managed) | WhatsApp channel (M1) | 🟡 GST handles — MAIA provides guide |

## M1 — AWS Deploy + Chatbot Setup (TBC)

Who: Dev (pending M0 AWS + OpenAI setup meeting)
Goal: MAIA instance live on GST's AWS; chatbot connected and responding.

Gareth schedules meeting with GST to set up AWS account + OpenAI API key — gates this milestone

Deploy MAIA instance on GST's AWS

Set up chatbot — WhatsApp preferred; Telegram fallback if WhatsApp not ready at go-live

Connect chatbot to MAIA instance

Smoke-test basic message flow: send message → MAIA responds

Confirm instance + chatbot stable before M2 begins

WhatsApp/WABA: GST manages their own setup. Do not block deploy on it — use Telegram as fallback if needed.

## M2 — SAP B1 Integration + Data Seed (TBC)

Who: Dev + PM
Goal: Full SAP Service Layer sync working. All read + write flows verified before internal test. Gates on SAP UAT license received.

SAP vendor delivers UAT license access — expected Wed 25 Jun (hard gate)

Confirm integration approach with Azib: SAP B1 Service Layer API (RESTful) — confirmed in vendor meeting

Confirm custom UDF fields from GST's SAP — need list of customized fields outside MAIA standard; Service Layer cannot support custom UDFs natively; new endpoints required

Build + verify SAP READ:

Item master sync (species, cut, weight, pack format, price list per customer)

Customer master sync

Inventory / stock level sync (confirm: live SAP vs daily extract vs hybrid)

Customer-specific price lists

Build + verify SAP WRITE:

Sales Order push to SAP B1

Invoice push to SAP B1

Delivery Order push to SAP B1

Confirm SAP development/UAT environment available (mirror of production data) — as agreed in SAP vendor meeting

Configure Crystal Reports-aligned PDF templates — Quotation, SO, Invoice, DO (from client samples)

Seed GST company users into MAIA

Seed customer + item master data from SAP exports

Confirm SAP document numbering structure (per branch or centralised; annual reset?) — affects SO/Invoice number series

All writes must be tested on the UAT/development environment first — never write to GST's live SAP production until go-live.

## M3 — Internal Test + Live Dev-Fix Session (TBC)

Who: Gareth + Dev
Duration: ~2–3 hours (one session)
Format: PM runs every scope item live on GST env; dev fixes on the spot. Anything not fixable in session → explicit defer decision logged. Nothing goes to client UAT with a known failure.

### Core workflow checklist — run live

| # | Item | FE | Chatbot | SAP | Status |
| --- | --- | --- | --- | --- | --- |
| 1 | Item master synced from SAP (species, cut, weight, price list) | — | — | ☐ | ⬜ |
| 2 | Customer master synced from SAP | — | — | ☐ | ⬜ |
| 3 | Stock availability sync (SAP live / daily extract — per agreed source) | — | — | ☐ | ⬜ |
| 4 | Upload RFQ Excel → MAIA reads and extracts line items (IDP) | ☐ | ☐ | — | ⬜ |
| 5 | Product matching — customer wording mapped to SAP item master; closest match surfaced | ☐ | ☐ | — | ⬜ |
| 6 | Substitution suggestion when exact match unavailable | ☐ | ☐ | — | ⬜ |
| 7 | Quotation output — match results returned as text message (not Excel) | ☐ | ☐ | — | ⬜ |
| 8 | Standard Sales Order created in MAIA + pushed to SAP B1 | ☐ | ☐ | ☐ | ⬜ |
| 9 | Credit limit check on SO — breach triggers finance approval routing | ☐ | ☐ | — | ⬜ |
| 10 | Payment slip forwarded to finance via chatbot → approval before close-out | ☐ | ☐ | — | ⬜ |
| 11 | Invoice generated + pushed to SAP B1 | ☐ | — | ☐ | ⬜ |
| 12 | Delivery Order generated + stored | ☐ | — | ☐ | ⬜ |
| 13 | Crystal Reports-aligned PDF renders correctly (SO, Invoice, DO) | ☐ | — | — | ⬜ |
| 14 | Daily digest — unclosed SOs, outstanding payment slips, flagged stock | ☐ | — | — | ⬜ |

End of session: green items locked; deferred items explicitly logged with decision

### Items NOT to test in M3 (out of scope — do not creep in)

CPRN (Customer Purchase Request Notes) — Phase 2

RFQ deep matching logic (Phase 2 Customisation 1)

Aging + clearance reminders — Phase 2

SOA (Statement of Account) generation — Phase 2, subject to SAP feasibility

KL branch rollout — Phase 1 starts with confirmed branch only (Penang or KL TBC)

## M4 — UAT — Client Session (TBC)

Who: PM + GST UAT users (Joey Ong — Sales; Soo Chin — Operations; Tim — Operations Manager; Finance PIC)
Format: PM briefs scope → GST team runs UAT on the spot → PM triages same session.

Brief client: what's in scope vs deferred; what's new vs prior discussions

GST team runs core workflow live on MAIA env:

Upload RFQ Excel → product matching results returned

Standard SO creation via WhatsApp

Credit limit scenario — breach → approval routed to finance

Payment slip submission → finance approval

Invoice + DO generated and pushed to SAP

Crystal Reports PDF layout verified against GST gold-standard samples

Daily digest view

PM on standby; log issues and triage same session

Minor issues: fix same day or by go-live date

Sign-off criteria agreed before session starts

Collect UAT results → conditional sign-off or punch list

## M5 — Go-Live (TBC)

Who: PM + GST
Goal: UAT punch list cleared → confirm live → sign-off.

All UAT punch list items resolved

Instance stable (no regressions from UAT fixes)

Chatbot live on production — GST team using it

All GST users confirmed active in MAIA (correct branch assignment)

SAP sync live on production (not UAT environment)

Crystal Reports PDF templates verified on production

Sign-off obtained — payment milestone triggered

Go-live confirmed — GST team begins live operations

## M6 — Training (TBC)

Who: PM + full GST team (sales coordinators, finance, logistics, management)
Format: Full structured session; cover end-to-end live workflow.

Prep training material (slides / walkthrough based on UAT scenarios)

Demo environment with clean data ready

Train: RFQ upload → product matching → quotation output

Train: Standard SO creation via WhatsApp

Train: Credit limit check — what happens when breach detected

Train: Payment slip submission → finance approval flow

Train: Invoice + DO generation

Train: Daily digest — what it shows, how to act on it

Train: Document retrieval (SO, Invoice, DO by customer / date / order number)

Cover: how to flag issues post go-live; escalation contact

WhatsApp path: confirm WABA live or confirm Telegram is active go-live channel

## Scope at Go-Live (What GST Gets)

| Feature | Status |
| --- | --- |
| RFQ Excel intake + line item extraction (IDP) | ✅ Phase 1 |
| Product matching — SAP item master lookup, match surfacing | ✅ Phase 1 (basic) |
| Standard Sales Order creation via WhatsApp | ✅ Phase 1 |
| Pre-order checks: stock, credit limit, customer pricing | ✅ Phase 1 |
| Finance approval routing — payment slips + credit exceptions | ✅ Phase 1 |
| SAP B1 integration — read (items, customers, stock, pricing) | ✅ Phase 1 |
| SAP B1 integration — write (SO, Invoice, DO push) | ✅ Phase 1 |
| Crystal Reports-aligned document output (SO, Invoice, DO) | ✅ Phase 1 |
| Daily digests — unclosed SOs, payment slips, flagged stock | ✅ Phase 1 |

## NOT in Phase 1 Scope (Do Not Creep In)

CPRN (Customer Purchase Request Notes / blanket orders) — Phase 2

Deep RFQ matching logic (customer cross-reference, substitution rules engine) — Phase 2 Customisation 1

Aging + clearance reminders (near-expiry stock alerts) — Phase 2

SOA (Statement of Account) generation — Phase 2, subject to SAP feasibility

KL branch rollout — Phase 1 = one branch only (confirm which branch)

Langkawi branch — post Phase 1

MRP / manufacturing process integration — not in SOW

Stock transformation (whole fish → cut) — to confirm if Phase 1 or Phase 2 (raised in SAP vendor meeting)

## Key Contacts

| Role | Name | Contact |
| --- | --- | --- |
| GST Sales PIC | Joey Ong | — |
| GST Operations | Soo Chin (boss) | chin@gstgroup.com.my |
| GST Operations Manager | Tim | timwong@gstgroup.com.my |
| GST Finance | Miss Lee (Penang) | finance@gstgroup.com.my |
| GST CEO Wife | Teoh Le Ying | teohly@gstgroup.com.my |
| SAP Vendor (integration PIC) | Azib Iqbal | azibiqbal01@gmail.com |
| Mindhive dev (SAP integration) | Jermaine | jermaine@mindhive.asia |

## Milestone Dates

| # | Milestone | Date |
| --- | --- | --- |
| 1 | Signed Date | TBC |
| 2 | Payment Date (upfront) | TBC |
| 3 | Kickoff Date | TBC |
| 4 | Requirements Lock Date | TBC |
| 5 | SAP UAT License Received | Expected Wed 25 Jun 2026 |
| 6 | Instance Deploy Date | TBC |
| 7 | SAP Integration Complete | TBC |
| 8 | Internal Test Date | TBC |
| 9 | UAT Date | TBC |
| 10 | Go-Live Date | TBC |
| 11 | Training Date | TBC |
| 12 | Customisations Date | TBC |

## See Also

[[SOW for MAIA GST Fine Foods]]

[[GST Fine Foods — Requirement Gathering Questionnaire]]

[[Requirement Gathering Output - GST Fine Foods - 2026-05]]

[[GST SAP Vendor × Mindhive — Meeting Notes]]

[[GST Meeting Transcripts]]

[[[Guide] Channel & Infrastructure Setup Guide Copy]]

[[Macrofood Phase 1 Timeline]]

[[Dalson Phase 1 Timeline]]

|（注：部分内容可能由 AI 生成）