## Task management
Task name | Description | Project | Phase | Status | Priority | Owner | Created on | Deadline | Time left | Attachments | Parent items | Parent items 2 | Parent items 3 | Documents | Remarks | Clients | Delayed timeline
ERPNext Doctype ID Sanitization |  | MAIA | Phase 01 | 0. Not Started |  | Ivan | 2026-04-19 16:00
|  |  | Phase 01 | 0. Not Started |  |  | 2026-04-19 16:00
Item Type Interpretation |  | MAIA | Phase 01 | 0. Not Started |  | Ivan | 2026-04-19 16:00 | [6 empty] | Brief
Notification and ToDos Grooming = |  | MAIA | Phase 01 | 0. Not Started |  | Ivan | 2026-04-19 16:00 | 2026-04-29 16:00
Formulate a metric for sprint completion along with some visibility board for our pipeline | Here we basically want to create a dashboard using which we will get a visibility of our pipeline along with any any feedbacks or client requirements or feedbacks that might need to be addressed | General Process Improvements | MVP | 9. Backlog |  | Sadman,Ivan | 2025-10-13 16:00
Google Review: Bug Reported |  | Google Review | Phase 01 | 3. Completed |  | Brendan | 2025-10-13 16:00 | 2025-10-15 16:00
Dashboard Refresh |  | Google Review | Phase 01 | 3. Completed |  | Brendan | 2025-10-13 16:00 | 2025-10-12 16:00 |  |  |  | Google Review: Bug Reported
Deleted Reviews still remains in FE |  | Google Review | Phase 01 | 3. Completed |  | Brendan | 2025-10-13 16:00 | 2025-10-22 16:00 |  |  |  | Google Review: Bug Reported
1A. Order Intake + Order Creation in Mforce |  | MAIA: Faber Castell | Phase 01 | 3. Completed |  |  | 2026-04-05 16:00 | 2026-04-08 16:00
Set up video onboarding for newcomers |  | General Process Improvements | MVP | 9. Backlog |  |  | 2025-10-14 16:00
Get the query to understand if the the issue is resurfacing or not |  | Google Review | Phase 01 | 3. Completed |  | Sadman,Ivan,Brendan | 2025-10-23 16:00 | 2025-10-27 16:00 |  |  |  | Google Review: Bug Reported |  |  | Checked 2 times... the problem has not surfaced any more
Create the Template the test cases and qa process |  | General Process Improvements | MVP | 9. Backlog |  | Sadman | 2025-10-30 16:00
UAT Brief |  | MAIA: Holsen | Phase 01 | 3. Completed |  | Gareth Ng | 2026-03-17 16:00 | 2026-03-17 16:00
UAT Brief(new) |  | MAIA: Fixguru | Phase 01 | 3. Completed |  | Gareth Ng | 2026-04-05 16:00 | 2026-04-05 16:00
Timeline review and UAT Brief |  | MAIA: Ultimax | Phase 01 | 3. Completed |  | Jun Yan Lim | 2026-03-29 16:00 | 2026-03-30 16:00
MAIA Training B2B |  | MAIA: Lean Giap | Phase 01 | 3. Completed |  | Brendan | 2026-03-17 16:00 | 2026-03-17 16:00 |  |  |  | Original Phase 1 Dev Timeline
SQL integration dev |  | MAIA: Mackessen | Phase 01 | 3. Completed |  | Brendan | 2026-03-19 16:00 | 2026-04-05 16:00
UAT - Retest Cycle |  | Pelangi Voucher | Phase 01 | 1.b. Planned |  |  | 2026-04-19 16:00 | 2026-04-22 16:00
MAIA Training B2B |  | MAIA: Farmshop | Phase 01 | 3. Completed |  | Brendan | 2026-03-10 16:00 | 2026-03-10 16:00 |  |  |  | B2B timeline
Briefing B2B |  | MAIA: Farmshop | Phase 01 | 3. Completed |  | Brendan | 2026-03-11 16:00 | 2026-03-11 16:00 |  |  |  | B2B timeline
Small and major Fixes B2B |  | MAIA: Farmshop | Phase 01 | 3. Completed |  | Brendan | 2026-03-12 16:00 | 2026-03-17 16:00 |  |  |  | B2B timeline
Prod ready B2B |  | MAIA: Farmshop | Phase 01 | 3. Completed |  | Brendan | 2026-03-18 16:00 | 2026-03-18 16:00 |  |  |  | B2B timeline
On site Guidance Sales agent + Logistics B2B |  | MAIA: Farmshop | Phase 01 | 3. Completed |  | Brendan | 2026-03-24 16:00 | 2026-03-24 16:00 |  |  |  | B2B timeline
On site Guidance logistics + Driver B2B |  | MAIA: Farmshop | Phase 01 | 3. Completed |  | Brendan | 2026-03-26 16:00 | 2026-03-26 16:00 |  |  |  | B2B timeline
B2B Sign off |  | MAIA: Farmshop | Phase 01 | 3. Completed |  | Brendan | 2026-03-26 16:00 | 2026-03-30 16:00 |  |  |  | B2B timeline
B2C Test plan Finalized |  | MAIA: Farmshop | Phase 01 | 3. Completed |  | Brendan | 2026-03-16 16:00 | 2026-03-16 16:00 |  |  |  | Origiinal b2c timeline
Internal QA B2C |  | MAIA: Farmshop | Phase 01 | 3. Completed |  | Brendan | 2026-03-17 16:00 | 2026-03-22 16:00 |  |  |  | Origiinal b2c timeline
B2C Proof Sent to Farmshop |  | MAIA: Farmshop | Phase 01 | 3. Completed |  | Brendan | 2026-03-24 16:00 | 2026-03-24 16:00 |  |  |  | Origiinal b2c timeline
Small & Major fixes |  | MAIA: Farmshop | Phase 01 | 3. Completed |  | Brendan | 2026-03-23 16:00 | 2026-03-25 16:00 |  |  |  | Origiinal b2c timeline
B2C UAT Brief |  | MAIA: Farmshop | Phase 01 | 3. Completed |  | Brendan | 2026-03-26 16:00 | 2026-03-26 16:00 |  |  |  | Origiinal b2c timeline
B2C UAT |  | MAIA: Farmshop | Phase 01 | 3. Completed |  | Brendan | 2026-03-29 16:00 | 2026-03-31 16:00 |  |  |  | Origiinal b2c timeline
B2C last fixes |  | MAIA: Farmshop | Phase 01 | 3. Completed |  | Brendan | 2026-03-30 16:00 | 2026-04-01 16:00 |  |  |  | Origiinal b2c timeline
B2C Sign off |  | MAIA: Farmshop | Phase 01 | 3. Completed |  | Brendan | 2026-04-02 16:00 | 2026-04-02 16:00 |  |  |  | Origiinal b2c timeline
B2B Month Long Hypercare |  | MAIA: Farmshop | Phase 01 | 3. Completed |  | Brendan | 2026-03-29 16:00 | 2026-04-29 16:00 |  |  |  | B2B timeline
Eric Testing |  | MAIA: Lean Giap | Phase 01 | 3. Completed |  | Brendan | 2026-03-19 16:00 | 2026-03-23 16:00 |  |  |  | Original Phase 1 Dev Timeline
Feedback Receive from Eric |  | MAIA: Lean Giap | Phase 01 | 3. Completed |  | Brendan | 2026-03-23 16:00 | 2026-03-23 16:00 |  |  |  | Original Phase 1 Dev Timeline
Internal discussion on Feedback |  | MAIA: Lean Giap | Phase 01 | 3. Completed |  | Brendan | 2026-03-23 16:00 | 2026-03-24 16:00 |  |  |  | Original Phase 1 Dev Timeline
Brief Azib on Epicor changes |  | MAIA: Lean Giap | Phase 01 | 3. Completed |  | Brendan | 2026-03-25 16:00 | 2026-03-25 16:00 |  |  |  | Original Phase 1 Dev Timeline
Azib dev |  | MAIA: Lean Giap | Phase 01 | 2. In Progress |  | Brendan | 2026-03-26 16:00 | 2026-03-29 16:00 |  |  |  | Original Phase 1 Dev Timeline |  |  |  |  | 2026-03-31 16:00
internal testing |  | MAIA: Lean Giap | Phase 01 | 0. Not Started |  | Brendan | 2026-03-29 16:00 | 2026-03-31 16:00 |  |  |  | Original Phase 1 Dev Timeline
Alignment with Eric on changes |  | MAIA: Lean Giap | Phase 01 | 3. Completed |  | Brendan | 2026-03-29 16:00 | 2026-03-29 16:00 |  |  |  | Original Phase 1 Dev Timeline
Eric UAT |  | MAIA: Lean Giap | Phase 01 | 0. Not Started |  | Brendan | 2026-03-31 16:00 | 2026-04-01 16:00 |  |  |  | Original Phase 1 Dev Timeline
Prod Ready |  | MAIA: Lean Giap | Phase 01 | 0. Not Started |  | Brendan | 2026-04-02 16:00 | 2026-04-02 16:00 |  |  |  | Original Phase 1 Dev Timeline
V1 Release |  | MAIA: Lean Giap | Phase 02 | 0. Not Started |  | Brendan | 2026-04-09 16:00 | 2026-04-09 16:00 |  |  |  | ARAP Timeline
V1 Brief with Eric |  | MAIA: Lean Giap | Phase 02 | 0. Not Started |  | Brendan | 2026-04-09 16:00 | 2026-04-09 16:00 |  |  |  | ARAP Timeline
v1 Feedback |  | MAIA: Lean Giap | Phase 02 | 0. Not Started |  | Brendan | 2026-04-14 16:00 | 2026-04-14 16:00 |  |  |  | ARAP Timeline
Brief Tech on Feedback changes |  | MAIA: Lean Giap | Phase 02 | 0. Not Started |  | Brendan | 2026-04-15 16:00 | 2026-04-15 16:00 |  |  |  | ARAP Timeline
Feedback Dev |  | MAIA: Lean Giap | Phase 02 | 0. Not Started |  | Brendan | 2026-04-16 16:00 | 2026-04-19 16:00 |  |  |  | ARAP Timeline
Internal UAT on Feedback changes |  | MAIA: Lean Giap | Phase 02 | 0. Not Started |  | Brendan | 2026-04-16 16:00 | 2026-04-19 16:00 |  |  |  | ARAP Timeline
V2 Release |  | MAIA: Lean Giap | Phase 02 | 0. Not Started |  | Brendan | 2026-04-20 16:00 | 2026-04-20 16:00 |  |  |  | ARAP Timeline
V2 Brief with Eric |  | MAIA: Lean Giap | Phase 02 | 0. Not Started |  | Brendan | 2026-04-21 16:00 | 2026-04-21 16:00 |  |  |  | ARAP Timeline
Sign off ARAP |  | MAIA: Lean Giap | Phase 02 | 0. Not Started |  | Brendan | 2026-04-09 16:00 | 2026-04-23 16:00 |  |  |  | ARAP Timeline
Set up meta account |  | MAIA: Mackessen | Phase 01 | 3. Completed |  | Brendan | 2026-03-17 16:00 | 2026-03-17 16:00
Setup Mackessen Intances |  | MAIA: Mackessen | Phase 01 | 3. Completed |  | Brendan | 2026-03-12 16:00 | 2026-03-12 16:00
Manually Add data for Mackessen to test |  | MAIA: Mackessen | Phase 01 | 3. Completed |  | Brendan | 2026-04-02 16:00 | 2026-04-02 16:00
UAT briefing with Mackessen |  | MAIA: Mackessen | Phase 01 | 0. Not Started |  | Brendan | 2026-04-07 16:00 | 2026-04-07 16:00
Client UAT |  | MAIA: Mackessen | Phase 01 | 2. In Progress |  | Brendan | 2026-04-12 16:00 | 2026-04-29 16:00
Product Ready |  | MAIA: Mackessen | Phase 01 | 0. Not Started |  | Brendan | 2026-04-15 16:00 | 2026-03-15 16:00
Phase 1 Sign off |  | MAIA: Mackessen | Phase 01 | 0. Not Started |  | Brendan | 2026-05-04 16:00 | 2026-05-04 16:00
Bug fixes |  | MAIA: Mackessen | Phase 01 | 3. Completed |  | Brendan | 2026-04-07 16:00 | 2026-04-09 16:00
Bug fixes - Bulk Stock Entry/Recon |  | MAIA: Ultimax | Phase 01 | 2. In Progress |  | Jun Yan Lim | 2026-03-29 16:00 | 2026-03-30 16:00
Product Ready |  | MAIA: Ultimax | Phase 01 | 2a.Blocked |  | Jun Yan Lim | 2026-04-15 16:00 | 2026-04-15 16:00
UAT Period |  | MAIA: Ultimax | Phase 01 | 2.c. Delayed |  | Jun Yan Lim | 2026-04-07 16:00 | 2026-04-12 16:00
Meta Account Setup |  | MAIA: Ultimax | Phase 01 | 2.c. Delayed |  | Jun Yan Lim | 2026-04-13 16:00 | 2026-04-13 16:00
Ship Base MAIA |  | MAIA: Ultimax | Phase 01 | 2.c. Delayed |  | Jun Yan Lim | 2026-04-16 16:00 | 2026-04-16 16:00
UAT Testing |  | MAIA: Holsen | Phase 01 | 2.c. Delayed |  | Gareth Ng | 2026-03-17 16:00 | 2026-04-23 16:00
UAT Follow Up |  | MAIA: Holsen | Phase 01 | 3. Completed |  | Gareth Ng | 2026-03-30 16:00 | 2026-03-30 16:00
Meta Account Setup |  | MAIA: Holsen | Meta WABA | 2. In Progress |  | Gareth Ng | 2026-04-14 16:00 | 2026-04-23 16:00
Poison Signing Order Form (Completed) |  | MAIA: Holsen | Phase 01 | 2. In Progress |  | Gareth Ng,Bushra Mualla | 2026-04-20 16:00 | 2026-04-20 16:00
Sales User See Only Own Customer |  | MAIA: Holsen | Phase 01 | 3. Completed |  | Gareth Ng | 2026-03-30 16:00 | 2026-04-02 16:00
UAT Bug Fixes |  | MAIA: Holsen | Phase 01 | 2. In Progress |  | Gareth Ng | 2026-03-30 16:00 | 2026-04-21 16:00
UAT Bug fixes |  | MAIA: Ultimax | Phase 01 | 2a.Blocked |  | Jun Yan Lim | 2026-04-08 16:00 | 2026-04-14 16:00
Internal Testing |  | MAIA: Mackessen | Phase 01 | 3. Completed |  | Brendan | 2026-04-05 16:00 | 2026-04-06 16:00
Custom Calculator |  | MAIA: Fixguru | Phase 02 | 2. In Progress |  | Gareth Ng | 2026-03-29 16:00 | 2026-04-22 16:00
Einvoice Integration |  | MAIA: Fixguru | Phase 01 | 2. In Progress |  | Gareth Ng | 2026-03-17 16:00 | 2026-04-21 16:00
UAT Form |  | MAIA: Fixguru | Phase 01 | 3. Completed |  | Gareth Ng | 2026-03-29 16:00 | 2026-03-29 16:00
Phase 1 Sign off |  | MAIA: Holsen | Phase 01 | 0. Not Started |  | Gareth Ng | 2026-04-28 16:00 | 2026-04-28 16:00
UAT Bug Fixes |  | MAIA: Fixguru | Phase 01 | 2. In Progress |  | Gareth Ng | 2026-04-08 16:00 | 2026-04-16 16:00
Product Ready |  | MAIA: Fixguru | Phase 01 | 0. Not Started |  | Gareth Ng | 2026-04-14 16:00 | 2026-05-03 16:00
Phase 1 Sign Off |  | MAIA: Fixguru | Phase 01 | 0. Not Started |  | Gareth Ng | 2026-05-03 16:00 | 2026-05-03 16:00
UAT Testing |  | MAIA: Fixguru | Phase 01 | 0. Not Started |  | Gareth Ng | 2026-04-22 16:00 | 2026-04-29 16:00
Migrate bastion server to Leangiap |  | MAIA: Lean Giap | MVP | 9. Backlog |  |  | 2026-03-29 16:00
Align with Eric on Monday 30th sync direction |  | MAIA: Lean Giap | MVP | 3. Completed |  |  | 2026-03-29 16:00
updated BE dev time |  | MAIA: Lean Giap | Phase 01 | 9. Backlog |  | Brendan | 2026-03-30 16:00 | 2026-04-01 16:00 |  |  |  | Updated Phase 1 Dev Timeline
updated internal uat |  | MAIA: Lean Giap | Phase 01 | 9. Backlog |  | Brendan | 2026-04-01 16:00 | 2026-04-06 16:00 |  |  |  | Updated Phase 1 Dev Timeline
Eric uat updated |  | MAIA: Lean Giap | Phase 01 | 9. Backlog |  | Brendan | 2026-04-07 16:00 | 2026-04-07 16:00 |  |  |  | Updated Phase 1 Dev Timeline
Updated FE Dev time |  | MAIA: Lean Giap | Phase 01 | 9. Backlog |  | Brendan | 2026-03-31 16:00 | 2026-03-31 16:00 |  |  |  | Updated Phase 1 Dev Timeline
Prod ready updated |  | MAIA: Lean Giap | Phase 01 | 9. Backlog |  | Brendan | 2026-04-09 16:00 | 2026-04-09 16:00 |  |  |  | Updated Phase 1 Dev Timeline
V1 Dev BE |  | MAIA: Lean Giap | Phase 02 | 2. In Progress |  | Brendan | 2026-03-30 16:00 | 2026-04-02 16:00 |  |  |  | ARAP Timeline
v1 dev FE |  | MAIA: Lean Giap | Phase 02 | 2. In Progress |  | Brendan | 2026-04-01 16:00 | 2026-04-06 16:00 |  |  |  | ARAP Timeline
v1 dev chatbot |  | MAIA: Lean Giap | Phase 02 | 2. In Progress |  | Brendan | 2026-04-01 16:00 | 2026-04-01 16:00 |  |  |  | ARAP Timeline
internal testing |  | MAIA: Lean Giap | Phase 02 | 0. Not Started |  | Brendan | 2026-04-06 16:00 | 2026-04-08 16:00 |  |  |  | ARAP Timeline
extraction testing (bs) |  | MAIA: Lean Giap | Phase 02 | 2. In Progress |  | Brendan | 2026-04-01 16:00 | 2026-04-02 16:00 |  |  |  | ARAP Timeline
AP documentation |  | MAIA: Lean Giap | Phase 02 | 2. In Progress |  | Brendan | 2026-03-31 16:00 | 2026-03-31 16:00 |  |  |  | ARAP Timeline
Original Phase 1 Dev Timeline |  | MAIA: Lean Giap | Phase 01 |  |  | Brendan
ARAP Prod Ready |  | MAIA: Lean Giap | Phase 02 | 0. Not Started |  | Brendan
Updated Phase 1 Dev Timeline |  | MAIA: Lean Giap | Phase 01 | 9. Backlog
ARAP Timeline |  | MAIA: Lean Giap | Phase 02 | 9. Backlog |  |  | 2026-03-30 16:00
1A.1 faber instance deployed |  | MAIA: Faber Castell | Phase 01 | 9. Backlog
1A.2 customer data ingested |  | MAIA: Faber Castell | Phase 01 | 9. Backlog
1A.3 product data ingested |  | MAIA: Faber Castell | Phase 01 | 9. Backlog
1A.4 customer pricing ingested |  | MAIA: Faber Castell | Phase 01 | 9. Backlog
1A.5 user profile ingested |  | MAIA: Faber Castell | Phase 01 | 9. Backlog
1A.6 sftp connection established |  | MAIA: Faber Castell | Phase 01 | 9. Backlog
Origiinal b2c timeline |  | MAIA: Farmshop | Phase 01
Updated timeline |  | MAIA: Farmshop | Phase 01 | 9. Backlog
Client UAT |  | MAIA: Farmshop | Phase 01 | 3. Completed |  |  | 2026-04-01 16:00 | 2026-04-05 16:00 |  |  |  | Updated timeline
Fixes & retest |  | MAIA: Farmshop | Phase 01 | 3. Completed |  |  | 2026-04-05 16:00 | 2026-04-07 16:00 |  |  |  | Updated timeline
feedback |  | MAIA: Farmshop | Phase 01 | 3. Completed |  |  | 2026-04-07 16:00 | 2026-04-08 16:00 |  |  |  | Updated timeline
Completition |  | MAIA: Farmshop | Phase 01 | 2.c. Delayed |  |  | 2026-04-09 16:00 | 2026-04-09 16:00 |  |  |  | Updated timeline
Update to prod |  | MAIA: Farmshop | Phase 01 | 2.c. Delayed |  |  | 2026-04-12 16:00 | 2026-04-14 16:00 |  |  |  | Updated timeline
Client Sign off |  | MAIA: Farmshop | Phase 01 | 2.c. Delayed |  |  | 2026-04-16 16:00 | 2026-04-16 16:00 |  |  |  | Updated timeline
SQL integration internal testing & Fixes |  | MAIA: Mackessen | POC | 9. Backlog |  |  | 2026-04-06 16:00 | 2026-04-09 16:00
|  | MAIA: Arrow Anbao Forging |  | 9. Backlog |  |  | 2026-04-05 16:00
Order level tax exemp enforcement (Development) |  | MAIA: Holsen | Phase 01 | 2. In Progress |  | Abdul Haiqal Abdul Aziz,Fariha Anis,Wei Shen | 2026-04-19 16:00 | 2026-04-21 16:00
AR NEw Timeline |  | MAIA: Lean Giap | Phase 02 | 9. Backlog |  |  | 2026-04-09 16:00
AR FE improv |  | MAIA: Lean Giap | Phase 02 | 9. Backlog |  |  | 2026-04-12 16:00 | 2026-04-13 16:00 |  |  |  | AR NEw Timeline
Delayed timeline |  | MAIA: Lean Giap | Phase 01 | 9. Backlog |  |  | 2026-04-09 16:00
new testing |  | MAIA: Lean Giap | Phase 01 | 9. Backlog |  |  | 2026-04-09 16:00 | 2026-04-09 16:00 |  |  |  | Updated Phase 1 Dev Timeline
inform eric to test |  | MAIA: Lean Giap | Phase 01 | 3. Completed |  |  | 2026-04-16 16:00 | 2026-04-16 16:00 |  |  |  | Delayed timeline
Bug fixes |  | MAIA: Lean Giap | Phase 01 | 3. Completed |  |  | 2026-04-12 16:00 | 2026-04-15 16:00 |  |  |  | Delayed timeline
final Eric Test |  | MAIA: Lean Giap | Phase 01 | 2. In Progress |  |  | 2026-04-16 16:00 | 2026-04-19 16:00 |  |  |  | Delayed timeline
Prod Transition |  | MAIA: Lean Giap | Phase 01 | 0. Not Started |  |  | 2026-04-21 16:00 | 2026-04-22 16:00 |  |  |  | Delayed timeline
Sign off (meeting) | Things to discuss: 1. Training date 2. Feedback if any and plans for fixes. 3. KYC and CRM | MAIA: Lean Giap | Phase 01 | 1.b. Planned |  | Brendan | 2026-04-20 16:00 | 2026-04-20 16:00 |  |  |  | Delayed timeline
ARAP brief |  | MAIA: Lean Giap | Phase 02 | 9. Backlog |  |  | 2026-04-09 16:00 |  |  |  |  | AR NEw Timeline
testing |  | MAIA: Lean Giap | Phase 02 | 9. Backlog |  |  | 2026-04-14 16:00 | 2026-04-15 16:00 |  |  |  | AR NEw Timeline
Eric breif |  | MAIA: Lean Giap | Phase 02 | 9. Backlog |  |  | 2026-04-16 16:00 | 2026-04-16 16:00 |  |  |  | AR NEw Timeline
AP timeline |  | MAIA: Lean Giap | Phase 02 | 9. Backlog |  |  | 2026-04-09 16:00
AP discussion |  | MAIA: Lean Giap | Phase 02 | 9. Backlog |  |  | 2026-04-09 16:00 |  |  |  |  | AP timeline
BE dev |  | MAIA: Lean Giap | Phase 02 | 9. Backlog |  |  | 2026-04-12 16:00 | 2026-04-14 16:00 |  |  |  | AP timeline
FE fev |  | MAIA: Lean Giap | Phase 02 | 9. Backlog |  |  | 2026-04-12 16:00 | 2026-04-15 16:00 |  |  |  | AP timeline
Chatbot dev |  | MAIA: Lean Giap | Phase 02 | 9. Backlog |  |  | 2026-04-15 16:00 | 2026-04-15 16:00 |  |  |  | AP timeline
Testing |  | MAIA: Lean Giap | Phase 02 | 9. Backlog |  |  | 2026-04-16 16:00 | 2026-04-19 16:00 |  |  |  | AP timeline
Handover to eric |  | MAIA: Lean Giap | Phase 02 | 9. Backlog |  |  | 2026-04-20 16:00 | 2026-04-20 16:00 |  |  |  | AP timeline
Plan Roll Out with Ilene |  | MAIA: Farmshop | Phase 01 | 2.c. Delayed |  |  | 2026-04-13 16:00 | 2026-04-13 16:00 |  |  |  | Updated timeline
Handover to Ilene |  | MAIA: Farmshop | Phase 01 | 2.c. Delayed |  |  | 2026-04-15 16:00 | 2026-04-15 16:00 |  |  |  | Updated timeline
Meeting (Feedback/Brief/) |  | MAIA: Holsen | Phase 01 | 3. Completed |  |  | 2026-04-14 16:00 | 2026-04-14 16:00
AWS Billing Setup |  | MAIA: Holsen | AWS | 2. In Progress |  |  | 2026-04-14 16:00 | 2026-04-19 16:00
Product Attribute Tagging |  | MAIA: Holsen | Phase 01 | 2. In Progress |  | Abdul Haiqal Abdul Aziz | 2026-04-19 16:00 | 2026-04-20 16:00
Historical Pricing with discount |  | MAIA: Fixguru | Phase 01 | 2. In Progress |  |  | 2026-04-12 16:00 | 2026-04-21 16:00
Aws Setup |  | MAIA: Fixguru | Phase 01 | 2. In Progress |  |  | 2026-04-14 16:00 | 2026-04-19 16:00
Fixguru Management away |  | MAIA: Fixguru | Phase 01 | 2. In Progress |  |  | 2026-04-14 16:00 | 2026-04-21 16:00
Autocount prod migration |  | MAIA: Fixguru | Phase 01 | 2. In Progress |  |  | 2026-04-12 16:00 | 2026-04-19 16:00
Test einvoice pdf pulling |  | MAIA: Fixguru | Phase 01 | 2. In Progress |  |  | 2026-04-13 16:00 | 2026-04-21 16:00
internal showcase (cal & einv) |  | MAIA: Fixguru | Phase 02 | 3. Completed |  |  | 2026-04-13 16:00 | 2026-04-19 16:00
sql testing |  | MAIA: Mackessen | POC | 9. Backlog |  |  | 2026-04-13 16:00 | 2026-04-13 16:00
Scheduled SCC IT Vendor meeting | Meeting with IT vendor to scope out work needed for SAP Integration | MAIA: SCC |  | 3. Completed |  | Jun Yan Lim | 2026-04-16 16:00 | 2026-04-16 16:00
B2C roll Out |  | MAIA: Farmshop | Phase 01 | 2. In Progress |  |  | 2026-04-13 16:00
B2B timeline |  | MAIA: Farmshop | Phase 01 | 0. Not Started |  |  | 2026-04-13 16:00
Prod Live |  | MAIA: Lean Giap | Phase 01 | 0. Not Started |  |  | 2026-04-23 16:00 | 2026-04-23 16:00 |  |  |  | Delayed timeline
AR Delayed Timeline |  | MAIA: Lean Giap | Phase 02 | 0. Not Started |  |  | 2026-04-09 16:00 | 2026-04-09 16:00
FE/BE Dev |  | MAIA: Lean Giap | Phase 02 | 2.c. Delayed |  |  | 2026-04-12 16:00 | 2026-04-19 16:00 |  |  |  | AR Delayed Timeline
Testing |  | MAIA: Lean Giap | Phase 02 | 0. Not Started |  |  | 2026-04-19 16:00 | 2026-04-20 16:00 |  |  |  | AR Delayed Timeline
bug fixes |  | MAIA: Lean Giap | Phase 02 | 0. Not Started |  |  | 2026-04-19 16:00 | 2026-04-20 16:00 |  |  |  | AR Delayed Timeline
Eric Brief |  | MAIA: Lean Giap | Phase 02 | 0. Not Started |  |  | 2026-04-20 16:00 | 2026-04-20 16:00 |  |  |  | AR Delayed Timeline
Eric test |  | MAIA: Lean Giap | Phase 02 | 0. Not Started |  |  | 2026-04-20 16:00 | 2026-04-22 16:00 |  |  |  | AR Delayed Timeline
client issue reported and fixes |  | MAIA: Lean Giap | Phase 02 | 0. Not Started |  |  | 2026-04-20 16:00 | 2026-04-22 16:00 |  |  |  | AR Delayed Timeline
Sign off |  | MAIA: Lean Giap | Phase 02 | 0. Not Started |  |  | 2026-04-23 16:00 | 2026-04-23 16:00 |  |  |  | AR Delayed Timeline
Prod Setup |  | MAIA: Lean Giap | Phase 02 | 0. Not Started |  |  | 2026-04-23 16:00 | 2026-04-27 16:00 |  |  |  | AR Delayed Timeline
Go live |  | MAIA: Lean Giap | Phase 02 | 0. Not Started |  |  | 2026-04-28 16:00 | 2026-04-28 16:00 |  |  |  | AR Delayed Timeline
AP Delayed Timeline |  | MAIA: Lean Giap | Phase 02 | 0. Not Started |  |  | 2026-04-14 16:00
FE Dev |  | MAIA: Lean Giap | Phase 02 | 2.c. Delayed |  |  | 2026-04-12 16:00 | 2026-04-19 16:00 |  |  |  | AP Delayed Timeline
BE Dev |  | MAIA: Lean Giap | Phase 02 | 2.c. Delayed |  |  | 2026-04-12 16:00 | 2026-04-19 16:00 |  |  |  | AP Delayed Timeline
Testing |  | MAIA: Lean Giap | Phase 02 | 0. Not Started |  |  | 2026-04-19 16:00 | 2026-04-20 16:00 |  |  |  | AP Delayed Timeline
Bug fixes |  | MAIA: Lean Giap | Phase 02 | 0. Not Started |  |  | 2026-04-19 16:00 | 2026-04-20 16:00 |  |  |  | AP Delayed Timeline
Eric Brief |  | MAIA: Lean Giap | Phase 02 | 1.b. Planned |  |  | 2026-04-20 16:00 | 2026-04-20 16:00 |  |  |  | AP Delayed Timeline
Eric test |  | MAIA: Lean Giap | Phase 02 | 1.b. Planned |  |  | 2026-04-21 16:00 | 2026-04-22 16:00 |  |  |  | AP Delayed Timeline
Client issue report & fix |  | MAIA: Lean Giap | Phase 02 | 1.b. Planned |  |  | 2026-04-21 16:00 | 2026-04-22 16:00 |  |  |  | AP Delayed Timeline
SIgn off ap |  | MAIA: Lean Giap | Phase 02 | 1.b. Planned |  |  | 2026-04-23 16:00 | 2026-04-23 16:00 |  |  |  | AP Delayed Timeline
Prod Setup ap |  | MAIA: Lean Giap | Phase 02 | 0. Not Started |  |  | 2026-04-23 16:00 | 2026-04-27 16:00 |  |  |  | AP Delayed Timeline
GO live ap |  | MAIA: Lean Giap | Phase 02 | 0. Not Started |  |  | 2026-04-28 16:00 | 2026-04-28 16:00 |  |  |  | AP Delayed Timeline
internal testing |  | MAIA: Lean Giap | Phase 01 | 3. Completed |  |  | 2026-04-12 16:00 | 2026-04-15 16:00 |  |  |  | Delayed timeline
1A.7 output file to be exported |  | MAIA: Faber Castell | Phase 01 | 0. Not Started
1A.8 push order to FTP (pre-price) |  | MAIA: Faber Castell | Phase 01 | 0. Not Started
1A.9 b2b integration |  | MAIA: Faber Castell | Phase 01 | 0. Not Started
1B. Email & Excel |  | MAIA: Faber Castell | Phase 01 | 0. Not Started |  |  | 2026-04-07 16:00 | 2026-04-12 16:00
1B.1 excel order ingestion |  | MAIA: Faber Castell | Phase 01 | 0. Not Started
1B.2 email channel integration |  | MAIA: Faber Castell | Phase 01 | 0. Not Started
2. Credit Control |  | MAIA: Faber Castell | Phase 01 | 0. Not Started |  |  | 2026-04-12 16:00 | 2026-04-15 16:00
2.1 credit file ingested |  | MAIA: Faber Castell | Phase 01 | 0. Not Started
2.2 update exposure, overdue, credit limit to maia |  | MAIA: Faber Castell | Phase 01 | 0. Not Started
2.3 credit approval |  | MAIA: Faber Castell | Phase 01 | 0. Not Started
2.4 credit check notification - email |  | MAIA: Faber Castell | Phase 01 | 0. Not Started
4. Push order to FTP (Post-check) |  | MAIA: Faber Castell | Phase 01 | 0. Not Started |  |  | 2026-04-20 16:00 | 2026-04-21 16:00
4.1 exclude b2b order |  | MAIA: Faber Castell | Phase 01 | 0. Not Started
4.2 b2b order notification to CS (submit by) AND ALL FINANCE users |  | MAIA: Faber Castell | Phase 01 | 0. Not Started
4.3 export order to FTP |  | MAIA: Faber Castell | Phase 01 | 0. Not Started
Product QA |  | MAIA: Faber Castell | Phase 01 | 0. Not Started |  |  | 2026-04-19 16:00 | 2026-04-23 16:00
UAT |  | MAIA: Faber Castell | Phase 01 | 0. Not Started |  |  | 2026-04-26 16:00 | 2026-05-02 16:00
3. Mforce Order Intake |  | MAIA: Faber Castell | Phase 01 | 0. Not Started |  |  | 2026-04-16 16:00 | 2026-04-19 16:00
3.1 pull mforce order export file from ftp |  | MAIA: Faber Castell | Phase 01 | 0. Not Started
3.2 differentiate new order vs existing order in maia |  | MAIA: Faber Castell | Phase 01 | 0. Not Started
3.3 new mforce order creation flow |  | MAIA: Faber Castell | Phase 01 | 0. Not Started
3.4 existing maia order mforce update flow |  | MAIA: Faber Castell | Phase 01 | 0. Not Started
Feedback Feature Update |  | Pelangi Awan | Phase 03 | 3. Completed |  |  | 2026-02-16 04:24 | 2026-02-19 16:00
Quiz/Exam Rework - Question Filter |  | Pelangi Awan | Phase 03 | 3. Completed |  |  | 2026-03-03 16:00 | 2026-03-11 16:00
Quiz/Exam Rework - Monthly Calendar |  | Pelangi Awan | Phase 03 | 3. Completed |  |  | 2026-03-11 16:00 | 2026-03-18 16:00
Quiz/Exam Rework - Adaptive Difficulty |  | Pelangi Awan | Phase 03 | 3. Completed |  |  | 2026-03-16 16:00 | 2026-03-19 16:00
Material Mapping (Pelangi) |  | Pelangi Awan | Phase 03 | 3. Completed |  |  | 2026-03-12 16:00 | 2026-03-17 16:00
Database Schema Planning |  | Pelangi Awan | Phase 03 | 3. Completed |  |  | 2026-03-15 16:00 | 2026-03-17 16:00
UAT Milestone 1 |  | Pelangi Awan | Phase 03 | 3. Completed |  |  | 2026-03-25 16:00 | 2026-04-02 16:00
LLM Change - BC Deepseek v3 |  | Pelangi Awan | Phase 03 | 3. Completed |  |  | 2026-03-23 16:00 | 2026-03-24 16:00
LLM Change - BM OpenAI 4o mini |  | Pelangi Awan | Phase 03 | 3. Completed |  |  | 2026-03-25 16:00 | 2026-03-26 16:00
Q&A Textbook Ingestion - BM |  | Pelangi Awan | Phase 03 | 2. In Progress |  |  | 2026-04-05 16:00 | 2026-04-09 16:00
Q&A Textbook Ingestion - BC |  | Pelangi Awan | Phase 03 | 2. In Progress |  |  | 2026-03-16 16:00 | 2026-04-02 16:00
Q&A Textbook Ingestion - Ekonomi |  | Pelangi Awan | Phase 03 | 2. In Progress |  |  | 2026-03-09 16:00 | 2026-03-15 16:00
Subscription & Onboarding - Individual |  | Pelangi Awan | Phase 03 | 2. In Progress |  |  | 2026-03-12 16:00 | 2026-03-16 16:00
Subscription & Onboarding - Bundle |  | Pelangi Awan | Phase 03 | 2. In Progress |  |  | 2026-03-17 16:00 | 2026-03-23 16:00
Teacher Portal |  | Pelangi Awan | Phase 03 | 2. In Progress |  |  | 2026-03-24 16:00 | 2026-04-06 16:00
Student Portal |  | Pelangi Awan | Phase 03 | 2. In Progress |  |  | 2026-04-07 16:00 | 2026-04-12 16:00
Parent Portal |  | Pelangi Awan | Phase 03 | 2. In Progress |  |  | 2026-04-07 16:00 | 2026-04-12 16:00
Pelangi Admin Portal |  | Pelangi Awan | Phase 03 | 2. In Progress |  |  | 2026-04-13 16:00 | 2026-04-15 16:00
Dashboard - Pelangi Admin |  | Pelangi Awan | Phase 03 | 2. In Progress |  |  | 2026-04-15 16:00 | 2026-04-15 16:00
Dashboard - Student, Parent |  | Pelangi Awan | Phase 03 | 2. In Progress |  |  | 2026-04-15 16:00 | 2026-04-16 16:00
Dashboard - Teacher |  | Pelangi Awan | Phase 03 | 2. In Progress |  |  | 2026-04-19 16:00 | 2026-04-20 16:00
Q&A QA - all 3 subjects |  | Pelangi Awan | Phase 03 | 2. In Progress |  |  | 2026-04-12 16:00 | 2026-04-16 16:00
Milestone 2 UAT Preparation - Webapp |  | Pelangi Awan | Phase 03 | 0. Not Started |  |  | 2026-04-21 16:00 | 2026-04-22 16:00
Milestone 2 UAT Preparation - Q&A |  | Pelangi Awan | Phase 03 | 0. Not Started |  |  | 2026-04-21 16:00 | 2026-04-22 16:00
UAT Milestone 2 |  | Pelangi Awan | Phase 03 | 0. Not Started |  |  | 2026-04-26 16:00 | 2026-04-30 16:00
Question Bank - BM |  | Pelangi Awan | Phase 03 | 2. In Progress |  |  | 2026-04-19 16:00 | 2026-04-27 16:00
Question Bank - BC |  | Pelangi Awan | Phase 03 | 2. In Progress |  |  | 2026-04-08 16:00 | 2026-04-16 16:00
Question Bank - Ekonomi |  | Pelangi Awan | Phase 03 | 2. In Progress |  |  | 2026-04-28 16:00 | 2026-05-04 16:00
UAT Milestone 3 |  | Pelangi Awan | Phase 03 | 0. Not Started |  |  | 2026-05-10 16:00 | 2026-05-23 16:00
Teacher Chatbot |  | Pelangi Awan | Phase 03 | 0. Not Started |  |  | 2026-04-19 16:00 | 2026-04-30 16:00
Language Preference |  | Pelangi Awan | Phase 03 | 0. Not Started |  |  | 2026-04-21 16:00 | 2026-04-21 16:00
English Qs Bank Improvement |  | Pelangi Awan | Phase 03 | 0. Not Started |  |  | 2026-05-05 16:00 | 2026-05-16 16:00
UAT Sign off |  | Pelangi Voucher | Phase 01 | 0. Not Started |  |  | 2026-04-23 16:00 | 2026-04-23 16:00
Production Launch |  | MAIA: Farmshop | Phase 01 | 0. Not Started |  |  | 2026-05-03 16:00 | 2026-05-03 16:00 |  |  |  | Updated timeline
Friday Cadence 24Apr | Must talk about: 1. First B2B Invoice Payment 2. B2C Invoice Issuance 3. Feedback management and timeline. 4. Feedback on how much time it saves with MAIA, overall user experience feedback | MAIA: Farmshop | Phase 01 | 0. Not Started |  |  | 2026-04-23 16:00 | 2026-04-23 16:00 |  |  |  | Updated timeline
Cadence 30 Apr |  | MAIA: Farmshop | Phase 01 | 0. Not Started |  |  | 2026-04-29 16:00 | 2026-04-29 16:00 |  |  |  | Updated timeline
B2B/C Feedback Fixes |  | MAIA: Farmshop | Phase 01 | 1a. Scoping |  | Brendan | 2026-04-19 16:00 | 2026-04-22 16:00 |  | Screenshot 2026-04-20 at 10.58.14 AM.png |  | Updated timeline
Timeline alignment with Kode |  | MAIA: Farmshop | Phase 01 | 0. Not Started |  |  | 2026-04-19 16:00 | 2026-04-19 16:00 |  |  |  | Updated timeline
Subscription dev (Kode) |  | MAIA: Farmshop | Phase 01 | 0. Not Started |  |  | 2026-04-20 16:00 | 2026-04-22 16:00 |  |  |  | Updated timeline
subscription testing |  | MAIA: Farmshop | Phase 01 | 0. Not Started |  |  | 2026-04-23 16:00 | 2026-04-26 16:00 |  |  |  | Updated timeline
finalized (Payment) |  | MAIA: Farmshop | Phase 01 | 0. Not Started |  |  | 2026-04-23 16:00 | 2026-04-27 16:00 |  |  |  | Updated timeline
Checkout Testing |  | MAIA: Farmshop | Phase 01 | 0. Not Started |  |  | 2026-04-27 16:00 | 2026-04-28 16:00 |  |  |  | Updated timeline
DN Listing Invoice/Order HyperLink |  | MAIA: Farmshop | Phase 01 | 0. Not Started |  | Brendan,Amirul Iman bin Amran,Wei Yon | 2026-04-20 16:00 | 2026-04-20 16:00 |  |  |  | Updated timeline
PDF Generation Fix | Raise on Standup 20 Apr26: 1. Ensure that the tables respect the document footer margins. 2. Ensure that Logo is only rendered on the first page and not every page. 3. Manage client expectation and education on how PDFs are Generated | MAIA: Farmshop | Phase 01 | 0. Not Started | Q3. Important but not urgent | Brendan,Wei Yon,Bushra Mualla | 2026-04-20 16:00 | 2026-04-20 16:00 |  |  |  | Updated timeline
Add activity log on pdf generation |  | MAIA: Farmshop | Phase 01 | 0. Not Started |  |  | 2026-04-20 16:00 | 2026-04-20 16:00 |  |  |  | Updated timeline
B2B Invoice Payment |  | MAIA: Farmshop | Payment | 2. In Progress |  |  | 2026-04-23 16:00 | 2026-04-23 16:00 |  |  |  | Updated timeline
B2C Invoice Payment |  | MAIA: Farmshop | Payment | 0. Not Started |  |  | 2026-04-23 16:00 | 2026-04-23 16:00 |  |  |  | Updated timeline
Training w LG ( after rsign off) |  | MAIA: Lean Giap | Phase 01 | 2a.Blocked |  |  | 2026-04-26 16:00 | 2026-04-26 16:00 |  |  |  | Delayed timeline
Customer Note > Epicor | Ensure Customer Notes created in MAIA is pushed to Epicor | MAIA: Lean Giap | Phase 01 | 0. Not Started |  | Muhammad Azib Iqbal Bin Harun,Brendan | 2026-04-20 16:00 | 2026-04-20 16:00 |  |  |  | Delayed timeline
check eric testing |  | MAIA: Lean Giap | Phase 01 | 0. Not Started |  |  | 2026-04-19 16:00 |  |  |  |  | Delayed timeline
Notification Catalogue |  | MAIA | Phase 01 | 0. Not Started |  | Ivan | 2026-04-19 16:00 | [5 empty] | Notification and ToDos Grooming =
ToDo Catalogue |  | MAIA | Phase 01 | 0. Not Started |  | Ivan | 2026-04-19 16:00 | [5 empty] | Notification and ToDos Grooming =
Notification Serving Pipeline |  | MAIA | Phase 01 | 0. Not Started |  | Ivan | 2026-04-19 16:00 | [5 empty] | Notification and ToDos Grooming =
ToDo Serving Pipeline |  | MAIA | Phase 01 | 0. Not Started |  | Ivan | 2026-04-19 16:00 | [5 empty] | Notification and ToDos Grooming =
Chatbot Serving Specifications |  | MAIA | Phase 01 | 0. Not Started |  |  | 2026-04-19 16:00 | [5 empty] | Notification and ToDos Grooming =
AWS setup |  | MAIA: Mackessen | AWS | 0. Not Started |  |  | 2026-04-16 16:00 | 2026-04-19 16:00
Chatbot Serving Pipeline |  | MAIA | Phase 01 | 0. Not Started |  |  | 2026-04-19 16:00 | [5 empty] | Notification and ToDos Grooming =
Final Notification and ToDo QA |  | MAIA | Phase 01 | 0. Not Started |  |  | 2026-04-19 16:00 | [5 empty] | Notification and ToDos Grooming =
Product transition |  | MAIA: Mackessen | Phase 01 | 0. Not Started |  |  | 2026-04-30 16:00 | 2026-05-03 16:00
|  | MAIA | Phase 01 | 0. Not Started |  |  | 2026-04-19 16:00 | [5 empty] | Notification and ToDos Grooming =
MKS Scope Review |  | MAIA: Mackessen | Phase 01 | 0. Not Started |  | Brendan | 2026-04-20 16:00 | 2026-04-20 16:00
Proposal Approach Brief |  | MAIA: Ming Medical | Phase 01 | 0. Not Started |  | Brendan | 2026-04-16 16:00 | 2026-04-16 16:00
Develop CPG template for ming to Fill |  | MAIA: Ming Medical | Phase 01 | 0. Not Started |  | Jermaine,Brendan,Ivan | 2026-04-20 16:00 | 2026-04-21 16:00
InComplete CPG file receive |  | MAIA: Ming Medical | Phase 01 | 0. Not Started |  |  | 2026-04-19 16:00 | 2026-04-19 16:00
Cadence (Feedback) |  | MAIA: Ultimax | Phase 01 | 3. Completed |  | Jun Yan Lim | 2026-04-13 16:00 | 2026-04-13 16:00 |  | Ultimax_9Apr_Feedback_Dev_Handoff.docx |  |  |  | Ultimax_9Apr_Feedback_Dev_Handoff
SO PDF to have Self Pay and SOCSO template |  | MAIA: Ultimax | Phase 01 | 3. Completed |  | Bushra Mualla | 2026-04-14 16:00 | 2026-04-14 16:00
DN PDF to remove weight information |  | MAIA: Ultimax | Phase 01 | 3. Completed |  | Bushra Mualla,Wei Yon | 2026-04-16 16:00 | 2026-04-16 16:00
Stock Recon Function Exp Mgmgnt to Client | Agenda of the call: 1. Align expectation on how Stock Reconciliation Feature > We will not implement pulling all inventory information by item group > Alternative: Segregate item locations by item group (done manually or by user) > Why this alternative: then can re use the existing pull inventory by location to get all the stock (by item group, organised by sub locations within the warehouse) | MAIA: Ultimax | Phase 01 | 0. Not Started |  | Jun Yan Lim | 2026-04-19 16:00
AWS Billing Completed |  | MAIA: Ultimax | AWS | 0. Not Started |  |  | 2026-04-21 16:00 | 2026-04-21 16:00
Send SOW to Ming medical |  | MAIA: Ming Medical | Phase 01 | 0. Not Started |  | Brendan | 2026-04-22 16:00 | 2026-04-22 16:00
Draft SOW |  | MAIA: Ming Medical | Phase 01 | 0. Not Started |  |  | 2026-04-20 16:00 | 2026-04-20 16:00
Ming Medical AWAY |  | MAIA: Ming Medical | Phase 01 | 0. Not Started |  |  | 2026-04-23 16:00 | 2026-05-02 16:00
WABA Setup |  | MAIA: Ultimax | Meta WABA | 0. Not Started |  |  | 2026-04-21 16:00 | 2026-04-21 16:00
Send ming CPG template |  | MAIA: Ming Medical | Phase 01 | 0. Not Started |  |  | 2026-04-22 16:00 | 2026-04-22 16:00
AWS Billing Guide Sent | Sent to Whatsapp group etc | MAIA: Ultimax | AWS | 3. Completed |  | Jun Yan Lim | 2026-04-16 16:00 | 2026-04-16 16:00
Cadence (3rd Week of April 26) | Agenda of the call: 1. Align expectation on how Stock Reconciliation Feature > We will not implement pulling all inventory information by item group > Alternative: Segregate item locations by item group (done manually or by user) > Why this alternative: then can re use the existing pull inventory by location to get all the stock (by item group, organised by sub locations within the warehouse) 2. Clarification on the bundles SKU and name > What is the finalized name. | MAIA: Ultimax | Phase 01 | 7. Scheduled |  |  | 2026-04-20 16:00 | 2026-04-20 16:00
Company Phone number purchase? |  | MAIA: Ultimax | Meta WABA | 3. Completed |  |  | 2026-04-16 16:00 | 2026-04-16 16:00
FE Warehouse BUG | Users unable to CRUD warehouses and warehouse group in the Logistics workspace. Ultimax will need to organise their inventory and set up their inventory locations by item group, not having this feature will block them from doing so and block sign off. | MAIA: Ultimax | Phase 01 | 1a. Scoping |  | Amirul Iman bin Amran,Abdul Haiqal Abdul Aziz | 2026-04-19 16:00 | 2026-04-20 16:00
ProductIon Launch |  | MAIA: Ultimax | Phase 01 | 0. Not Started |  |  | 2026-04-29 16:00 | 2026-04-29 16:00
UAT (1 day) |  | MAIA: Ultimax | Phase 01 | 0. Not Started |  |  | 2026-04-27 16:00 | 2026-04-27 16:00
UAT (Fixes) |  | MAIA: Ultimax | Phase 01 | 0. Not Started |  |  | 2026-04-28 16:00 | 2026-04-28 16:00
IT Vendor meeting with SAP |  | MAIA: SCC |  | 7. Scheduled |  |  | 2026-04-22 16:00 | 2026-04-22 16:00
Thermac SOW Rescope | Discussion for quotation concerns raised during proposal meeting. 1. Empty SKU for item that does not exist in the database 2. Quotation Calculator 3. Historical item pricing 4. Adhoc charges lines inside item table 5. Free text field with just columns so can input anything. | MAIA: Thermac | Phase 01 | 7. Scheduled |  | Jun Yan Lim,Ivan | 2026-04-19 16:00 | [6 empty] | 17 Apr - 2026 Proposal meeting notes
Fix long horizon Export bug |  | ZUS ARAP | Production | 0. Not Started |  | Brendan | 2026-04-19 16:00
Sprint Planning |  | MAIA: Ming Medical | Phase 01 | 0. Not Started |  |  | 2026-04-23 16:00 | 2026-04-26 16:00
Meta Setup |  | MAIA: Ming Medical | Phase 01 | 0. Not Started |  |  | 2026-04-22 16:00 | 2026-04-22 16:00
Aws Setup |  | MAIA: Ming Medical | Phase 01 | 0. Not Started |  |  | 2026-04-22 16:00 | 2026-04-22 16:00
SOW 2nd draft |  | MAIA: Thermac | Phase 01 | 0. Not Started |  |  | 2026-04-19 16:00 | 2026-04-19 16:00
Item RAG Search Accuracy Improvement |  | MAIA | Phase 01 | 2. In Progress |  | Jermaine,Afiq Aqil | 2026-04-19 16:00
Item RAG Search Accuracy Improvement |  | MAIA | Phase 02 | 0. Not Started |  | Jermaine,Afiq Aqil | 2026-04-19 16:00
Item RAG Search Accuracy Improvement |  | MAIA | Phase 03 | 0. Not Started |  | Jermaine,Afiq Aqil | 2026-04-19 16:00
Send new SOW to Thermac |  | MAIA: Thermac | Phase 01 | 0. Not Started |  |  | 2026-04-20 16:00 | 2026-04-20 16:00
Ultimax data clean up |  | MAIA: Ultimax | Phase 01 | 1.b. Planned |  | Jun Yan Lim | 2026-04-20 16:00 | 2026-04-20 16:00
B2B Invoice sent |  | MAIA: Farmshop | Payment | 0. Not Started |  |  | 2026-04-05 16:00 | 2026-04-09 16:00 |  |  |  | Updated timeline
Check for Subscription |  | MAIA: Farmshop | Payment | 2a.Blocked |  | Brendan | 2026-04-19 16:00 |  |  |  |  | Updated timeline
B2B Subscription Start Date |  | MAIA: Farmshop | Payment | 2a.Blocked |  |  | 2026-04-23 16:00 | 2026-04-23 16:00 |  |  |  | Updated timeline
B2C Subs Start |  | MAIA: Farmshop | Payment | 2a.Blocked |  |  | 2026-04-23 16:00 | 2026-04-23 16:00 |  |  |  | Updated timeline
|  | MAIA: Farmshop | Payment | 0. Not Started |  |  | 2026-04-19 16:00 |  |  |  |  | Updated timeline
Product SYNC | 1. Chase Payment 2. Check Subscription 3. B2C Invoicing date. 4. Farmshop side Kode CR, follow up 5. Prep for the Friday Cadence | MAIA: Faber Castell | Phase 01 | 3. Completed |  | Brendan | 2026-04-19 16:00 |  |  |  |  | Updated timeline
Product Sync | Test product item search. Dev and chatbot | MAIA: Ultimax | Phase 01 | 0. Not Started |  |  | 2026-04-19 16:00
Get afiq to prep auto report for B2C Conversation |  | MAIA: Farmshop | Payment | 0. Not Started |  | Jermaine,Afiq Aqil,Afiq Aqil | 2026-05-03 16:00 | 2026-05-03 16:00 |  |  |  | Updated timeline
Product Sync | 1. Chase Payment for B2B 2. Prep for Friday Meeting (check meeting task for agenda) 3. Invoice B2C Chatbot 4. Start B2B Subscription Invoiceing 5. Natalie to be briefed for Monthly Billing Cadences 6. Prep Afiq side for Monthly Chat Usage Reports. | MAIA: Farmshop | Phase 01 | 0. Not Started |  | Brendan | 2026-04-19 16:00 |  |  |  |  | Updated timeline
|  | MAIA: Farmshop | Payment | 0. Not Started |  |  | 2026-04-19 16:00 |  |  |  |  | Updated timeline
Product Sync |  | MAIA: Lean Giap | Phase 01 | 0. Not Started |  | Brendan | 2026-04-19 16:00 |  |  |  |  | Delayed timeline
Customer Notes Query Back | Identify how to best retrieve customer notes back to serve to the chatbot user - Single source of truth in MAIA (not write back from EPICOR) - How they want the notes to be To scope | MAIA: Lean Giap | Phase 01 | 1. Req. Gathering | Q1: Important and urgent | Jermaine,Brendan | 2026-04-19 16:00 | 2026-04-19 16:00 |  |  |  | Delayed timeline
get updates from azib on sql setup |  | MAIA: Mackessen | POC | 0. Not Started |  |  | 2026-04-19 16:00
3-day Onboarding |  | MAIA: Roadmap | Phase 01 | 0. Not Started |  | Ivan | 2026-04-19 16:00
Full Product Catalogue |  | MAIA: Ming Medical | Phase 01 | 0. Not Started |  | Brendan | 2026-04-20 16:00 | 2026-04-20 16:00
Customer History |  | MAIA: Ming Medical | Phase 01 | 0. Not Started |  | Brendan | 2026-04-20 16:00 | 2026-04-20 16:00
Quotation Engine Spec |  | MAIA: Ming Medical | Phase 01 | 3. Completed |  | Ivan | 2026-04-17 16:00 | 2026-04-17 16:00
Quotation Engine Architecture Discussion |  | MAIA: Ming Medical | Phase 01 | 0. Not Started |  | Jermaine,Ivan | 2026-04-21 16:00 | 2026-04-21 16:00
Production (ALL) |  | MAIA: Ming Medical | Phase 01 | 0. Not Started |  |  | 2026-05-20 16:00 | 2026-05-20 16:00
open AI |  | MAIA: Ming Medical | Phase 01 | 0. Not Started |  |  | 2026-04-19 16:00
whatsapp number |  | MAIA: Ming Medical | Phase 01 | 0. Not Started |  |  | 2026-04-19 16:00
Gap analysis (MVP -> V1) |  | MAIA: Farmshop | Phase 02 | 0. Not Started |  | Brendan,Ivan,Jermaine | 2026-05-03 16:00 | 2026-05-03 16:00 |  |  |  | Updated timeline
check when did they stop paying |  | ZUS ARAP | Payment | 0. Not Started |  | Johnson,Jermaine | 2026-04-19 16:00
Add UoM to Pick List |  | MAIA: Holsen | Phase 01 | 0. Not Started |  |  | 2026-04-19 16:00
DN from PL | Why? What? how? | MAIA: Holsen | Phase 01 | 1a. Scoping |  |  | 2026-04-19 16:00
Meta Account Setup |  | MAIA: Holsen | Meta WABA | 2a.Blocked |  | Gareth Ng | 2026-04-19 16:00
Whatsapp Number |  | MAIA: Holsen | Meta WABA | 2a.Blocked |  |  | 2026-04-19 16:00
AWS Billing |  | MAIA: Holsen | AWS | 2. In Progress |  |  | 2026-04-19 16:00
OpenAI API Key |  | MAIA: Holsen | OpenAI | 3. Completed |  |  | 2026-04-19 16:00
Item and Doctype Tagging |  | MAIA: Holsen | Phase 01 | 2. In Progress |  |  | 2026-04-19 16:00 | 2026-04-19 16:00
Scoping how to be Business Partner |  | MAIA: META Business Partner | Phase 01 | 1a. Scoping | Q1: Important and urgent | Jermaine | 2026-04-19 16:00
|  | MAIA: META Business Partner | Phase 01 | 0. Not Started |  |  | 2026-04-19 16:00
Production (without Batch/SN Tax Enformcement) |  | MAIA: Holsen | Phase 01 | 0. Not Started |  |  | 2026-04-29 16:00 | 2026-04-29 16:00
Tax Exemption Batch/SN Enforcement |  | MAIA: Holsen | Phase 02 | 2.c. Delayed |  | Ivan,Gareth Ng | 2026-05-03 16:00 | 2026-05-30 16:00
Production(Full) |  | MAIA: Holsen | Phase 02 | 0. Not Started |  |  | 2026-05-28 16:00 | 2026-05-31 16:00
C1/C3/A57 QA |  | MAIA: Holsen | Phase 01 | 0. Not Started |  | Gareth Ng | 2026-04-21 16:00 | 2026-04-21 16:00
AWS Billing |  | MAIA: Fixguru | Phase 01 | 0. Not Started |  |  | 2026-04-19 16:00
|  | MAIA: Fixguru | Phase 01 | 0. Not Started |  |  | 2026-04-19 16:00
|  | MAIA: Fixguru | Phase 01 | 0. Not Started |  |  | 2026-04-19 16:00
|  | MAIA: Fixguru | Phase 01 | 0. Not Started |  |  | 2026-04-19 16:00
|  | MAIA: Fixguru | Phase 01 | 0. Not Started |  |  | 2026-04-19 16:00
Stock Recon CSV include item name |  | MAIA: Ultimax | Phase 01 | 3. Completed |  |  | 2026-04-15 16:00 | 2026-04-15 16:00
Product Bundle Search Testing (on dev) |  | MAIA: Ultimax | Phase 01 | 2. In Progress |  | Jun Yan Lim | 2026-04-20 16:00 | 2026-04-20 16:00
Work Order Scoping |  | MAIA | Phase 03 | 0. Not Started |  |  | 2026-04-19 16:00
Stock Chup Scoping |  | MAIA | Phase 03 | 0. Not Started |  |  | 2026-04-19 16:00
|  | MAIA | Phase 03 | 0. Not Started |  |  | 2026-04-19 16:00
Data Assessment & Migration Quote |  | MAIA: SCC |  | 0. Not Started |  |  | 2026-04-19 16:00
AWS Account & Billing |  | MAIA: SCC |  | 0. Not Started |  |  | 2026-04-19 16:00
Whatsapp Number |  | MAIA: SCC |  | 0. Not Started |  |  | 2026-04-19 16:00
Meta WABA Setup |  | MAIA: SCC |  | 0. Not Started |  |  | 2026-04-19 16:00
Open AI API Keys |  | MAIA: SCC |  | 0. Not Started |  |  | 2026-04-19 16:00
|  | MAIA: SCC |  | 0. Not Started |  |  | 2026-04-19 16:00
Scope out quotation calculator |  | MAIA: Thermac | Phase 01 | 0. Not Started |  |  | 2026-04-19 16:00
META Account |  | MAIA: Mackessen | Meta WABA | 0. Not Started |  |  | 2026-04-19 16:00
Whatsapp Number |  | MAIA: Mackessen | Meta WABA | 0. Not Started |  |  | 2026-04-19 16:00
Communicate Delay of Batch/SN Tax Quota Enforcement |  | MAIA: Holsen | Phase 02 | 0. Not Started |  | Gareth Ng | 2026-04-20 16:00 | 2026-04-20 16:00
Reseed company name | Reseed company name to "Ultimax Supply Sdn. Bhd." > Ensure all items and document is mapped correctly to the new company name | MAIA: Ultimax | Phase 01 | 0. Not Started |  |  | 2026-04-26 16:00 | 2026-04-26 16:00
|  | MAIA: Holsen | Phase 01 | 0. Not Started |  |  | 2026-04-19 16:00
Go over aws and waba setup and timeline Meeting |  | MAIA: Ultimax | Phase 01 | 0. Not Started |  |  | 2026-04-21 16:00 | 2026-04-21 16:00
SOW Signed | Signed agreement confirming scope, deliverables, and responsibilities | MAIA: GST Fine Foods | Commercial | 0. Not Started |  |  | 2026-05-04 16:00
Initial Payment Received | First payment received to officially start onboarding | MAIA: GST Fine Foods | Commercial | 0. Not Started |  |  | 2026-05-04 16:00
Kickoff & Scope Alignment | Align on onboarding scope, timeline, stakeholders, success criteria | MAIA: GST Fine Foods | Onboarding | 0. Not Started |  |  | 2026-05-04 16:00
Requirement Gathering Completed | All business requirements clarified and signed off by client | MAIA: GST Fine Foods | Commercial | 0. Not Started |  |  | 2026-05-04 16:00
Data Readiness Validation | Validate client-provided item, customer, pricing, tax data | MAIA: GST Fine Foods | Onboarding | 0. Not Started |  |  | 2026-05-04 16:00
Data Mapping & Cleanup | Standardize formats, resolve inconsistencies, prepare for import | MAIA: GST Fine Foods | Onboarding | 0. Not Started |  |  | 2026-05-04 16:00
Item Master Upload | Import and verify item data into system | MAIA: GST Fine Foods | Onboarding | 0. Not Started |  |  | 2026-05-04 16:00
Customer Master Upload | Import and verify customer data into system | MAIA: GST Fine Foods | Onboarding | 0. Not Started |  |  | 2026-05-04 16:00
Pricing Configuration | Configure pricing rules, validate edge cases with client | MAIA: GST Fine Foods | Onboarding | 0. Not Started |  |  | 2026-05-04 16:00
Company Profile Setup | Configure company entity, tax, currency, branding | MAIA: GST Fine Foods | Onboarding | 0. Not Started |  |  | 2026-05-04 16:00
User Setup & Roles | Create users, assign roles, validate access | MAIA: GST Fine Foods | Onboarding | 0. Not Started |  |  | 2026-05-04 16:00
Warehouse & Outlet Setup | Configure operational structure for fulfillment | MAIA: GST Fine Foods | Onboarding | 0. Not Started |  |  | 2026-05-04 16:00
Core Workflow Configuration | Configure order → invoice → payment → delivery workflows for client | MAIA: GST Fine Foods | Onboarding | 0. Not Started |  |  | 2026-05-04 16:00
Edge Case Handling Setup | Configure exceptions (pricing overrides, partial delivery, etc.) | MAIA: GST Fine Foods | Onboarding | 0. Not Started |  |  | 2026-05-04 16:00
AWS Account Coordination | Obtain access, confirm environment ownership and deployment readiness | MAIA: GST Fine Foods | Credentials | 0. Not Started |  |  | 2026-05-04 16:00
AWS Billing Coordination | Confirm billing setup, payment method, ownership | MAIA: GST Fine Foods | Credentials | 0. Not Started |  |  | 2026-05-04 16:00
API & Integration Credential Collection | Collect, validate, and store required API keys and tokens | MAIA: GST Fine Foods | Credentials | 0. Not Started |  |  | 2026-05-04 16:00
Channel Integration Setup | Configure and validate external platform integrations | MAIA: GST Fine Foods | Credentials | 0. Not Started |  |  | 2026-05-04 16:00
WABA Number Verification | Verify phone numbers and ownership for WhatsApp setup | MAIA: GST Fine Foods | Credentials | 0. Not Started |  |  | 2026-05-04 16:00
WABA Setup & Testing | Configure WhatsApp Business and validate messaging flow | MAIA: GST Fine Foods | Credentials | 0. Not Started |  |  | 2026-05-04 16:00
Telegram Setup & Go Live | Configure Telegram bot and validate live messaging flow | MAIA: GST Fine Foods | Credentials | 0. Not Started |  |  | 2026-05-04 16:00
Instance Deployment | Deploy MAIA instance and ensure system accessibility | MAIA: GST Fine Foods | Credentials | 0. Not Started |  |  | 2026-05-04 16:00
Internal QA Testing (Workflows) | Validate full workflow internally before client exposure | MAIA: GST Fine Foods | Milestones | 0. Not Started |  |  | 2026-05-04 16:00
End-to-End Testing | Test full flow with realistic scenarios | MAIA: GST Fine Foods | Milestones | 0. Not Started |  |  | 2026-05-04 16:00
Client UAT Execution | Guide client through real scenario testing | MAIA: GST Fine Foods | Milestones | 0. Not Started |  |  | 2026-05-04 16:00
Issue Fixing & Retest | Resolve issues and revalidate workflows | MAIA: GST Fine Foods | Milestones | 0. Not Started |  |  | 2026-05-04 16:00
User Training Sessions | Train users on real usage | MAIA: GST Fine Foods | Milestones | 0. Not Started |  |  | 2026-05-04 16:00
Go-Live Readiness Check | Final validation before launch | MAIA: GST Fine Foods | Milestones | 0. Not Started |  |  | 2026-05-04 16:00
Go Live | System officially used by client in production | MAIA: GST Fine Foods | Milestones | 0. Not Started |  |  | 2026-05-04 16:00
Final Payment Received | Final project payment completed before closure | MAIA: GST Fine Foods | Commercial | 0. Not Started |  |  | 2026-05-04 16:00
Subscription Start Date | Start of recurring billing / subscription cycle | MAIA: GST Fine Foods | Commercial | 0. Not Started |  |  | 2026-05-04 16:00
Customisation Requirement Scoping | Identify and document all client-specific feature gaps vs MAIA standard | MAIA: GST Fine Foods | Customisation | 0. Not Started |  |  | 2026-05-04 16:00
Customisation Feasibility Assessment | Evaluate technical feasibility, complexity, and trade-offs | MAIA: GST Fine Foods | Customisation | 0. Not Started |  |  | 2026-05-04 16:00
Customisation Scope Lock | Finalize agreed customisations and freeze scope with client | MAIA: GST Fine Foods | Commercial | 0. Not Started |  |  | 2026-05-04 16:00
Customisation Solution Design | Define system design, data flow, and implementation approach | MAIA: GST Fine Foods | Customisation | 0. Not Started |  |  | 2026-05-04 16:00
Customisation Development | Implement client-specific features, logic, or workflows | MAIA: GST Fine Foods | Customisation | 0. Not Started |  |  | 2026-05-04 16:00
Customisation Internal QA | Test custom features internally before exposing to client | MAIA: GST Fine Foods | Customisation | 0. Not Started |  |  | 2026-05-04 16:00
Customisation UAT | Validate custom features with client in real scenarios | MAIA: GST Fine Foods | Milestones | 0. Not Started |  |  | 2026-05-04 16:00
Customisation Fix & Retest | Resolve issues and revalidate custom functionality | MAIA: GST Fine Foods | Customisation | 0. Not Started |  |  | 2026-05-04 16:00
Customisation Sign-Off | Client approval on all custom-built features | MAIA: GST Fine Foods | Commercial | 0. Not Started |  |  | 2026-05-04 16:00
Customisation Deployment to Prod | Deploy custom features into production environment | MAIA: GST Fine Foods | Milestones | 0. Not Started |  |  | 2026-05-04 16:00