Holsen Phase 1 — Backward Plan to Go-Live

## owner: Gareth
status: draft
last_reviewed: 2026-06-21
client: Holsen
phase: 1

End goal: UAT closed + Holsen Sales/Logistics live on Thu 25 Jun 2026
Created: 2026-06-21 | Updated: 2026-06-21
Scope: Core MAIA (A1) — close remaining UAT items → sign-off → client ingests live data → go-live. C1/C3 compliance + PSO + batch/COA enhancements stay post-go-live (see end).

## Milestone Map

NOW ── M1 Close UAT + Sign-off ── M2 Client Data Prep + Ingest ── M3 Go-Live ── M4 Refresher Training Sat Mon Tue–Wed Thu July (date TBC) Jun 21 Jun 22 Jun 23–24 Jun 25

| Phase | Date | Who | Goal |
| --- | --- | --- | --- |
| M1 Close UAT + Sign-off | Mon 22 Jun | Gareth + Dev + Holsen testers | Clear remaining UAT items live; sign-off |
| M2 Client Data Prep + Ingest | Tue–Wed 23–24 Jun | Holsen + PM | Client prepares + ingests live master data |
| M3 Go-Live | Thu 25 Jun | PM + Holsen | Cutover to production; live ops begin |
| M4 Refresher Training | July (date TBC) | PM + Holsen users | Re-train live users post go-live (last session was 3 months ago) |

## ⚠️ Critical path

Go-live is gated on two things landing in order:

UAT sign-off Mon 22 Jun — any unresolved blocker slips the whole chain.

Live data ingested + verified by Wed 24 Jun — client cannot prep data until UAT-confirmed config is frozen.

UAT close (Mon) → data prep + ingest (Tue–Wed) → go-live (Thu). If Monday UAT leaves a blocker open, escalate same day — there is no slack before Thursday.

## M1 — Close UAT + Sign-off (Mon 22 Jun)

Who: Gareth + Dev + Holsen testers
Format: Run every remaining item live on Holsen env; dev fixes on the spot; anything unfixable → explicit defer decision; then sign-off.

### Remaining UAT items (run live)

| # | Item | FE | Chatbot | Owner | Status |
| --- | --- | --- | --- | --- | --- |
| 1 | [TO FILL — remaining open UAT item] | ☐ | ☐ | [TO FILL] | ⬜ |
| 2 | [TO FILL] | ☐ | ☐ | [TO FILL] | ⬜ |
| 3 | [TO FILL] | ☐ | ☐ | [TO FILL] | ⬜ |

Populate from [[MAIA UAT Form - Holsen - 2026-03]] + [[Holsen SOW Feature Checklist]] — list only items still open as of Jun 21.

### Smoke-check (already passing — confirm no regression)

SO creation via WhatsApp (natural language)

Duplicate order prevention (Customer + PO match → blocked)

DO + Picking List generation

Role-based approval flow (SO draft → submit → approve)

### Sign-off

End of session: agree what's green, what's deferred

Holsen testers confirm sign-off (or conditional sign-off + punch list)

Log deferred items → post-go-live backlog

## M2 — Client Data Prep + Ingest (Tue–Wed 23–24 Jun)

Who: Holsen (data owner) + PM (support)
Format: With config frozen post-sign-off, client prepares + loads live master data into the production instance. PM verifies integrity.

Client prepares customer master (final live list)

Client prepares product/SKU master (with pricing, UOM, attributes)

Ingest customer + item master into Holsen production instance

Verify customer-based pricing auto-retrieves correctly on SO

Verify SKU attribute tags (Trading / Mfg / Poison / Commodity) carry through

Confirm role assignments + document permission matrix on production

Confirm Meta/WhatsApp (or @maia_holsen_bot Telegram) channel live and bound to instance

PM data-integrity smoke pass — spot-check seeded records end-to-end

Client cannot start until UAT config is frozen (M1). If data lands late Wed, go-live readiness check slips into Thu morning.

## M3 — Go-Live (Thu 25 Jun)

Who: PM + Holsen
Format: Cutover to production; live order processing begins; PM on standby for hypercare.

Final readiness check — instance + chatbot stable, data verified

Cutover: production live for Sales + Logistics users

First live order processed end-to-end (SO → DO → Pick List → CSV export) with PM watching

PM on standby — hypercare for go-live day issues

Confirm go-live with Holsen; schedule post-go-live check-in

Update [[Onboarding Status]] → live

## M4 — Refresher Training (July — date pending client confirm)

Status (2026-07-06): Stock ingest handover brief sent to client (see UAT/Handover Brief - Holsen 2026 Stock Ingest - 2026-06-26). Pending client to confirm + lock refresher training date. Needs follow-up.

Who: PM + Holsen Sales/Logistics users
Format: Refresher session — last training was Training v3 (5 Mar 2026), ~3 months before go-live. Re-orient live users on current flows now that they're on production. Date to be confirmed with Holsen.

### Agenda

Recap since last training (5 Mar) — what changed, what's now live

Sales flow — SO creation via WhatsApp (natural language), duplicate-order prevention, customer-based pricing auto-retrieval

Approval flow — SO draft → submit → approve; Amend / Request Clarification actions

Logistics flow — DO + Picking List generation, fulfillment method declaration

SKU attribute cues — Trading / Manufacturing / Poison / Commodity tags and what each signals

Daily digests — unclosed SOs, delivery delays, low/out-of-stock alerts

Live Q&A — users raise real issues hit during first weeks of go-live

Confirm next steps — flag any post-go-live feature needs (PSO, C1/C3, batch/COA) for backlog

### Prep checklist

Confirm refresher date with Holsen (July)

Confirm attendees — Sales, Logistics, Finance, Admin users

Prep training slides (refresh from Training v3 deck)

Demo/training instance ready with sample data

Collect go-live-week pain points to address in session

## Commercial — Payment Terms Adjustment

Batch enforcement (Phase A3) delayed as promised → Phase 1 closure payment revised downward.

|  | Original | Revised |
| --- | --- | --- |
| Remaining balance at closure | 50% | 30% |
| Reason | Batch/COA/compliance not delivered in Phase 1 | Deferred to later phase per agreement |

Holsen pays 30% (not 50%) at Phase 1 sign-off. Remaining balance owed when batch enforcement phase ships.

Confirm revised payment terms with Holsen before go-live

Update SOW / commercial record accordingly

## NOT in this go-live scope (post-go-live)

Do not let these creep into 25 Jun:

C3 compliance enforcement (FR-01 to FR-05) — Phase A3

Advanced batch intake, COA handling, K1 traceability — Phase A3 (payment balance held here)

A57 tax exemption enforcement

SQL/AutoCount direct integration (coming August)

Analytics/dashboard FRs (FR-08, FR-09), sticker labels (FR-07), DO bundling (FR-06)

|（注：部分内容可能由 AI 生成）