Macrofood Phase 1 — Backward Timeline to Go-Live

End goal: Sales module live + client trained — originally Fri 26 Jun, slipped twice, now Tue 7 Jul 2026. Core go-live target: end of July / early August.
Created: 2026-06-18 | Updated: 2026-07-06
Scope: Sales module only — confirmed pick list → SO → DN → push to SQL. Invoice/CN, AR recon, credit control deferred (see end).
Model: Structured on the Fixguru 2nd UAT Backward Plan — internal-test-with-live-dev-fix before the client sees it, then on-the-spot UAT during training.

## Slip Log

| Date | Change |
| --- | --- |
| 2026-06-18 | Original plan: go-live 26 Jun |
| ~2026-06-26 | Training pushed off Friday (per 2026-07-01 weekly update) |
| 2026-07-01 | Training rescheduled to Tue 7 Jul |
| 2026-07-02/03 | M1 + M2 complete — instance, Telegram chatbot, SQL sync all live |
| 2026-07-06 | M3 in progress (this week, continue testing); M5 sequence flipped — training first (7 Jul), UAT after — UAT scope now mainly covers customised features (see Customisation Timeline below) |

Open client action: confirm Meta Business verification status (WhatsApp channel) — Telegram fallback already deployed and live.

## Milestone Map

M0 Deps + Kickoff (Jun 18-19) → M1 Instance + Chatbot (Jun 19-22) → M2 SQL + Data Seed (Jun 22-24) → M3 Internal Test + Live Fix (Jun 24) → M4 Stability + UAT Prep (Jun 25) → M5 Training + UAT + GO-LIVE (originally Jun 26, now Jul 7 training / UAT + go-live end of Jul-early Aug)

| Phase | Date | Who | Goal |
| --- | --- | --- | --- |
| M0 Deps + Kickoff | Thu 18–Fri 19 Jun | Gareth + Macrofood | Vendor form out; chase all client deps |
| M1 Instance + Chatbot | ✅ Complete 2-3 Jul | Dev | Deploy on client AWS; chatbot live |
| M2 SQL + Data Seed | ✅ Complete 2-3 Jul | Dev + PM | SQL sync working; master data seeded; PDF config |
| M3 Internal Test + Live Fix | 🟡 In progress (this week) | Gareth + Dev | Test full scope live; fix on spot |
| M4 Stability + UAT Prep | Rolled into M5 prep | PM | Stable; UAT form + training ready; client briefed |
| M5 Training + UAT + Go-live | Training Tue 7 Jul; UAT after; go-live end of Jul / early Aug | PM + Macrofood | Train, UAT (post-training), sign-off, go-live |

## Critical path — SQL vendor (M0 → M2 → M3)

SQL sync was the hard go-live blocker gated on Macrofood's SQL vendor (Mr. Chua, +60 12 212 2126). Vendor delivered; M1 + M2 now complete as of 2-3 Jul.

## M0 — Dependencies & Kickoff (Thu 18 – Fri 19 Jun)

Who: Gareth + Macrofood

SQL integration form sent to vendor (Mr. Chua) — 18 Jun

Client grants AWS account access

Client shares OpenAI account + API key

Client finalizes pick-list workflow

Client sends doc samples (SO, DN) for PDF templates

Client sends company user list

Confirm customer + item master data scope

## M1 — Instance + Chatbot Setup — COMPLETE (2026-07-02/03)

Who: Dev

Deploy MAIA instance on client's AWS

Set up chatbot — Telegram deployed and live; WhatsApp still pending on client side (Meta Business verification)

Connect chatbot to instance; smoke-test basic message flow

Channel: Telegram is live now, not just a fallback. WhatsApp switches over once client clears Meta Business verification.

## M2 — SQL Integration + Data Seed — COMPLETE (2026-07-02/03)

Who: Dev + PM

Vendor returned API credentials + cloned test DB

Build + verify SQL sync — customer/item master read, SO/DN write

Test all write endpoints on cloned test DB (port 8016, firewall/IP whitelist confirmed)

Seed company users + customer/item master data

Configure SO / DN PDF templates from client samples

## M3 — Internal Test + Live Dev-Fix Session — IN PROGRESS (this week)

Who: Gareth + Dev
Status: Testing continues this week, in parallel with M5 training (sequence flipped — training runs first, M3 fixes feed into post-training UAT).

### Go-live scope checklist (run live)

| # | Item | Status |
| --- | --- | --- |
| 1 | Customer master synced from SQL (read) | ⬜ |
| 2 | Item/SKU master synced from SQL (read) | ⬜ |
| 3 | Upload confirmed pick list → MAIA | ⬜ |
| 4 | Create SO from confirmed figures | ⬜ |
| 5 | Generate Delivery Note (DN) | ⬜ |
| 6 | Push SO / DN → SQL (write) | ⬜ |
| 7 | Pricing enforcement (wholesale/retail/customer-specific) | ⬜ |
| 8 | SO / DN PDF renders correctly | ⬜ |

## M5 — Training (Tue 7 Jul) → UAT after (sequence flipped)

Who: PM + Macrofood testers
Format: Training runs first. UAT no longer same-session on-the-spot — it now sits after training and mainly covers the 3 customised features below (see Customisation Timeline). Core sales flow (pick list → SO → DN → SQL) already validated in M3.

Channel for training: Telegram (live) — WhatsApp pending client's Meta Business verification

Brief: what's in scope (pick list → SO → DN → SQL)

Training Slide prep

Demo instance setup ready

Run training session — 7 Jul

UAT (post-training) — mainly customised features, dates TBC below

Sign-off (or conditional sign-off + punch list) → go-live (target: end of July / early Aug)

## Customisation Timeline — 3 Features (dates TBC)

Scope moved out of core Phase 1, now tracked separately. Sequence: A → B → C.

| # | Feature | QA Date | Internal Showcase Date | UAT Date |
| --- | --- | --- | --- | --- |
| A | Bulk Item Price Update | TBC | TBC | TBC |
| B | Slow-moving / Near-expiry Stock Alert | TBC | TBC | TBC |
| C | AR (Reconciliation) | TBC | TBC | TBC |

QA Date — tech ships to product team, product QA starts

Internal Showcase Date — product team demos feature internally before client sees it

UAT Date — client tests the feature live

Target: all 3 features through UAT and go-live-ready by end of July / early August.

## NOT in Phase 1 scope

Invoice, Credit Note → after core sales go-live

AR Reconciliation, Bulk Price Update, Product Catalog, Credit limit control → deployed separately after core go-live (now tracked in Customisation Timeline above)

AP (supplier) reconciliation, Delivery trip management, Warehouse barcode/QR (WMS), Batch tracking, Inventory aging alerts → future phase

## Milestone Dates

| # | Milestone | Date |
| --- | --- | --- |
| 1 | Signed Date | 2026-05-15 |
| 2 | Payment Date (50% upfront) | 2026-05-20 |
| 3 | Kickoff Date | 2026-06-18 |
| 4 | Requirements Lock Date | 2026-06-04 |
| 5 | M1+M2 Complete | 2026-07-02/03 |
| 6 | Training Date | 2026-07-07 |
| 7 | UAT Date | TBC (post-training) |
| 8 | Go-Live Date | TBC (target end of Jul / early Aug) |
| 9 | Customisations Date | TBC (see Customisation Timeline) |

|（注：部分内容可能由 AI 生成）