## Sheet1
SCC CORPORATION SDN BHD — MAIA IMPLEMENTATION ACTION ITEMS
Scope: SCC Corporation Sdn Bhd only (not all 5 entities) · SAP B1 10.0 · AHPD + FSED divisions · Data migration: provided
# | Action Item | Detail / Notes | Category | Owner | Status | Sizing Bucket | Remarks | Effort (md)
PRE-PHASE 1 GATE
1 | Confirm SAP B1 VPN routing from AWS to SCC SAP instance | Three-party vendor meeting done and in progress. Confirm: network path is clear, ports open, Mindhive has test credentials. Do not start integration build until confirmed. | Gate | Mindhive + SAP Vendor | In Progress | Discovery
2 | Confirm SAP B1 Service Layer deployed and accessible | Same question as GST. Must confirm before integration scoping. Verbal confirmation is not enough — test the endpoint. | Gate | SAP Vendor | In Progress | Discovery
3 | Obtain UAT SAP B1 account for Mindhive engineers | Read + write test credentials for all 8 API touchpoints. Required before integration build starts. | Gate | SCC | Not Started | Infrastructure
4 | Lock role-permission matrix for SCC users | Critical dependency for access control build. Sales rep, sales support exec, finance, warehouse, management. Who sees what? Who can create / approve / view only? | Gate | SCC + Mindhive | Not Started | Discovery
5 | Collect Karen's pricing workflow detail | Karen owns pricing. Must understand: tiered pricing rules, customer-specific overrides, how sourced-item pricing is determined pre-purchase, and how landed cost is factored into quotation. | Gate | SCC (Karen) | Not Started | Discovery | Post Core MAIA
6 | Collect Thomas's sales report template | Thomas's reporting requirements must be scoped before build. Confirm whether this is a Phase 1 or Phase 2 item and whether it drives any doctype or dashboard requirements. | Gate | SCC (Thomas) | Not Started | Discovery | Custom Dashboard
7 | Confirm which SAP approval workflows migrate to MAIA vs stay in SAP | Invoice approval → MAIA (eliminate double work). Credit note approval → MAIA. E-invoice submission → stays in SAP. API must bypass SAP's internal approval logic for migrated workflows. Confirm full list with SCC. | Gate | SCC + Mindhive | Not Started | Discovery
8 | Confirm document numbering scheme (quotation, SO, invoice, CN) | Quotations are NOT in the 8 SAP API touchpoints — does QT push to SAP or stay MAIA-only? Confirm explicitly before build. | Gate | SCC | Completed | Discovery | Stays in MAIA Only
9 | Collect sample SAP data exports for all 8 touchpoints | Customer master, item master (AHPD + FSED), pricing, open SOs, open invoices, CNs, pick lists, payment entries. Needed for data model validation. | Gate | SCC | In Progress | Data | Pending exploded view
10 | Collect samples of existing document PDFs (QT, SO, Invoice, DN, CN, Pick List) | Required for PDF layout matching. Both AHPD and FSED document samples if formats differ. | Gate | SCC | In Progress | Data
11 | Confirm stock reservation module commercial treatment | Stock reservation is NOT in signed proposal scope. Decision required: include in Phase 1 as an add-on (re-scope + re-price), or defer to Phase 2. This is a real workflow module, not a config toggle. | Gate | Jeremy / Mindhive | Not Started | Commercial
12 | Confirm landed cost complexity commercial treatment | Sourced-item landed cost calculation (forex, shipping, order consolidation) is a scope gap. Decision: Phase 1 informational display only, or Phase 1 calculator? Must be scoped and priced before build. | Gate | Jeremy / Mindhive | Not Started | Commercial | Landed cost is out of scope currently, keep in this doc for future
13 | Collect physical document samples for digitisation scoping | Pending samples from SCC. Once received, scope the digitisation effort (OCR + structured ingestion) and determine whether it is Phase 1 or Phase 2 and what the commercial treatment is. | Gate | SCC | In Progress | Discovery | Pending their sharing
14 | Confirm scope: SCC Corporation only, single MAIA instance | Single SAP B1 instance shared across 5 entities. MAIA scoped to SCC Corporation only. Integration must filter by entity. Confirm with SAP vendor that entity-level filtering is available via API. | Gate | SAP Vendor + Mindhive | Completed | Discovery
15 | Confirm 5-year historical data migration scope and format | Client requested 5-year historical data migration cost assessment. Scope: which document types, what volume, what format SAP can export. Needed before pricing the migration line. | Gate | SCC + Mindhive | In Progress | Data
INFRASTRUCTURE
1 | Provision AWS environment for SCC MAIA instance | Standard MAIA deployment stack. Separate instance from GST and other clients. Confirm region, sizing, S3, Redis, MariaDB. | Infrastructure | Mindhive | Not Started | Infra Build
2 | Register dedicated phone number for SCC WABA | Separate from other MAIA clients. Start immediately — Meta KYC is slow. Risk of account ban on self-service — Mindhive to supervise. | Infrastructure | SCC | Not Started | Infra / Admin
3 | Create Meta Business Account and submit WABA application for SCC | Mindhive to own process to avoid Meta ban risk. | Infrastructure | Mindhive | Not Started | Infra Build
4 | Provision OpenAI API key for SCC instance | Budget to be included in commercial proposal if not already covered. | Infrastructure | Mindhive / SCC | Not Started | Infra / Admin
SAP INTEGRATION — READ
1 | Build SAP B1 connector: Customer master sync → MAIA | One-way READ. Webhook preferred, cron poll fallback. Entity-scoped to SCC Corporation only. | Integration | Mindhive | In Progress | Build
2 | Build SAP B1 connector: Item master sync → MAIA | One-way READ. AHPD and FSED items. Include category, UOM, pricing flags. Sales rep cannot access SAP directly — item data must be complete and current in MAIA. | Integration | Mindhive | In Progress | Build
3 | Build SAP B1 connector: Pricing sync → MAIA | Standard price lists + customer-specific overrides. Tiered pricing structures must map correctly. Sourced items with null-price enforcement: surface reviewer prompt at quotation time. | Integration | Mindhive | In Progress | Build
4 | Build SAP B1 connector: Inventory/stock sync → MAIA | READ only. Needed for stock reservation visibility and quotation accuracy. Webhook preferred. | Integration | Mindhive | In Progress | Build
5 | Build SAP B1 connector: Credit limit + outstanding sync → MAIA | Pre-submission credit check depends on this. Credit standing must be current — not bi-weekly. | Integration | Mindhive | In Progress | Build
SAP INTEGRATION — WRITE
1 | Build SAP B1 push: Sales Order MAIA → SAP | MAIA is source of truth. On SO confirmation, push to SAP. Eliminate sales support exec as manual SAP entry bottleneck for SOs. | Integration | Mindhive | Not Started | Build
2 | Build SAP B1 push: Sales Invoice / Credit Note / Debit Note MAIA → SAP | On SI/CN/DN creation and approval in MAIA, push to SAP. API must bypass SAP internal approval logic for migrated approval workflows. | Integration | Mindhive | Not Started | Build
3 | Build SAP B1 push: Delivery Note / Return Note MAIA → SAP | On DN/RN creation in MAIA, push to SAP. | Integration | Mindhive | Not Started | Build
4 | Build SAP B1 push: Pick List MAIA → SAP | On pick list confirmation, push to SAP. | Integration | Mindhive | Not Started | Build
5 | Build SAP B1 push: Payment Receipt / Payment Voucher MAIA → SAP | On payment entry confirmation in MAIA, push to SAP. | Integration | Mindhive | Not Started | Build
6 | Integration reconciliation test: all 8 touchpoints | End-to-end test all READ and WRITE paths. Validate entity-scoping (SCC Corporation only). Acceptance metric. | Integration | Mindhive | Not Started | Test
CORE MAIA FLOW
1 | Configure core MAIA document flow for SCC | cRFQ → Quotation → SO → Pick List → DN → SI → Payment Entry. Validate against SCC's actual workflow. Confirm DN/Return Note path and CN/Debit Note path. | Build | Mindhive | Completed | Config
2 | Configure null-price enforcement for sourced items | Sourced items: null price on item master. At quotation time, reviewer is prompted to enter price. Prevents margin absorption from pre-purchase quoting without cost certainty. | Config | Mindhive | Completed | Config | Out of the box, we just need to ensure the SKUs that are sourced are having null std price
3 | Configure credit standing pre-submission check | Before SO confirmation: surface credit limit, outstanding, overdue, available credit from SAP. Credit controller notified + ToDo created if blocked. Audit trail recorded. | Config | Mindhive | Completed | Config | Out of the box, in the FE and Chatbot visual cues
4 | Configure payment proof → draft payment entry workflow | Proof upload → draft payment entry → finance review and confirmation. Eliminates WhatsApp proof screenshots. | Build | Mindhive | Completed | Build | Currently can be done, this is a human workflow, we need to educate on status gating
5 | Configure invoice retrieval by salesperson (no VPN needed) | Sales rep searches and retrieves any invoice from MAIA directly. Forward to customer. Eliminates dependency on sales support exec for invoice access. | Build | Mindhive | Completed | Build | Out of the box
6 | Configure pick list → DN actual quantity capture | Warehouse updates actual picked quantities in MAIA. Flows to DN. Eliminates paper → WhatsApp → re-entry cycle. | Build | Mindhive | Not Started | Build |  | 0.5
7 | Configure role-based access and UserPermission scoping | Based on locked role-permission matrix. Sales reps see their own customers/docs. Finance sees invoices/payments. Management cross-visibility. Replicate SAP per-head licensing relief — unlimited MAIA users. | Config | Mindhive | Not Started | Config | Pending Role Permission Matrix
SCOPE GAP — STOCK RESERVATION
1 | Scope stock reservation module (not in signed proposal) | Stock reservation = reserve committed stock against SO before physical pick. Prevents overselling. This is a proper workflow module. Must scope: reservation trigger, release trigger, partial reservation, expiry rules. | Build | Mindhive | Not Started | Build | Check if stated in SOW, else maybe rengoe or phase it out | 5
2 | Build stock reservation module (if confirmed Phase 1) | On SO confirmation, reserve stock in MAIA. Show available-minus-committed to sales reps at quotation time. Reservation releases on DN completion or SO cancellation. Pending commercial decision. | Build | Mindhive | Completed | Build | Out of the box behaviour already done
3 | Configure stock reservation visibility on quotation/SO creation | Sales rep sees committed vs available stock when selecting items. Prevents quoting stock already committed elsewhere. Requires stock reservation module + SAP inventory sync. | Build | Mindhive | Not Started | Build | Bounty ticket in scoping. | 2
SCOPE GAP — LANDED COST
1 | Scope landed cost display for sourced items | Sourced items: sales rep quotes before purchase is committed. Cost = landed cost (forex + shipping + consolidation + market price). Current risk: margin absorbed if purchase cost exceeds estimated cost at quote time. | Scoping | Mindhive | Next Phase | Scoping | Next Phase
2 | Build landed cost calculator UI (if confirmed Phase 1) | Input: estimated forex rate, shipping cost, consolidation factor. Output: estimated landed cost per unit for margin calculation at quotation. Informational only — does not auto-price. Reviewer sets final price. Pending commercial decision. | Build | Mindhive | Next Phase | Build | Next Phase
3 | Define margin alert threshold for sourced item quotations | If confirmed purchase cost exceeds quoted price by >X%, surface alert to sales manager. Prevents silent margin erosion post-quotation. Threshold to be defined with SCC. | Build | Mindhive | Next Phase | Build | Next Phase
SCOPE GAP — PHYSICAL DOC DIGITISATION
1 | Receive and assess physical document samples from SCC | Pending. Once received: identify document types, volume, condition. Assess OCR feasibility, structure extractability, and integration path into MAIA. | Scoping | SCC + Mindhive | In Progress | Scoping |  | 0.2
2 | Scope and price physical document digitisation effort | Based on samples. Determine: Phase 1 vs Phase 2, commercial treatment (one-time fee vs included), required build (OCR pipeline, structured ingestion, document classification). | Scoping | Mindhive | In Progress | Scoping |  | 0.5
3 | Build physical document digitisation pipeline (if confirmed) | OCR → structured extraction → classified storage in MAIA. Scope depends on document types and volume. Pending samples. | Build | Mindhive | Not Started | Build | High difficulty area is for orders that are still open require linkage to the order in SAP. Closed orders are archived records. | 5
APPROVAL WORKFLOW MIGRATION
1 | Configure invoice approval workflow in MAIA (migrated from SAP) | Invoice approval moves to MAIA to eliminate double work. Finance user approves in MAIA → MAIA pushes confirmed SI to SAP bypassing SAP's internal approval logic. SAP API must support bypass. | Build | Mindhive | Scoping | Build | Require MAIA Workflow here for Invoice Doctype. Dig more into why there is a manual out of system workflow. Can be an upsell? | 9
2 | Configure credit note approval workflow in MAIA (migrated from SAP) | CN approval moves to MAIA. Same pattern as invoice: approve in MAIA → push to SAP bypassing SAP approval. Finance user owns this workflow. | Build | Mindhive | Not Started | Build | Require MAIA Workflow here for Invoice Doctype.
3 | Confirm e-invoice workflow stays in SAP (not migrated) | E-invoice submission remains SAP-side. MAIA does not touch e-invoice flow. Confirm with SAP vendor that the push from MAIA → SAP does not interfere with e-invoice module. | Gate | SAP Vendor + Mindhive | Completed | Discovery | Stays in SAP
4 | Validate SAP API bypass for migrated approval workflows | Before build: test that SAP Service Layer accepts document push from MAIA without triggering SAP's internal approval routing. This is a technical constraint that must be proven, not assumed. | Gate | Mindhive + SAP Vendor | Not Started | Test | Need Jermaine to help
cRFQ / QUOTATION
1 | Configure cRFQ module for SCC AHPD + FSED product catalogue | Load SCC item master into cRFQ knowledge source. Configure domain reasoning for two divisions: animal health (parts by product type + species applicability) and foodservice equipment (parts by machine model + service type). | Build | Mindhive | Out of Scope | Build
2 | Implement null-price enforcement in cRFQ Compose artifact | For sourced items with null price: cRFQ compose artifact flags the line as price-to-be-confirmed. Reviewer is prompted at quotation time. Reasoning engine does not guess a price. | Build | Mindhive | Out of Scope | Build
3 | Test quotation draft generation for SCC order profile | Target: ≥80% product match without correction, ≥95% line item completeness, ≥50% QT preparation time reduction. Sample set from SCC historical quotations. | UAT | Mindhive + SCC | Next Phase | UAT
4 | Configure customer preference semantic capture for SCC | RAG-based retrieval on QT/SO remarks. Surfaces historical preferences on new document creation. Reduces dependency on sales support exec knowledge. Wow feature for adoption. | Build | Mindhive | Next Phase | Build
PDF GENERATION
1 | Build QT PDF matched to SCC document sample | Layout must match SCC's current quotation format. Collect sample before build. | Build | Mindhive | Not Started | Build | Use back SAP Service Layer PDF Generator | 1
2 | Build SO PDF |  | Build | Mindhive | Not Started | Build | Use back SAP Service Layer PDF Generator
3 | Build DN/Return Note PDF |  | Build | Mindhive | Not Started | Build | Use back SAP Service Layer PDF Generator
4 | Build Sales Invoice PDF |  | Build | Mindhive | Not Started | Build | Use back SAP Service Layer PDF Generator
5 | Build Credit Note / Debit Note PDF |  | Build | Mindhive | Not Started | Build | Use back SAP Service Layer PDF Generator
6 | Build Pick List PDF |  | Build | Mindhive | Not Started | Build | Use back SAP Service Layer PDF Generator
7 | SCC sign-off on all PDF layouts | All document types reviewed and approved before UAT. Gate for PDF acceptance metric. | UAT | SCC | Not Started | UAT
DATA MIGRATION
1 | Extract and load customer master from SAP → MAIA | One-time historical load. Entity-scoped to SCC Corporation. Validate count and key fields. | Data | Mindhive | Scoping | Build
2 | Extract and load item master from SAP → MAIA | AHPD + FSED items. Include pricing flags, category tags, null-price markers for sourced items, applicability metadata for cRFQ. | Data | Mindhive | Scoping | Build
3 | Extract and load pricing / price lists from SAP → MAIA | Standard + customer-specific overrides. Tiered structures. Validate against SAP spot-check. | Data | Mindhive | Scoping | Build
4 | Extract and load open SOs and outstanding balances | Day-0 state must be accurate for credit standing and active order visibility. | Data | Mindhive | Scoping | Build
5 | Price and scope 5-year historical data migration | Client requested cost assessment. Scope by document type and volume. Price as separate line item — this is not included in standard MAIA onboarding. Confirm export format from SAP. | Data | Mindhive | Scoping | Commercial |  | TBD
6 | Execute 5-year historical data migration (if confirmed) | Pending commercial sign-off. Migrate SO, QT, SI, CN, DN, Payment history for preference mining and reference. | Data | Mindhive | Scoping | Build |  | TBD
7 | Reconcile migrated data against SAP | Verify all loaded records match SAP export. Acceptance metric gate. | Data | Mindhive + SCC | Scoping | UAT
NOTIFICATIONS & TODO
1 | Configure credit block notification → finance / sales manager | On SO submission with credit breach: Detail notification to credit controller. ToDo created. Audit trail. | Build | Mindhive | Completed | Config | out of the box
2 | Configure invoice approval routing → finance user | On SI creation: notify finance user for approval. Replaces SAP internal routing. | Build | Mindhive | Scoping | Config
3 | Configure credit note approval routing → finance user | On CN creation: notify finance user for approval. Replaces SAP internal routing. | Build | Mindhive | Scoping | Config
4 | Configure payment proof upload → finance ToDo | On proof upload, route to finance queue. Auto-close on payment confirmation. | Build | Mindhive | Not Started | Config
5 | Configure stale SO / stale quotation alerts | SOs and QTs open past threshold with no progression. Sales manager + rep notified. | Build | Mindhive | Completed | Config
6 | Configure comment tagging notifications across all doctypes | @mention routing. Replaces WhatsApp coordination for document-specific discussions. | Build | Mindhive | Completed | Config
UAT / COMMERCIAL
1 | Define Phase 1 acceptance metrics for SCC | Model after GST framework. Must include: SAP sync accuracy, document push accuracy, null-price enforcement, credit standing accuracy, approval routing, pick qty accuracy, PDF format, historical data completeness. | Planning | Mindhive | Not Started | Planning
2 | Prepare UAT sample set for quotation testing | Min 15-20 real QT scenarios from SCC history. Cover: AHPD parts, FSED service packages, sourced items with null price, tiered pricing, credit-blocked customers. | UAT | Mindhive | Not Started | UAT
3 | Run Phase 1 UAT against all acceptance metrics | Systematic test per metric. Document pass/fail. Gate for Phase 1 payment milestone. | UAT | Mindhive + SCC | Not Started | UAT
4 | Collect Phase 1 payment milestone | Trigger: Phase 1 UAT pass per signed proposal. | Commercial | Mindhive | Not Started | Commercial
5 | Monitor daily MAIA transaction counts post go-live | Silent adoption failure detection. Key risk: sales reps bypassing MAIA and going back to verbal/WhatsApp ordering. Daily count monitoring is the detection mechanism. | Post Go-Live | Mindhive | Not Started | Monitoring
6 | Present Phase 2 scope to SCC after 30-day adoption gate | Phase 2 items: stock reservation (if deferred), landed cost calculator (if deferred), physical doc digitisation, Thomas's reports, structured customer preferences, management dashboards. | Commercial | Mindhive | Not Started | Planning