## Slide 1
maia
USER ACCEPTANCE TESTING · GO-LIVE READINESS
Macro Frozen × MAIA
Core Order Workflow UAT
Session run by AutorunBiz PLT × MAIA · Facilitator: Ivan · Walkthrough: Gareth
28 July 2026
Macro Frozen office
1:00 – 3:15 p.m.
Hard stop 3:15 p.m.
THE ONLY OUTPUT THAT MATTERS
A go-live decision
by 3:15 p.m.
GREEN
AMBER
RED
Evidence-based, not opinion-based.
Notes: Open by naming the purpose: this is hands-on UAT, not a demo. The session succeeds only if we can make a defensible Green/Amber/Red call by 3:15.

## Slide 2
PURPOSE
What today decides
This is a hands-on User Acceptance Test, not a product demonstration. We are checking whether your team can run the core order workflow themselves.
1
The workflow works end to end
Customer order → Sales Order → Pick List → Delivery Note → Invoice → SQL.
2
Each user can do their own job
Not Gareth driving. Your people, your accounts, your roles.
3
Controls block what they should
Permissions, price approval tiers and credit checks are tested by trying to break them.
4
The workflow is safe to go live
After the final production-data synchronisation.
Success = the evidence supports a clear Green, Amber or Red decision before 3:15 p.m.
Anything we cannot prove today becomes a logged defect with an owner and a date — not an assumption.
Notes: Emphasise: we test prohibited actions as well as permitted ones. A control that has never been tried is not a control.

## Slide 3
RUNNING ORDER
Agenda — 1:00 to 3:15 p.m.
1:00 – 1:15
Introduction, changes since last UAT, data notice
Ivan
1:15 – 1:30
One-order guided walkthrough
Gareth
1:30 – 1:40
Confirm operating model and roles
Ivan + David
1:40 – 2:05
Scenario 1 — Lead → Customer → non-PO kg order
Queenie + team
2:05 – 2:30
Scenario 2 — formal PO and carton order
Grace, Ben, CJ
2:30 – 3:05
Scenario 3 — live order and Pick List PDF
Whole Macro Frozen team
3:05 – 3:15
Results and go-live decision
Ivan + David
85
minutes hands-on
with your team
Parking lot
Anything off today's scope gets written down and owned — not debated in the room.
Hard stop 3:15 p.m.
The decision is made inside the session.
Notes: Highlighted rows are hands-on. Keep the walkthrough to one order and 15 minutes — no feature tour.

## Slide 4
GROUND RULES
How we will run the session
1
Your hands on the keyboard
Gareth demonstrates once, then observes. If we have to take over, that is a finding and we log it.
2
We test what must be blocked
Ben will try to open Queenie's Lead. Lai will try to submit a Delivery Note. Both must fail.
3
Known data issue ≠ product defect
Before logging a missing record: is it after 3 July, or on the known exception list?
4
Everything unresolved gets an owner
Blocker, impact, workaround, owner, date. No open items leave this room unassigned.
If something is genuinely broken, we want to find it here — not on Monday with a real customer waiting.
Notes: Set the tone: finding defects today is a good outcome, not an embarrassment.

## Slide 5
CHANGES SINCE THE LAST UAT · 1 OF 2
What is different this time
1
Leads only — Prospect hidden
One place for new opportunities. Leads carry notes and details, then convert into a Customer with the information intact.
No more deciding between Lead and Prospect.
2
Box orders on kilogram items
An agreed method for customers who order in cartons when the item is priced by weight.
See the next slide for the exact rule.
3
Improved Pick List PDF
Clearer customer details, better layout, practical space for handwriting, and re-upload back into MAIA.
Must be judged in the warehouse, not on screen.
4
Shipping address on Customer Listing
Delivery locations are now visible in the listing to help group orders by route or area.
Lai will use this in Scenario 2.
5
Near-expiry and low-stock alerts
Version 1 has shipped — notifications plus a report, with PDF output for users. Still being improved.
Refinements land in the first week of August.
6
Excel-like bulk price setting
An Excel-style editing experience with pivot table views by item or by customer.
For awareness — not an acceptance target today.
Everything on these two slides is presented so nobody mistakes a deliberate change for a defect.

## Slide 6
CHANGES SINCE THE LAST UAT · 2 OF 2
What is different this time
7
SQL data synchronised to 3 July 2026
A full synchronisation is loaded, with a short list of known source-data exceptions.
Covered in detail in two slides.
8
SCN / CCN adapter hardening
Both document flows work today, but the adapter is still being hardened.
Target: first week of August.
9
Purchasing page hidden
MAIA does not support a Purchasing Module for Macro Frozen. Hiding the page also keeps costing information out of view for current users.
Nobody builds a habit on a workflow we do not run.
10
Goods Receive Note stays in SQL
GRN creation, stock receiving and purchasing-related stock entry continue in SQL, unchanged.
By design — not a gap in today's test.
Everything on these two slides is presented so nobody mistakes a deliberate change for a defect.

## Slide 7
THE RULE THAT MATTERS MOST
Kilograms, cartons, and what actually gets billed
The billed quantity is always the actual picked weight. Never a guess made at order entry.
CUSTOMER ORDERS IN KG
Customer order
20.00 kg
Sales Order quantity
20.00 kg
Actual picked
19.71 kg
Billed on the Delivery Note and Invoice
19.71 kg
A short pick is normal. The customer is billed for what actually left the warehouse, not what was ordered.
CUSTOMER ORDERS IN CARTONS
Additional Notes
“2 cartons”
Sales Order quantity
1 kg placeholder
Carton 1 picked
10.44 kg
Carton 2 picked
11.82 kg
Billed on the Delivery Note and Invoice
22.26 kg
Carton count goes in Additional Notes. The 1 kg placeholder holds the line. Real weight is confirmed at picking.
Automatic splitting of document lines is not built yet, so Lai breaks the picked total into individual weight lines by hand, and Grace checks it before submitting.
Notes: This is the single most misunderstood rule. Make Queenie and Ben repeat it back before moving on.

## Slide 8
HONEST STATUS
What is not ready — and not part of today's acceptance
Sales Dashboard by salesperson
Estimated first week of September
Product Catalogue Generator
Estimated mid-September
AR bank-statement reconciliation and OR creation in SQL
Estimated mid-September
Packing List Excel extraction
Not completed — not part of the adopted workflow
Automatic line splitting across SO, DO and Pick List
Not completed — manual breakdown continues
Goods Receive Note creation for stock entry
Outside current MAIA scope — continue in SQL
Also out of scope today
Purchasing module workflows
Delivery-route management
Driver application
Barcode / QR scanning
AP and supplier payments
Cosmetic-only improvements
RESOLVED SINCE LAST REVIEW
Proof of Delivery is now confirmed in scope — capture and storage are part of today's acceptance.
None of the above blocks go-live for the core order workflow. They are tracked with their own dates.
Notes: Say this early and plainly. If the client discovers a gap themselves later in the session, trust drops.

## Slide 9
BEFORE WE START TESTING
What is in the UAT data
3 JULY 2026
SQL synchronisation cut-off
for this environment
Before logging a missing record
1
Is it dated after 3 July?
2
Is it on the known exception list?
3
Does it exist in SQL at all?
4
Only then classify it as a defect.
Records that could not be synchronised
Exception | Count | Amount | Current understanding
Payment Entries with missing Invoice references | 8 | RM593,457 | Linked Invoices are suspected deleted
Zero-amount Payment Entries | 6 | RM0 | No accounting-ledger impact
Delivery Note with zero quantity | 1 | — | Invalid or incomplete DN record
These are existing source-data issues, not new MAIA defects.
They are tracked separately for data remediation. Today we are validating workflow, permissions, controls, documents and the valid synchronised records. If a newer customer, item, price or document is missing, we check the cut-off and the exception list before treating it as a defect.
Notes: Read the client-facing wording almost verbatim. This slide protects the defect log from noise.

## Slide 10
WHERE WE STARTED
Before MAIA — today's order-to-invoice flow
17 steps
from customer order to filed proof of delivery
One bottleneck
David reads, interprets and consolidates every message
Three re-entries
Excel packing list, fresh template, then SQL by hand
Every re-entry is a chance to bill the wrong weight.
Notes: Do not dwell. This slide exists to make the after-state feel earned.

## Slide 11
THE ADOPTED TARGET — APPROACH 1
After MAIA — the workflow we are testing today
No separate Excel Packing List
The Pick List becomes the Draft Delivery Note directly.
One source of quantity
Actual picked weight flows through DN and Invoice.
Controls built into the flow
Price approval and two credit checks, before anything ships.
Worked example — picked total 99.20 kg becomes DN lines of 19.80 + 20.10 + 19.65 + 19.90 + 19.75 kg
Notes: Confirm out loud with David that Approach 1 is still the adopted model before starting the scenarios.

## Slide 12
CONFIRM THE OPERATING MODEL
Who does what today
D
David
Owner · Credit & Price Controller
Approves below-minimum prices. Shares credit overrides with Finance. Final go-live call.
C
CJ
Sales Manager & Sales User
Sees the whole sales team. Approves mid-tier price exceptions. Runs own orders too.
Q
Queenie
Sales User
Own Leads and customers. Forwards orders to MAIA, reviews the draft, submits the SO.
B
Ben
Sales User
Own Leads and customers. Forwards orders to MAIA, reviews the draft, submits the SO.
L
Lai
Warehouse Manager
Pick List, actual picked quantity, box weights, Draft Delivery Note. Cannot submit a DN.
G
Grace
Finance · Credit Controller
Formal PO intake, reviews every DN line, submits the DN, then creates the Invoice.
Every named user logs in with their own account. No shared credentials during UAT or after go-live.

## Slide 13
ACCESS CONTROL
Who can see what — and what nobody can see
Sales Users
Queenie · Ben
Own Leads & customers only
Own Sales Orders only
Can't see each other's records
Sales Manager
CJ
Sees whole sales team
Approves mid-tier prices
No credit-override rights
Owner
David
Sees everything
Sets any price tier
Approves credit overrides
Only one who sees cost price
Finance
Grace · Apple
Credit controllers
View prices, can't set them
No cost-price visibility
“See all” never means see everything — the negative tests we will run
Queenie cannot see Ben's Leads or customers
Ben cannot see Queenie's Leads or customers
Sales users cannot approve their own price exception
CJ cannot approve below the minimum price
Grace and Apple cannot set or approve any price
Lai cannot submit a Delivery Note
Sales users cannot edit credit limits
Only David, Grace or Apple can approve a credit override
Only David can see product buying cost
Notes: These are not theoretical. QA has attempted each one; we will re-attempt live in the scenarios. Credit-override authority sits with the credit controllers — David, Grace and Apple — not with CJ or sales. Price authority stays with David and CJ only; Grace and Apple can view any price but never set one.

## Slide 14
CONTROLS
Price approval and credit checks
Three-tier price approval
At or above the approved customer price
Auto-proceed
No approver
Below customer price, above the minimum
Approval required
CJ
Below the minimum price
Approval required
David
Hard rules
Sales users can never approve their own price · CJ can never approve below the minimum · Grace and Apple can view any price but never set one
Today, approving means CJ or David open the order themselves, set the price, and submit it — the requester tags them with a comment to notify.
Credit checks run twice
1
At Sales Order submission
Before the order enters the warehouse queue.
2
Again at Delivery Note stage
Before goods leave and before invoicing.
Each check tests
Outstanding balance
Credit limit
Overdue position
Previous invoice clearance, where required
David, Grace or Apple — the credit controllers — approve an override.

## Slide 15
SCOPE
What we are accepting today
Included in today's acceptance
Access
Logins, roles, permissions, sales ownership limits, manager oversight
Leads
Creation, notes, conversion to Customer, information carry-over
Order intake
WhatsApp forwarding, Draft SO, customer and SKU matching, user corrections
Units, price, credit
Kilogram orders, carton requests, approval routing, credit check at SO and re-check at DN
Warehouse
Pick List creation and grouping, shipping-address columns, MAIA's own PDF layout, re-upload, actual quantities and box weights
Documents
Draft DN from Pick List, review, submission, Invoice creation, POD capture. SO, Invoice and DN keep the SQL PDF layout.
Data
SQL synchronisation, record integrity, duplicate-document controls
Not acceptance-gated today
Sales Dashboard by salesperson
Product Catalogue Generator
AR bank-statement reconciliation
Official Receipt creation from AR
Packing List Excel extraction
Automatic document-line splitting
Goods Receive Note creation
Purchasing module workflows
Full product catalogue workflow
Delivery-route management
Driver application
Barcode / QR scanning
AP and supplier reconciliation
Near-expiry / low-stock refinements
Cosmetic-only improvements
Anything outside the left column goes to the parking lot with an owner — it does not change today's decision.

## Slide 16
SCENARIO 1 · 1:40 – 2:05 · PRIMARY USER: QUEENIE
Lead → Customer → non-PO kilogram order
Validate the simplified Lead model, notes carry-over, sales ownership restrictions, and a standard kilogram order end to end.
Steps
1
Queenie creates a Lead and adds customer notes
2
Ben attempts to open Queenie's Lead — access must be denied
3
Queenie converts the Lead to a Customer; notes and ownership carry over
4
Queenie forwards a 20 kg order; MAIA drafts the SO; she reviews and submits
5
Approved price auto-proceeds; credit check passes
6
Lai creates the Pick List; actual picked quantity is 19.71 kg
7
Lai completes the Pick List, creates the Draft DN, splits the box weights
8
Lai attempts to submit the DN — must be denied
9
Grace reviews and submits the DN, then creates the Invoice; verify SQL
Pass criteria
Prospect is not visible anywhere
Ben is blocked from Queenie's Lead
Notes and ownership survive conversion
Billing uses the actual 19.71 kg
Every permission holds
SQL records are correct
Red-numbered steps are actions that MUST fail. If they succeed, that is a blocker.
Notes: Scenario 1. Keep to the window. If the scenario stalls, log the blocker and move on — the decision at 3:15 matters more than a completed run.

## Slide 17
SCENARIO 2 · 2:05 – 2:30 · PRIMARY USERS: GRACE, BEN, CJ
Formal PO and carton order
Validate formal PO intake, the carton rule on a kilogram-based item, and middle-tier price approval routing.
Steps
1
Grace uploads the customer PO; MAIA extracts customer, item and PO reference
2
Ben verifies customer & SKU; notes “2 cartons” with the 1 kg placeholder
3
Ben attempts to set the price himself — must be denied
4
Ben tags CJ in a comment to request approval
5
CJ opens the SO, sets the price, and submits; SO credit check passes
6
Lai groups the order using the shipping address and prints the Pick List PDF
7
Warehouse records carton weights of 10.44 kg and 11.82 kg
8
Pick List uploaded and completed; Draft DN total confirms at 22.26 kg
9
Grace reviews, submits the DN and creates the Invoice; verify SQL
Pass criteria
PO mapping works
The carton rule is followed exactly
Self-approval is blocked
CJ can set and submit an eligible price
Shipping address supports grouping
The printed PDF is usable for handwriting
Final quantity is 22.26 kg
Red-numbered steps are actions that MUST fail. If they succeed, that is a blocker.
Notes: Scenario 2. Keep to the window. If the scenario stalls, log the blocker and move on — the decision at 3:15 matters more than a completed run.

## Slide 18
SCENARIO 3 · 2:30 – 3:05 · USERS: THE ENTIRE MACRO FROZEN TEAM
Live operational order
Prove the real team can run a real order without Gareth taking over. Real order, real accounts, real roles. Gareth and Ivan observe; every assist is logged.
Steps
1
Salesperson receives the order and forwards it to MAIA
2
Salesperson reviews the Draft SO and submits it
3
Price and credit controls run
4
Lai groups the order using shipping information and produces the Pick List
5
Warehouse records the actual picked quantity and box weights
6
Lai completes the Pick List and creates the Draft DN
7
Lai splits the actual line weights; DN credit check runs
8
Grace reviews, submits the DN and creates the Invoice; verify SQL
9
The team explains each handoff in their own words
Pass criteria
Users operate independently
Visibility rules hold under real use
Handoffs are clear to the team itself
The PDF is practical in the warehouse
Quantities and SQL records are correct
Nobody falls back to the old Excel process
No scripted denials here — this run is judged on whether the team gets through it unaided.
Notes: Scenario 3. Keep to the window. If the scenario stalls, log the blocker and move on — the decision at 3:15 matters more than a completed run.

## Slide 19
DISCIPLINE
How we classify what we find
BLOCKER
Core workflow is unsafe or impossible
Red unless fixed and re-tested
MAJOR WITH WORKAROUND
Core works with a controlled workaround
Amber is possible
MINOR
No material effect on correctness
Does not block go-live
ENHANCEMENT
A future improvement
Parking lot
KNOWN DATA EXCEPTION
An existing SQL source-data issue
Tracked separately from defects
Classification happens in the room, by agreement — not afterwards by email.

## Slide 20
3:05 – 3:15 P.M.
The go-live decision
GREEN
Proceed to go-live
Critical scenarios pass
Accounts and permissions correct
Sales ownership restrictions hold
Manager visibility is in place
Pick List PDF is usable
Price and credit controls work
Actual quantity drives DN and Invoice
SQL records are correct
No blocker remains
AMBER
Proceed with conditions
No data-integrity risk remains
No permission risk remains
The workaround is documented
An owner is assigned
An expiry date is set
Macro Frozen accepts the constraint
RED
Do not go live
Sales users can see each other's records
Manager visibility is missing
Account setup is incomplete
Unauthorised approval or submission is possible
Wrong customer, item, quantity, price or weight
Duplicate documents are created
SQL write failure
Pick List PDF is unusable
Users cannot complete the flow alone
Live two-way synchronisation is never enabled after a Red decision.

## Slide 21
AFTER A GREEN OR APPROVED AMBER
The go-live transition and what follows
1
Catch-up sync
Run the final SQL synchronisation up to the current date and time.
2
Reconcile
Check key record counts and control totals against SQL.
3
Confirm exclusions
Verify the known excluded records remain documented.
4
Enable live sync
Turn on ongoing two-way synchronisation between MAIA and SQL.
5
Smoke test
Run a controlled post-sync test on a real order before opening it up.
6
Official go-live
The MAIA workflow becomes Macro Frozen's live operating process.
7
Hypercare group
MAIA sets up a WhatsApp group for live support, issue resolution, bug reports and improvement feedback.
8
Subscription starts
The balance of the set-up fee falls due only on delivery of all customisations.
9
Virtual UAT per release
We run a virtual UAT session for each customisation feature as it ships.
Items still in build — dashboard, catalogue generator, AR reconciliation, near-expiry refinements — continue on their own dates and do not gate this transition.
Notes: Steps 1-5 are technical. Step 6 is the commercial moment. Steps 7-9 are the support model: hypercare WhatsApp group, subscription start with the set-up fee balance held against delivery of all customisations, and a virtual UAT for each customisation as it ships.

## Slide 22
CLOSING THE SESSION
Today's result
GREEN
AMBER
RED
We tested the revised workflow, the simplified Lead model, sales ownership restrictions, manager visibility, carton handling on kilogram items, the improved Pick List PDF, shipping-address grouping, actual-weight processing, approvals, documents and SQL synchronisation.
Still outside today's acceptance
Sales Dashboard · Product Catalogue Generator · AR reconciliation · Packing List Excel extraction · Automatic document-line splitting · Goods Receive Note creation
Next step
On approval we run the catch-up synchronisation, reconcile the records, enable live two-way sync, then go live. A hypercare WhatsApp group opens the same day.
Every open item leaves here with an owner and a date.
maia
Macro Frozen × MAIA · Core Order Workflow UAT · 28 July 2026
Notes: Read the result out loud, confirm it with David, and confirm the owner and date of every open item before anyone leaves.